## Project Summary
Project Summary Report |  | Updated up to
DETAILS | AMOUNT | %
TOTAL CONTRACT VALUE (Original) | 15625800 | 100%
TOTAL ISSUED VALUE | 6705488 | 42.91%
TOTAL COMPLETED VALUE | 4502913 | 67.15%
BALANCE TO BE ISSUED | 8920312 | 57.09%
Work to be Executed | 2202575 | 14.1%
TOTAL INVOICED VALUE AS OF | 3703027 | 23.7%
TOTAL INVOICED VALUE FROM CONTRACT |  | 0%
BALANCE VALUE AS OF CONTRACT | 11922773 | 76.3%
READY FOR INVOICE | 0 | 0%
BALANCE TO BE INVOICED | 799886 | 17.76%

## BOQ MASTER
CONTRACT # GTC=1240/2024-EXTENSION OF U/G LV MAINS NETWORK & SERVICE CONNECTIONS-BOQ-MASTER STATUS
SL | CWR | CWR No. | Received Date | CWR Start Date | Tentative RO expected Date | CWR Completion Date | Shut Down/Return Date | Type of job | (MOC/BP/OFF Load) NO | Total Days | Work Order No | SITE STATUS | RO Number | RO STATUS | RO Approved Date | RO Expiry Date | JOB Done By | SS no | No of Service | Location | 1.1 - Cable |  | 1.2 R/C Existing |  | 1.3 R/C Future |  | 1.4 Reinstatement |  | 1.5 Special Reinstatement |  | 1.6 Phase-2 |  | 1.7 MCCB installation |  | 2.1 Termination |  | 2.2 ST |  | 2.3 PE |  | 2.4 TEE |  | 2.5 Pole term |  | 2.6 mccb supply(W/O Enclosure) |  | 2.7 mccb supply & Enclousre |  | Value |  | Final Status | Invoice Status | Invoice # | KM-CWR | KM-Invoiced AMT | DIF CWR | DIF AMT | Work Completed month | Final Inspection | Final Status
[21 empty] | EEC61525 |  | EEC61541 |  | EEC61542 |  | EEC61543 |  | EEC154309 |  | EEC158944 |  | EEC37611 |  | EEC61537 |  | EEC61536 |  | EEC61533 |  | EEC61535 |  | EEC61538 |  | EEM37607 |  | EEM37608 |  | Issued | Completed
[21 empty] | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp.
1 | 239462 | 1 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-09-17 | 2025-09-30 | DS | MOC-229130 | 13 | 1140013 | Completed | RO NA | RO NA | NA | NA | NEWCON | 17758 | 1 | New District Of Doha 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 1 | 1 | 0 | 0 | 520 | 520 | Invoiced | Invoiced | 5 | 1 |  |  |  | 2025-09-01 | Completed | Invoiced
2 | 239463 | 2 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-09-17 | 2025-09-25 | DS | C-126221(MSA-18035782 | 8 | 1140015 | Completed | 803226 | Approved/Printed | 2025-09-18 | 2025-10-03 | NEWCON | 21949 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1678 | 1678 | Invoiced | Invoiced | 2 | 2 |  |  |  | 2025-09-01 | Completed | Invoiced
3 | 239464 | 3 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-09-17 | 2025-09-16 | DS | C-189423(MSA-18035002) | -1 | 1140038 | Completed | 802824 | Approved/Printed | 2025-09-14 | 2025-09-28 | NEWCON | 13815 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 9 | 9 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2206 | 2206 | Invoiced | Invoiced | 1 | 3 |  |  |  | 2025-09-01 | Completed | Invoiced
4 | 239465 | 4 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-09-17 | 2025-09-17 | DS | C-17520(MSA-18035053 | 0 | 1140052 | Completed | 802825 | Approved/Printed | 2025-09-13 | 2025-09-29 | NEWCON | 1022 | 1 | Al Mirqab Al Jadeed/Al Nasr (39 ) | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2146 | 2146 | Invoiced | Invoiced | 1 | 4 |  |  |  | 2025-09-01 | Completed | Invoiced
5 | 239466 | 5 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-09-17 | 2025-09-16 | DS | MOC-196766 | -1 | 1140094 | Completed | 802824 | Approved/Printed | 2025-09-14 | 2025-09-28 | NEWCON | 5106 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2086 | 2086 | Invoiced | Invoiced | 1 | 5 |  |  |  | 2025-09-01 | Completed | Invoiced
6 | 239467 | 6 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-09-17 | 2025-09-21 | DS | MOC-241227 | 4 | 1140107 | Completed | 803227 | Approved/Printed | 2025-09-17 | 2025-10-02 | NEWCON | 1589 | 1 | New District Of Doha 65 | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1735 | 1735 | Invoiced | Invoiced | 3 | 6 |  |  |  | 2025-09-01 | Completed | Invoiced
7 | 239486 | 7 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-09-17 | 2025-09-16 | DS | MOC-246940 | -1 | 1140402 | Completed | 802824 | Approved/Printed | 2025-09-14 | 2025-09-28 | NEWCON | 4199 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 29 | 29 |  |  |  |  | 29 | 29 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 1 | 0 | 0 | 4543 | 4543 | Invoiced | Invoiced | 1 | 7 |  |  |  | 2025-09-01 | Completed | Invoiced
8 | 239473 | 8 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-09-17 | 2025-09-22 | DS | C-1036145(MSA-18034975) | 5 | 1140358 | Completed | 803255 | Approved/Printed | 2025-09-17 | 2025-10-02 | NEWCON | 3607 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1678 | 1678 | Invoiced | Invoiced | 1 | 8 |  |  |  | 2025-09-01 | Completed | Invoiced
9 | 239474 | 9 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-09-17 | 2025-09-22 | DS | C-1157544A(MSA-18034957) | 5 | 1140359 | Completed | 803255 | Approved/Printed | 2025-09-17 | 2025-10-02 | NEWCON | 17316 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1678 | 1678 | Invoiced | Invoiced | 1 | 9 |  |  |  | 2025-09-01 | Completed | Invoiced
10 | 239475 | 10 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-09-17 | 2025-09-25 | DS | C-153570A(MSA-18031116) | 8 | 1140361 | Completed | 803229 | Approved/Printed | 2025-09-20 | 2025-10-05 | NEWCON | 4519 | 1 | Abu Nakhla / Mukainess (81 ) | 10 | 10 |  |  |  |  | 0 | 0 |  |  |  |  | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 |  |  | 2400 | 2400 | Invoiced | Invoiced | 2 | 10 |  |  |  | 2025-09-01 | Completed | Invoiced
11 | 239476 | 11 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-09-17 | 2025-09-21 | DS | MOC-243788 | 4 | 1140371 | Completed | 803039 | Approved/Printed | 2025-09-15 | 2025-09-30 | NEWCON | 13512 | 1 | Al Kheesa (70 ) | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1450 | 1450 | Invoiced | Invoiced | 2 | 11 |  |  |  | 2025-09-01 | Completed | Invoiced
12 | 239477 | 12 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-09-17 | 2025-09-21 | DS | MOC-242923 | 4 | 1140375 | Completed | 803039 | Approved/Printed | 2025-09-15 | 2025-09-30 | NEWCON | 24873 | 1 | Al Kheesa (70 ) | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1390 | 1390 | Invoiced | Invoiced | 2 | 12 |  |  |  | 2025-09-01 | Completed | Invoiced
13 | 239479 | 13 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-09-17 | 2026-09-12 | DS | MOC-220551 | 360 | 1140382 | Completed | 803246 | Approved/Printed | 2025-09-28 | 2025-10-13 | NEWCON | 36998 | 1 | Al Kheesa (70 ) | 5 | 5 |  |  |  |  | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1735 | 1735 | Invoiced | Invoiced | 4 | 13 |  |  |  | 2025-09-01 | Completed | Invoiced
14 | 239480 | 14 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-09-17 | 2025-09-25 | DS | MOC-235193 | 8 | 1140386 | Completed | 803226 | Approved/Printed | 2025-09-18 | 2025-10-03 | NEWCON | 12409 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2146 | 2146 | Invoiced | Invoiced | 1 | 14 |  |  |  | 2025-09-01 | Completed | Invoiced
15 | 239481 | 15 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-09-17 | 2025-09-22 | DS | MOC-227361 | 5 | 1140387 | Completed | 803255 | Approved/Printed | 2025-09-17 | 2025-10-02 | NEWCON | 13060 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 7 | 7 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1969 | 1969 | Invoiced | Invoiced | 2 | 15 |  |  |  | 2025-09-01 | Completed | Invoiced
16 | 239482 | 16 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-09-17 | 2025-09-17 | DS | MOC-193718 | 0 | 1140388 | Completed | 802824 | Approved/Printed | 2025-09-14 | 2025-09-28 | NEWCON | 20665 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 8 | 8 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1630 | 1630 | Invoiced | Invoiced | 2 | 16 |  |  |  | 2025-09-01 | Completed | Invoiced
17 | 239491 | 17 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-09-17 | 2025-10-06 | DS | MOC-243369 | 19 | 1140430 | completed | 803624/804983 | Approved/Printed | 2025-09-23 | 2026-04-09 | NEWCON | 0477 | 1 | Najma (26 ) | 19 | 19 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 |  |  | 1 | 1 | 2 | 2 | 0 | 0 |  |  | 1 | 1 | 4150 | 4150 | Invoiced | Invoiced | 10 | 17 |  |  |  | 2025-12-25 | Completed | Invoiced
18 | 239492 | 18 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-09-17 | 2025-09-29 | DS | MOC-236046/MOC-236045 | 12 | 1140453 | Completed | 803230 | Approved/Printed | 2025-09-20 | 2025-10-05 | NEWCON | 5610 | 2 | Al Khor (74 ) | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 |  | 0 |  | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 2900 | 2900 | Invoiced | Invoiced | 5 | 18 |  |  |  | 2025-09-01 | Completed | Invoiced
19 | 239493 | 19 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-11-07 | 2025-10-18 | MOC | MOC-246388 | 31 | 1140523 | Completed | 803245 | Approved/Printed | 2025-10-07 | 2026-03-26 | NEWCON | 32700 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 87 | 87 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 3 | 3 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 7730 | 7730 | Invoiced | Invoiced | 3 | 19 |  |  |  | 2025-10-01 | completed | Invoiced
20 | 239494 | 20 | 2025-09-07 | 2025-09-06 | 2025-09-17 | 2025-11-07 | 2025-10-04 | MOC | MOC-246742 | 17 | 1140526 | Completed | 803625 | Approved/Printed | 2025-09-23 | 2025-10-08 | NEWCON | 34485 | 1 | Al Shahhniya (80 ) | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 5400 | 5400 | Invoiced | Invoiced | 1 | 20 |  |  |  | 2025-10-01 | completed | Invoiced
21 | 239495 | 21 | 2025-09-08 | 2025-09-07 | 2025-09-18 | 2025-11-08 | 2025-10-15 | MOC | MOC-231556 | 27 | 1140624 | Completed | 803245 | Approved/Printed | 2025-10-07 | 2026-03-26 | NEWCON | 34485 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 34 | 34 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 3 | 3 | 3 | 3 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 6282 | 6282 | Invoiced | Invoiced | 2 | 21 |  |  |  | 2025-10-01 | completed | Invoiced
22 | 239498 | 22 | 2025-09-08 | 2025-09-07 | 2025-09-18 | 2025-11-08 | 2025-09-28 | MOC | MOC-220546 | 10 | 1140631 | Completed | 803246 | Approved/Printed | 2025-09-28 | 2025-10-13 | NEWCON | 36998 | 1 | Al Kheesa (70 ) | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1735 | 1735 | Invoiced | Invoiced | 4 | 22 |  |  |  | 2025-09-01 | completed | Invoiced
23 | 239499 | 23 | 2025-09-08 | 2025-09-07 | 2025-09-18 | 2025-11-08 | 2025-10-09 | MOC | MOC-240681 | 21 | 1140667 | Completed | 803245 | Approved/Printed | 2025-10-07 | 2026-03-26 | NEWCON | 26559 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 32 | 32 |  |  |  |  | 32 | 32 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 5584 | 5584 | Invoiced | Invoiced | 2 | 23 |  |  |  | 2025-10-01 | completed | Invoiced
24 | 239511 | 24 | 2025-09-08 | 2025-09-07 | 2025-09-18 | 2025-11-08 | 2026-09-12 | MOC | MOC-139647 | 359 | 1141006 | Completed | RO NA | DID Permit Received | 2025-10-20 | 2025-12-31 | NEWCON | 10760 | 1 | Abu Nakhla / Mukainess (81 ) | 55 | 55 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 1 | 1 | 5985 | 5985 | Invoiced | Invoiced | 4 | 24 |  |  |  | 2025-11-01 | completed | Invoiced
25 | 239501 | 25 | 2025-09-08 | 2025-09-07 | 2025-09-18 | 2025-09-18 | 2025-09-21 | DS | C-1490118(MSA-18034496) | 3 | 1140904 | Completed | 803038 | Approved/Printed | 2025-09-15 | 2025-09-30 | NEWCON | 9839 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1735 | 1735 | Invoiced | Invoiced | 2 | 25 |  |  |  | 2025-09-01 | completed | Invoiced
26 | 239502 | 26 | 2025-09-08 | 2025-09-07 | 2025-09-18 | 2025-09-18 | 2025-09-22 | DS | C-1002387(MSA-18035668) | 4 | 1140909 | Completed | 803255 | Approved/Printed | 2025-09-17 | 2025-10-02 | NEWCON | 15642 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 18 | 18 |  |  |  |  | 0 | [5 empty] | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 |  |  | 1 | 1 |  |  | 2290 | 2290 | Invoiced | Invoiced | 1 | 26 |  |  |  | 2025-09-01 | completed | Invoiced
27 | 239503 | 27 | 2025-09-08 | 2025-09-07 | 2025-09-18 | 2025-09-18 | 2025-09-22 | DS | C-121056(MSA-18035612) | 4 | 1140913 | Completed | 803255/ 804645 | Approved/Printed | 2025-09-17 | 2025-10-19 | NEWCON | 3614 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1795 | 1795 | Invoiced | Invoiced | 1 | 27 |  |  |  | 2025-09-01 | completed | Invoiced
28 | 239506 | 28 | 2025-09-08 | 2025-09-07 | 2025-09-18 | 2025-09-18 | 2025-09-23 | DS | C-176033A(MSA-18031805) | 5 | 1140974 | Completed | 803255 | Approved/Printed | 2025-09-17 | 2025-10-02 | NEWCON | 1790 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1795 | 1795 | Invoiced | Invoiced | 2 | 28 |  |  |  | 2025-09-01 | completed | Invoiced
29 | 239507 | 29 | 2025-09-08 | 2025-09-07 | 2025-09-18 | 2025-09-18 | 2025-10-24 | DS | MOC-246975 | 36 | 1140990 | Completed | 803255 | Approved/Printed | 2025-09-17 | 2025-10-02 | NEWCON | 12918 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1390 | 1390 | Invoiced | Invoiced | 1 | 29 |  |  |  | 2025-09-01 | completed | Invoiced
30 | 239508 | 30 | 2025-09-08 | 2025-09-07 | 2025-09-18 | 2025-09-18 | 2025-09-24 | DS | MOC-201947+MOC-201948 | 6 | 1140994 | Completed | 803039 | Approved/Printed | 2025-09-15 | 2025-09-30 | NEWCON | 37696 | 2 | Al Kheesa (70 ) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2 | 2 | 0 | 0 | 1040 | 1040 | Invoiced | Invoiced | 7 | 30 |  |  |  | 2025-09-01 | Completed | Invoiced
31 | 239509 | 31 | 2025-09-08 | 2025-09-07 | 2025-09-18 | 2025-09-18 | 2025-09-20 | DS | MOC-245160+MOC-245161 | 2 | 1140999 | Completed | 803038 | Approved/Printed | 2025-09-15 | 2025-09-30 | NEWCON | 23510 | 2 | Umm Slal/Al Kharaitiyat (71 ) | 12 | 12 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 3704 | 3704 | Invoiced | Invoiced | 2 | 31 |  |  |  | 2025-09-01 | Completed | Invoiced
32 | 239510 | 32 | 2025-09-08 | 2025-09-07 | 2025-09-18 | 2025-09-18 | 2025-09-20 | DS | MOC-228589 | 2 | 1141005 | Completed | RO NA | RO NA | NA | NA | NEWCON | 25113 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 0 | 0 | 520 | 520 | Invoiced | Invoiced | 5 | 32 |  |  |  | 2025-09-01 | Completed | Invoiced
33 | 239512 | 33 | 2025-09-08 | 2025-09-07 | 2025-09-18 | 2025-09-18 | 2025-09-20 | DS | MOC-242049+247680+ 247681+247682 | 2 | 1141035 | Completed | 803038 | Approved/Printed | 2025-09-15 | 2025-09-30 | NEWCON | 40380 | 4 | Umm Slal/Al Kharaitiyat (71 ) | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 6280 | 6280 | Invoiced | Invoiced | 1 | 33 |  |  |  | 2025-09-01 | completed | Invoiced
34 | 239514 | 34 | 2025-09-08 | 2025-09-07 | 2025-09-18 | 2025-09-18 | 2025-09-17 | DS | MOC-243261 | -1 | 1141093 | Completed | 803039 | Approved/Printed | 2025-09-15 | 2025-09-30 | NEWCON | 22641 | 1 | Al Kheesa (70 ) | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2086 | 2086 | Invoiced | Invoiced | 2 | 34 |  |  |  | 2025-09-01 | completed | Invoiced
35 | 239515 | 35 | 2025-09-08 | 2025-09-07 | 2025-09-18 | 2025-11-08 | 2025-09-25 | MOC | C-1021340(MSA-18035733) | -9 | 1141103 | Completed | 803255 | Approved/Printed | 2025-09-17 | 2025-10-02 | NEWCON | 13045 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 10 | 10 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3120 | 3120 | Invoiced | Invoiced | 1 | 35 |  |  |  | 2025-09-01 | completed | Invoiced
36 | 239516 | 36 | 2025-09-09 | 2025-09-08 | 2025-09-19 | 2025-09-19 | 2026-09-12 | DS | MOC-246532 | 358 | 1141208 | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | 35054 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 1917 | 0 | Cancelled | Cancelled | Cancelled | 36 |  |  |  |  | Cancelled | Cancelled
37 | 239517 | 37 | 2025-09-23 | 2025-09-22 | 2025-10-03 | 2025-11-09 | 2025-10-28 | MOC | MOC-242308 | 25 | 1141212 | Completed | 804467 | Approved/Printed | 2025-10-05 | 2026-04-02 | NEWCON | 1308 | 1 | Al Kheesa (70 ) | 58 | 58 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 0 |  | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 5320 | 5320 | Invoiced | Invoiced | 3 | 37 |  |  |  | 2025-10-01 | completed | Invoiced
38 | 239518 | 38 | 2025-09-09 | 2025-09-08 | 2025-09-19 | 2025-11-09 | 2025-10-08 | MOC | C-93529(MSA-18035113) | 19 | 1141231 | Completed | 803247 | Approved/Printed | 2025-10-01 | 2026-03-26 | NEWCON | 21785 | 1 | Madinat Khalifa (South) (34 ) | 18 | 18 | 0 | 0 | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3316 | 3316 | Invoiced | invoiced | 6 | 38 |  |  |  | 2025-10-01 | Completed | Invoiced
39 | 239519 | 39 | 2025-09-09 | 2025-09-08 | 2025-09-19 | 2025-11-09 | 2025-11-03 | MOC | MOC-219806 | 45 | 1141247 | Completed | 803248 | Approved/Printed | 2025-10-01 | 2026-03-26 | NEWCON | 19325 | 1 | Madinat Khalifa (North) (32 ) | 125 | 125 | 0 | 0 | 0 | 0 | 125 | 125 | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 17055 | 17055 | Invoiced | Invoiced | 3 | 39 |  |  |  | 2025-10-01 | completed | Invoiced
40 | 239561 | 40 | 2025-09-10 | 2025-09-09 | 2025-09-20 | 2025-09-20 | 2025-09-23 | DS | C-1111833(MSA-18035730) | 3 | 1142009 | Completed | 803255 | Approved/Printed | 2025-09-17 | 2025-10-02 | NEWCON | 12355 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1795 | 1795 | Invoiced | Invoiced | 1 | 40 |  |  |  | 2025-09-01 | completed | Invoiced
41 | 239531 | 41 | 2025-09-09 | 2025-09-08 | 2025-09-19 | 2025-09-19 | 2025-09-23 | DS | MOC-242769 | 4 | 1141521 | Completed | 803255 | Approved/Printed | 2025-09-17 | 2025-10-02 | NEWCON | 35039 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 7 | 7 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2170 | 2170 | Invoiced | Invoiced | 1 | 41 |  |  |  | 2025-09-01 | completed | Invoiced
42 | 239532 | 42 | 2025-09-09 | 2025-09-08 | 2025-09-19 | 2025-09-19 | 2025-10-20 | DS | MOC-231519 | 31 | 1141531 | Completed | 803255 | Approved/Printed | 2025-09-17 | 2025-10-02 | NEWCON | 35038 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 15 | 15 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2392 | 2392 | Invoiced | Invoiced | 2 | 42 |  |  |  | 2025-10-01 | completed | Invoiced
43 | 239533 | 43 | 2025-09-09 | 2025-09-08 | 2025-09-19 | 2025-09-19 | 2025-10-12 | DS | MOC-240235 | 23 | 1141534 | Completed | 804441 | Approved/Printed | 2025-10-02 | 2025-10-17 | NEWCON | 0470 | 1 | Al Doha Al Jadeeda (15 ) | 9 | 9 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 |  |  | 1 | 1 | 2803 | 2803 | Invoiced | Invoiced | 2 | 43 |  |  |  | 2025-10-01 | completed | Invoiced
44 | 239534 | 44 | 2025-09-09 | 2025-09-08 | 2025-09-19 | 2025-09-19 | 2025-10-01 | DS | MOC-234736 | 12 | 1141535 | Completed | 803240 | Approved/Printed | 2025-09-22 | 2025-10-07 | NEWCON | 17492 | 1 | Al Khulaifat Al Jadeeda/Al Maa(56 ) | 4 | 4 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1561 | 1561 | Invoiced | Invoiced | 6 | 44 |  |  |  | 2025-09-01 | Completed | Invoiced
45 | 239535 | 45 | 2025-09-09 | 2025-09-08 | 2025-09-19 | 2025-09-19 | 2025-09-29 | DS | MOC-243146 | 10 | 1141551 | Completed | 803230 | Approved/Printed | 2025-09-20 | 2025-10-05 | NEWCON | 2224 | 1 | Al Khor (74 ) | 20 | 20 | 0 | 0 | 0 | 0 | 20 | 20 |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 4090 | 4090 | Invoiced | Invoiced | 5 | 45 |  |  |  | 2025-09-01 | Completed | Invoiced
46 | 239536 | 46 | 2025-09-09 | 2025-09-08 | 2025-09-19 | 2025-09-19 | 2025-09-20 | DS | C-1095720(MSA-18035534) | 1 | 1141567 | Completed | 803255 | Approved/Printed | 2025-09-17 | 2025-10-02 | NEWCON | 16152 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1852 | 1852 | Invoiced | Invoiced | 1 | 46 |  |  |  | 2025-09-01 | completed | Invoiced
47 | 239537 | 47 | 2025-09-09 | 2025-09-08 | 2025-09-19 | 2025-09-19 | 2025-10-18 | DS | C-112034(MSA-18035675) | 29 | 1141572 | Completed | 803250 | Approved/Printed | 2025-10-05 | 2026-03-26 | NEWCON | 4482 | 1 | Al Duhail South (31 ) | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 |  | 0 | 1 | 1 | 0 | 0 | 1795 | 1795 | Invoiced | Invoiced | 2 | 47 |  |  |  | 2025-10-01 | completed | Invoiced
48 | 239538 | 48 | 2025-09-09 | 2025-09-08 | 2025-09-19 | 2025-09-19 | 2025-10-10 | DS | C-981100(MSA-18035595) | 21 | 1141577 | Completed | 803255 | Approved/Printed | 2025-09-17 | 2025-10-02 | NEWCON | 3062 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 0 | 0 | 520 | 520 | Invoiced | Invoiced | 8 | 48 |  |  |  | 2025-09-01 | Completed | Invoiced
49 | 239548 | 49 | 2025-09-10 | 2025-09-09 | 2025-09-20 | 2025-11-10 | 2025-10-30 | MOC | C-1208903 (MSA-18035719) | 40 | 1141843 | Completed | 804467/ 808146 | Approved/Printed | 2025-10-05 | 2026-04-02 | NEWCON | 10049 | 1 | Al Kheesa (70 ) | 92 | 92 | 0 | 0 | 0 | 0 | 84 | 84 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 3 | 3 | 6 | 6 | 4 | 4 | 0 | 0 | 1 | 1 | 0 | 0 | 15988 | 15988 | Invoiced | Invoiced | 6 | 49 |  |  |  | 2025-12-01 | Completed | Invoiced
50 | 239562 | 50 | 2025-09-10 | 2025-09-09 | 2025-09-20 | 2025-09-20 | 2025-09-28 | DS | C-89448A(MSA-18035939) | 8 | 1142015 | Completed | 803626 | Approved/Printed | 2025-09-22 | 2025-10-07 | NEWCON | 29463 | 1 | Al Rayyan Al Jadeed/Muaither N(53 ) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 0 | 0 | 520 | 520 | Invoiced | Invoiced | 7 | 50 |  |  |  | 2025-09-01 | Completed | Invoiced
51 | 239563 | 51 | 2025-09-10 | 2025-09-09 | 2025-09-20 | 2025-09-20 | 2025-10-07 | DS | C-44972(MSA-18035543) | 17 | 1142019 | Completed | 803247 | Approved/Printed | 2025-10-01 | 2026-03-26 | NEWCON | 22222 | 1 | Madinat Khalifa (South) (34 ) | 9 | 9 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2263 | 2263 | Invoiced | Invoiced | 2 | 51 |  |  |  | 2025-10-01 | completed | Invoiced
52 | 239564 | 52 | 2025-09-10 | 2025-09-09 | 2025-09-20 | 2025-09-20 | 2025-10-12 | DS | MOC-244331+MOC-244332 | 22 | 1142027 | Completed | 803628 | Approved/Printed | 2025-09-25 | 2025-10-10 | NEWCON | 36965 | 2 | Kulaib (35 ) | 14 | 14 | 0 | 0 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 |  |  | 2 | 2 | 5138 | 5138 | Invoiced | Invoiced | 3 | 52 |  |  |  | 2025-10-01 | completed | Invoiced
53 | 239583 | 53 | 2025-09-11 | 2025-09-10 | 2025-09-21 | 2025-09-21 | 2025-10-29 | DS | MOC-228991 | 38 | 1142585 | Completed | 803626/ 805985 | Approved/Printed | 2025-09-22 | 2025-12-20 | NEWCON | 25036 | 1 | Al Rayyan Al Jadeed/Muaither N(53 ) | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 |  | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1621 | 1621 | Invoiced | Invoiced | 2 | 53 |  |  |  | 2025-10-01 | completed | Invoiced
54 | 239584 | 54 | 2025-09-11 | 2025-09-10 | 2025-09-21 | 2025-09-21 | 2025-10-04 | DS | MOC-240757 | 13 | 1142593 | Completed | 803625 | Approved/Printed | 2025-09-23 | 2025-10-08 | NEWCON | 30467 | 1 | Al Shahhniya (80 ) | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1570 | 1570 | Invoiced | Invoiced | 1 | 54 |  |  |  | 2025-10-01 | completed | Invoiced
55 | 239585 | 55 | 2025-09-11 | 2025-09-10 | 2025-09-21 | 2025-09-21 | 2025-09-28 | DS | C-152648A(MSA-18035870) | 7 | 1142599 | Completed | 803255 | Approved/Printed | 2025-09-17 | 2025-10-02 | NEWCON | 3886 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1690 | 1690 | Invoiced | invoiced | 1 | 55 |  |  |  | 2025-09-01 | completed | Invoiced
56 | 239589 | 56 | 2025-09-11 | 2025-09-10 | 2025-09-21 | 2025-11-11 | 2025-10-13 | MOC | C-65009(MSA-18034722) | 22 | 1142644 | Completed | 803368 | Approved/Printed | 2025-09-30 | 2026-03-26 | NEWCON | 0070 | 1 | Al Luqta/Al Rayyan Al Qadeem (52 ) | 99 | 99 | 0 | 0 | 0 | 0 | 96 | 96 | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 1 | 1 | 5 | 5 | 5 | 5 | 0 | 0 | 1 | 1 | 0 | 0 | 16312 | 16312 | Invoiced | invoiced | 5 | 56 |  |  |  | 2025-10-01 | Completed | Invoiced
57 | 239594 | 57 | 2025-09-14 | 2025-09-13 | 2025-09-24 | 2025-09-24 | 2025-10-06 | DS | C-45374A(MSA-18035530) | 12 | 1143075 | Completed | 804176 | Approved/Printed | 2025-09-29 | 2025-10-13 | NEWCON | 1135 | 1 | Al Mansoura/Bin Dirhem (25 ) | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2146 | 2146 | Invoiced | Invoiced | 2 | 57 |  |  |  | 2025-10-01 | completed | Invoiced
58 | 239596 | 58 | 2025-09-14 | 2025-09-13 | 2025-09-24 | 2025-09-24 | 2025-09-29 | DS | C-981627( MSA-18035520) | 5 | 1143091 | Completed | 803240 | Approved/Printed | 2025-09-22 | 2025-10-07 | NEWCON | 33666 | 1 | Al Khulaifat Al Jadeeda/Al Maa(56 | 15 | 15 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2680 | 2680 | Invoiced | Invoiced | 1 | 58 |  |  |  | 2025-09-01 | completed | Invoiced
59 | 239598 | 59 | 2025-09-14 | 2025-09-13 | 2025-09-24 | 2025-09-24 | 2025-10-01 | DS | MOC-247283 | 7 | 1143107 | Completed | 803626 | Approved/Printed | 2025-09-22 | 2025-10-07 | NEWCON | 21060 | 1 | Al Rayyan Al Jadeed/Muaither N(53 ) | 5 | 5 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1450 | 1450 | Invoiced | Invoiced | 1 | 59 |  |  |  | 2025-09-01 | completed | Invoiced
60 | 239600 | 60 | 2025-09-14 | 2025-09-13 | 2025-09-24 | 2025-09-24 | 2025-10-02 | DS | MOC-247414 | 8 | 1143116 | Completed | 803240 | Approved/Printed | 2025-09-22 | 2025-10-07 | NEWCON | 4618 | 1 | Al Khulaifat Al Jadeeda/Al Maa(56 ) | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1450 | 1450 | Invoiced | Invoiced | 1 | 60 |  |  |  | 2025-09-01 | completed | Invoiced
61 | 239604 | 61 | 2025-09-14 | 2025-09-13 | 2025-09-24 | 2025-09-24 | 2025-10-02 | DS | MOC-247792 | 8 | 1143164 | Completed | 803240 | Approved/Printed | 2025-09-22 | 2025-10-07 | NEWCON | 32056 | 1 | Al Khulaifat Al Jadeeda/Al Maa(56 ) | 6 | 6 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1510 | 1510 | Invoiced | Invoiced | 1 | 61 |  |  |  | 2025-09-01 | completed | Invoiced
62 | 239611 | 62 | 2025-09-14 | 2025-09-13 | 2025-09-24 | 2025-09-24 | 2025-10-29 | DS | MOC-219967+68+69+70+71 | 35 | 1143168 | completed | 803461 | Approved/Printed | 2025-10-19 | 2026-04-09 | NEWCON | 3656 | 5 | Al Luqta/Al Rayyan Al Qadeem (52 ) | 23 | 23 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 5 | 5 | 0 | 0 | 7814 | 7814 | Invoiced | Invoiced | 12 | 62 |  |  |  | 2025-10-01 | Completed | Invoiced
63 | 239647 | 63 | 2025-09-15 | 2025-09-14 | 2025-09-25 | 2025-09-25 | 2025-10-01 | DS | C-1164958 (MSA-18034686) | 6 | 1143515 | Completed | 803630 | Approved/Printed | 2025-09-25 | 2025-10-10 | NEWCON | 22709 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 4 | 4 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1450 | 1450 | Invoiced | Invoiced | 2 | 63 |  |  |  | 2025-09-01 | completed | Invoiced
64 | 239648 | 64 | 2025-09-15 | 2025-09-14 | 2025-09-25 | 2025-09-25 | 2025-09-22 | DS | C-1065156 (MSA-18035962) | -3 | 1143523 | Completed | 803629 | Approved/Printed | 2025-09-22 | 2025-10-07 | NEWCON | 5423 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1735 | 1735 | Invoiced | Invoiced | 1 | 64 |  |  |  | 2025-09-01 | completed | Invoiced
65 | 239649 | 65 | 2025-09-15 | 2025-09-14 | 2025-09-25 | 2025-09-25 | 2025-09-30 | DS | C-176064A (MSA-18035888) | 5 | 1143543 | Completed | 803629 | Approved/Printed | 2025-09-22 | 2025-10-07 | NEWCON | 29477 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1570 | 1570 | Invoiced | Invoiced | 2 | 65 |  |  |  | 2025-09-01 | completed | Invoiced
66 | 239650 | 66 | 2025-09-15 | 2025-09-14 | 2025-09-25 | 2025-09-25 | 2025-09-16 | DS | C-108688A (MSA-18035641) | -9 | 1143556 | COMPLETED | RO NA | RO NA | NA | NA | NEWCON | 14245 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 520 | 520 | Invoiced | Invoiced | 1 | 66 |  |  |  | 2025-09-01 | Completed | Invoiced
67 | 239656 | 67 | 2025-09-15 | 2025-09-14 | 2025-09-25 | 2025-09-25 | 2025-10-01 | DS | C-1193583 (MSA-18035783) | 6 | 1143579 | Completed | 803630 | Approved/Printed | 2025-09-25 | 2025-10-10 | NEWCON | 4284 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1912 | 1912 | Invoiced | Invoiced | 2 | 67 |  |  |  | 2025-10-01 | completed | Invoiced
68 | 239663 | 68 | 2025-09-15 | 2025-09-14 | 2025-09-25 | 2025-09-25 | 2025-10-09 | DS | MOC-243469 | 14 | 1143604 | Completed | 804176/ 805581 | Approved/Printed | 2025-09-29 | 2025-11-12 | NEWCON | 1095 | 1 | Al Mansoura/Bin Dirhem (25 ) | 5 | 5 | 0 | 0 | 0 |  | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1735 | 1735 | Invoiced | Invoiced | 5 | 68 |  |  |  | 2025-12-25 | Completed | Invoiced
69 | 239666 | 69 | 2025-09-15 | 2025-09-14 | 2025-09-25 | 2025-09-25 | 2025-09-30 | DS | MOC-247216 | 5 | 1143607 | Completed | 803625 | Approved/Printed | 2025-09-23 | 2025-10-08 | NEWCON | 38733 | 1 | Al Shahhniya (80 ) | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1570 | 1570 | Invoiced | Invoiced | 1 | 69 |  |  |  | 2025-09-01 | completed | Invoiced
70 | 239653 | 70 | 2025-09-15 | 2025-09-14 | 2025-09-25 | 2025-12-15 | 2025-11-02 | BP | BP#150252 | 38 | 1143564 | Completed | 803816 | Approved/Printed | 2025-10-08 | 2026-04-02 | NEWCON | 26215 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 286 | 286 | 0 |  | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 2 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 20874 | 20874 | Invoiced | Invoiced | 2 | 70 |  |  |  | 2025-10-01 | completed | Invoiced
71 | 239674 | 71 | 2025-09-15 | 2025-09-14 | 2025-09-25 | 2025-12-15 | 2025-10-07 | BP | BP#150258 | 12 | 1143616 | Completed | 803630 | Approved/Printed | 2025-09-25 | 2025-10-10 | NEWCON | 10763 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 60 | 60 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 5400 | 5400 | Invoiced | Invoiced | 3 | 71 |  |  |  | 2025-10-01 | completed | Invoiced
72 | 239683 | 72 | 2025-09-15 | 2025-09-14 | 2025-09-25 | 2025-12-15 | 2025-11-06 | MOC | BP#150160 MOC-246320 | 42 | 1143621 | Completed | 803816 | Approved/Printed | 2025-10-08 | 2026-04-02 | NEWCON | 26012 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 42 | 42 | 0 |  | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 5232 | 5232 | Invoiced | Invoiced | 2 | 72 |  |  |  | 2025-10-01 | completed | Invoiced
73 | 239684 | 73 | 2025-09-15 | 2025-09-14 | 2025-09-25 | 2025-12-15 | 2025-11-03 | BP | BP#150126+ BP#150127 | 39 | 1143625 | Completed | 803816 | Approved/Printed | 2025-10-08 | 2026-04-02 | NEWCON | 36163 | 2 | Umm Slal/Al Kharaitiyat (71 ) | 200 | 200 | 0 | 0 | 0 | 0 | 27 | 27 | 0 | 0 | 0 | 0 |  |  | 1 | 1 | 0 |  | 1 | 1 |  |  | 0 |  |  |  | 0 | 0 | 13974 | 13974 | Invoiced | Invoiced | 2 | 73 |  |  |  | 2025-10-01 | completed | Invoiced
74 | 239685 | 74 | 2025-09-16 | 2025-09-15 | 2025-09-26 | 2025-11-16 | 2026-09-12 | BP | BP#150315 | 351 | 1143713 | Completed | 810944 | Approved/Printed | 2025-12-23 | 2026-06-25 | KAR | 9860 | 1 | Al Kheesa (70 ) | 163 | 163 | 0 | 0 | 0 | 0 | 89 | 89 | 0 | 0 | 0 | 0 | 2 | 2 |  |  | 2 | 2 | 4 | 4 | 2 | 2 | 0 | 0 | 0 |  | 0 | 0 | 17873 | 17873 | Invoiced | Invoiced | 6 | 74 |  |  |  | 2026-01-01 | completed | Invoiced
75 | 239686 | 75 | 2025-09-16 | 2025-09-15 | 2025-09-26 | 2025-12-16 | 2026-01-17 | BP | BP#150233 | 113 | 1143788 | Completed | 810944 | Approved/Printed | 2025-12-23 | 2026-06-25 | KAR | 21628 | 1 | Al Kheesa (70 ) | 134 | 134 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 1 | 1 | 1 | 1 | 0 |  | 0 |  |  |  | 0 | 0 | 8690 | 8690 | Invoiced | Invoiced | 7 | 75 |  |  |  | 2026-01-01 | completed | Invoiced
76 | 239701 | 76 | 2025-09-16 | 2025-09-15 | 2025-09-26 | 2025-12-16 | 2026-01-21 | BP | BP#150173 | 117 | 1143910 | Completed | 810944 | Approved/Printed | 2025-12-23 | 2026-06-25 | KAR | 14366 | 1 | Al Kheesa (70 ) | 58 | 58 | 0 | 0 | 0 | 0 | 29 | 29 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 6643 | 6643 | Invoiced | Invoiced | 7 | 76 |  |  |  | 2026-01-01 | completed | Invoiced
77 | 239716 | 77 | 2025-09-16 | 2025-09-15 | 2025-09-26 | 2025-12-16 | 2026-01-27 | BP | BP#150156 | 123 | 1143978 | Completed | 810943 | Approved/Printed | 2025-12-30 | 2026-06-25 | KAR | 24878 | 1 | Al Kheesa (70 ) | 65 | 65 | 0 |  | 0 | 0 | 65 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 8295 | 8295 | Invoiced | Invoiced | 6 | 77 |  |  |  | 2026-01-01 | Pending | Invoiced
78 | 239721 | 78 | 2025-09-16 | 2025-09-15 | 2025-09-26 | 2025-09-26 | 2025-10-01 | DS | MOC-173917 | 5 | 1143985 | Completed | 803630 | Approved/Printed | 2025-09-25 | 2025-10-10 | NEWCON | 23973 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 7 | 7 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1969 | 1969 | Invoiced | Invoiced | 3 | 78 |  |  |  | 2025-09-01 | completed | Invoiced
79 | 239723 | 79 | 2025-09-16 | 2025-09-15 | 2025-09-26 | 2025-11-16 | 2025-11-30 | MOC | C-57432 (MSA#18035011) | 65 | 1143999 | Completed | 803368/ 806470 | Approved/Printed | 2025-09-30 | 2026-03-26 | NEWCON | 0094 | 1 | Al Luqta/Al Rayyan Al Qadeem (52 ) | 182 | 182 | 40 | 40 | 0 | 0 | 83 | 83 | 0 | 0 | 50 | 50 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 |  | 1 | 1 | 29436 | 29436 | Invoiced | Invoiced | 5 | 79 |  |  |  | 2025-11-01 | Completed | Invoiced
80 | 239801 | 80 | 2025-09-18 | 2025-09-17 | 2025-09-28 | 2025-09-28 | 2025-10-05 | DS | C-83304 (MSA-18035996) | 7 | 1144786 | Completed | 804177 | Approved/Printed | 2025-09-29 | 2025-10-13 | NEWCON | 3756 | 1 | Al Khulaifat Al Jadeeda/Al Maa(56 ) | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1735 | 1735 | Invoiced | Invoiced | 1 | 80 |  |  |  | 2025-10-01 | completed | Invoiced
81 | 239802 | 81 | 2025-09-18 | 2025-09-17 | 2025-09-28 | 2025-09-28 | 2025-10-05 | DS | MOC-222544+ MOC-222545 | 7 | 1144787 | Completed | 804177 | Approved/Printed | 2025-09-29 | 2025-10-13 | NEWCON | 19042 | 2 | Al Khulaifat Al Jadeeda/Al Maa(56 ) | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 3260 | 3260 | Invoiced | Invoiced | 2 | 81 |  |  |  | 2025-10-01 | completed | Invoiced
82 | 239816 | 82 | 2025-09-21 | 2025-09-20 | 2025-10-01 | 2025-10-01 | 2025-10-01 | DS | C-66629 (IDM-12850) | 0 | 1145574 | Completed | 803629 | Approved/Printed | 2025-09-22 | 2025-10-07 | NEWCON | 1990 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1735 | 1735 | Invoiced | Invoiced | 2 | 82 |  |  |  | 2025-09-01 | completed | Invoiced
83 | 239846 | 83 | 2025-09-21 | 2025-09-20 | 2025-10-01 | 2025-10-01 | 2025-10-08 | DS | C-1137949 (MSA-18036010) | 7 | 1145823 | Completed | 804645 | Approved/Printed | 2025-10-04 | 2025-10-19 | NEWCON | 26092 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1795 | 1795 | Invoiced | Invoiced | 2 | 83 |  |  |  | 2025-10-01 | completed | Invoiced
84 | 239847 | 84 | 2025-09-21 | 2025-09-20 | 2025-10-01 | 2025-10-01 | 2025-10-08 | DS | MOC-198986 | 7 | 1145829 | Completed | 804477 | Approved/Printed | 2025-10-01 | 2025-10-16 | NEWCON | 12527 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1735 | 1735 | Invoiced | Invoiced | 1 | 84 |  |  |  | 2025-10-01 | completed | Invoiced
85 | 239848 | 85 | 2025-09-21 | 2025-09-20 | 2025-10-01 | 2025-10-01 | 2025-10-06 | DS | MOC-197523 | 5 | 1145857 | Completed | 804177 | Approved/Printed | 2025-09-29 | 2025-10-13 | NEWCON | 14757 | 1 | Al Khulaifat Al Jadeeda/Al Maa(56 ) | 14 | 14 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1990 | 1990 | Invoiced | Invoiced | 2 | 85 |  |  |  | 2025-10-01 | completed | Invoiced
86 | 239853 | 86 | 2025-09-21 | 2025-09-20 | 2025-10-01 | 2025-12-21 | 2026-01-06 | BP | BP#N/2025/1778 (PIN57110426) | 97 | 1145914 | Completed | 804711/ 810939 | Approved/Printed | 2025-10-30 | 2026-04-09 | NEWCON | 18518 | 1 | Industrial Area (57 ) | 63 | 63 | 15 | 15 | 0 | 0 | 63 | 63 | 0 | 0 | 60 | 60 | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 18521 | 18521 | Invoiced | Invoiced | 7 | 86 |  |  |  | 2026-01-01 | Completed | Invoiced
87 | 239854 | 87 | 2025-09-21 | 2025-09-20 | 2025-10-01 | 2025-12-21 | 2025-10-23 | MOC | C-981553 (MSA-18035495) | 22 | 1145927 | Completed | 804492/ 806207 | Approved/Printed | 2025-10-20 | 2025-11-04 | NEWCON | 3424 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 36 | 36 | 0 |  | 0 | 0 | 36 | 36 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 6712 | 6712 | Invoiced | Invoiced | 4 | 87 |  |  |  | 2025-10-01 | completed | Invoiced
88 | 239865 | 88 | 2025-09-22 | 2025-09-21 | 2025-10-02 | 2025-12-22 | 2026-09-12 | BP | BP#N/2025/1754 (PIN70150188) | 345 | 1146206 | Completed | 810943 | Approved/Printed | 2025-12-30 | 2026-06-25 | NEWCON | 32923 | 1 | Al Kheesa (70 ) | 617 | 617 | 0 |  | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 2 | 2 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 43845 | 43845 | Invoiced | invoiced | 6 | 88 |  |  |  | 2026-01-01 | completed | Invoiced
89 | 239869 | 89 | 2025-09-22 | 2025-09-21 | 2025-10-02 | 2025-12-22 | 2026-03-24 | BP | BP#150151 | 173 | 1146225 | completed | 810947 | Approved/Printed | 2025-12-31 | 2026-06-25 | NEWCON | 5105 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 78 | 78 |  |  | 0 | 0 | 78 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 9816 | 9816 | Invoiced | Invoiced | 11 | 89 |  |  |  | 2026-03-15 | completed | Invoiced
90 | 239910 | 90 | 2025-09-22 | 2025-09-21 | 2025-10-02 | 2025-10-02 | 2025-10-16 | DS | MOC-237606 | 14 | 1146254 | Completed | 804493 | Approved/Printed | 2025-10-02 | 2025-10-17 | NEWCON | 25414 | 1 | Al Shahhniya (80 ) | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1852 | 1852 | Invoiced | Invoiced | 2 | 90 |  |  |  | 2025-10-01 | completed | Invoiced
91 | 239913 | 91 | 2025-09-22 | 2025-09-21 | 2025-10-02 | 2025-10-02 | 2025-10-06 | DS | MOC-219526 | 4 | 1146268 | Completed | 804177 | Approved/Printed | 2025-09-29 | 2025-10-13 | NEWCON | 18223 | 1 | Al Khulaifat Al Jadeeda/Al Maa(56 ) | 6 | 6 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1510 | 1510 | Invoiced | Invoiced | 2 | 91 |  |  |  | 2025-10-01 | completed | Invoiced
92 | 239925 | 92 | 2025-09-22 | 2025-09-21 | 2025-10-02 | 2025-10-27 | 2025-11-06 | MOC | C-47485 (MSA-18035388) | 35 | 1146319 | Completed | 804714/ 811854 | Approved/Printed | 2025-10-13 | 2026-04-09 | NEWCON | 16914 | 1 | Al Luqta/Al Rayyan Al Qadeem (52 ) | 129 | 129 | 0 | 0 | 0 | 0 | 54 | 54 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 1 | 1 | 4 | 4 | 4 | 4 | 0 | 0 | 1 | 1 | 1 | 1 | 15978 | 15978 | Invoiced | Invoiced | 5 | 92 |  |  |  | 2026-01-01 | Completed | Invoiced
93 | 239926 | 93 | 2025-09-22 | 2025-09-21 | 2025-10-02 | 2025-10-02 | 2025-10-14 | DS | MOC-123982 | 12 | 1146320 | Completed | 804477 | Approved/Printed | 2025-10-01 | 2025-10-16 | NEWCON | 15210 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 8 | 8 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 3195 | 3195 | Invoiced | Invoiced | 2 | 93 |  |  |  | 2025-10-01 | completed | Invoiced
94 | 239937 | 94 | 2025-09-23 | 2025-09-22 | 2025-10-03 | 2025-12-23 | 2026-03-24 | BP | BP#150230 | 172 | 1146502 | completed | 810947 | Approved/Printed | 2025-12-31 | 2026-06-25 | AL MORAQUIB | 4146 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 107 | 107 | 0 |  | 0 | 0 | 107 | 107 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 13209 | 13209 | Completed | Pending | Pending | 94 |  |  |  | 2026-03-07 | Pending | Pending
95 | 239938 | 95 | 2025-09-23 | 2025-09-22 | 2025-10-03 | 2025-12-23 | 2026-04-01 | BP | BP#150260 | 180 | 1146504 | Completed | 810945/ 816110 | Approved/Printed | 2025-12-29 | 2026-06-25 | NEWCON | 39100 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 114 | 114 | 0 | 0 | 40 | 40 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11826 | 11826 | Invoiced | Invoiced | 10 | 95 |  |  |  | 2026-03-25 | Completed | Invoiced
96 | 239966 | 96 | 2025-09-23 | 2025-09-22 | 2025-10-03 | 2025-10-03 | 2025-09-25 | DS | C-1093291 (MSA-18035977) | -8 | 1146629 | Completed | RO NA | RO NA | NA | NA | NEWCON | 12918 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 0 | 0 | 520 | 520 | Invoiced | Invoiced | 5 | 96 |  |  |  | 2025-09-01 | Completed | Invoiced
97 | 239967 | 97 | 2025-09-23 | 2025-09-22 | 2025-10-03 | 2025-10-03 | 2025-10-05 | DS | C-981689 (MSA-18035728) | 2 | 1146636 | Completed | 804177 | Approved/Printed | 2025-09-29 | 2025-10-13 | NEWCON | 4599 | 1 | Al Khulaifat Al Jadeeda/Al Maa(56 ) | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 1 | 2335 | 2335 | Invoiced | Invoiced | 2 | 97 |  |  |  | 2025-10-01 | completed | Invoiced
98 | 239972 | 98 | 2025-09-23 | 2025-09-22 | 2025-10-03 | 2025-12-23 | 2026-02-15 | BP | BP#150339 | 135 | 1146821 | Completed | 810947 | Approved/Printed | 2025-12-31 | 2026-06-25 | NEWCON | 5120 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 98 | 98 | 0 | 0 | 0 | 0 | 98 | 98 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 |  | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 13876 | 13876 | Invoiced | Invoiced | 7 | 98 |  |  |  | 2026-02-01 | Completed | Invoiced
99 | 239975 | 99 | 2025-09-24 | 2025-09-23 | 2025-10-04 | 2025-12-24 | 2026-09-12 | BP | BP#150106 | 343 | 1147013 | Pending | 810944 | Approved/Expired | 2025-12-23 | 2026-06-25 | NEWCON | 13887 | 1 | Al Kheesa (70 ) | 75 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6155 | 0 | Pending | Pending | Pending | 99 |  |  |  |  | Pending | Pending
100 | 239992 | 100 | 2025-09-24 | 2025-09-23 | 2025-10-04 | 2025-12-24 | 2025-10-08 | MOC | OL-F2-10226 | 4 | 1147134 | Completed | 804477 | Approved/Printed | 2025-10-01 | 2025-10-16 | NEWCON | 10226 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 25 | 25 |  |  | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 3458 | 3458 | Invoiced | Invoiced | 3 | 100 |  |  |  | 2025-10-01 | completed | Invoiced
101 | 239984 | 101 | 2025-09-24 | 2025-09-23 | 2025-10-04 | 2025-10-04 | 2025-10-09 | DS | C-149843A (MSA-18031710) | 5 | 1147128 | Completed | 804492/ 805583 | Approved/Printed | 2025-10-04 | 2025-10-28 | NEWCON | 3561 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 18 | 18 | 0 | 0 | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 5036 | 5036 | Invoiced | Invoiced | 7 | 101 |  |  |  | 2025-10-01 | Completed | Invoiced
102 | 239987 | 102 | 2025-09-24 | 2025-09-23 | 2025-10-04 | 2025-10-04 | 2025-10-16 | DS | MOC-244450+MOC-244451 | 12 | 1147130 | Completed | 804492 | Approved/Printed | 2025-10-04 | 2025-10-19 | NEWCON | 22864 | 2 | Umm Slal/Al Kharaitiyat (71 ) | 16 | 16 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 3260 | 3260 | Invoiced | Invoiced | 2 | 102 |  |  |  | 2025-10-01 | completed | Invoiced
103 | 240001 | 103 | 2025-09-24 | 2025-09-23 | 2025-10-04 | 2025-10-04 | 2025-10-09 | DS | MOC-242313+MOC-242315 | 5 | 1147149 | Completed | 804492 | Approved/Printed | 2025-10-04 | 2025-10-19 | NEWCON | 23664 | 2 | Umm Slal/Al Kharaitiyat (71 ) | 11 | 11 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 2960 | 2960 | Invoiced | Invoiced | 2 | 103 |  |  |  | 2025-10-01 | completed | Invoiced
104 | 240002 | 104 | 2025-09-24 | 2025-09-23 | 2025-10-04 | 2025-10-04 | 2025-10-12 | DS | MOC-247962 | 8 | 1147151 | Completed | 804493 | Approved/Printed | 2025-10-02 | 2025-10-17 | NEWCON | 34779 | 1 | Al Shahhniya (80 ) | 10 | 10 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 2440 | 2440 | Invoiced | Invoiced | 5 | 104 |  |  |  | 2025-10-01 | Completed | Invoiced
105 | 240024 | 105 | 2025-09-25 | 2025-09-24 | 2025-10-05 | 2025-12-25 | 2025-11-25 | BP | BP#N/2025/905 (PIN#34010009) | 51 | 1147409 | Completed | 804715 | Approved/Printed | 2025-10-20 | 2026-04-09 | NEWCON | 23447 | 1 | Madinat Khalifa (South) (34 ) | 73 | 73 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6170 | 6170 | Invoiced | Invoiced | 5 | 105 |  |  |  | 2025-11-01 | Completed | Invoiced
106 | 240025 | 106 | 2025-09-29 | 2025-09-28 | 2025-10-09 | 2025-11-29 | 2025-10-26 | MOC | C-1003542 (MSA-18034820) | 17 | 1147486 | Completed | 805335 | Approved/Printed | 2025-10-16 | 2025-10-31 | NEWCON | 17194 | 1 | Al Kheesa (70 ) | 15 | 15 |  |  | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 4175 | 4175 | Invoiced | invoiced | 6 | 106 |  |  |  | 2025-10-01 | Completed | Invoiced
107 | 240026 | 107 | 2025-09-25 | 2025-09-24 | 2025-10-05 | 2025-12-25 | 2026-02-04 | BP | BP#150920 | 122 | 1147547 | Completed | 810947 | Approved/Printed | 2025-12-31 | 2026-06-25 | NEWCON | 4296 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 52 | 52 | 0 |  | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 5696 | 5696 | Invoiced | Invoiced | 9 | 107 |  |  |  | 2026-02-01 | completed | Invoiced
108 | 240029 | 108 | 2025-09-25 | 2025-09-24 | 2025-10-05 | 2025-12-25 | 2026-02-08 | BP | BP#150953 | 126 | 1147571 | Completed | 810945 | Approved/Printed | 2025-12-29 | 2026-06-25 | NEWCON | 20611 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 90 | 90 | 0 |  | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 7230 | 7230 | Invoiced | Invoiced | 9 | 108 |  |  |  | 2026-02-01 | completed | Invoiced
109 | 240033 | 109 | 2025-09-25 | 2025-09-24 | 2025-10-05 | 2025-12-25 | 2026-09-12 | BP | BP-150431+ BP-150432 | 342 | 1147613 | Not Clear | Hold | Hold | Pending | Pending | NEWCON | 23056 | 1 | Al Kheesa (70 ) | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1795 | 0 | Hold | Pending | Pending | 109 |  |  |  |  | Pending | Pending
110 | 240054 | 110 | 2025-09-28 | 2025-09-27 | 2025-10-08 | 2025-12-28 | 2025-12-06 | BP | BP#N/2025/1056 (PIN#35116053) | 59 | 1148175 | Completed | 804716 | Approved/Printed | 2025-10-16 | 2026-04-09 | NEWCON | 2161 | 1 | Kulaib (35 ) | 34 | 34 | 0 |  | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4400 | 4400 | Invoiced | Invoiced | 5 | 110 |  |  |  | 2025-11-01 | Completed | Invoiced
111 | 240081 | 111 | 2025-09-28 | 2025-09-27 | 2025-10-08 | 2025-08-10 | 2025-10-22 | DS | C-127653A; (MSA-18034608) | 14 | 1148332 | Completed | 805336 | Approved/Printed | 2025-10-12 | 2025-10-27 | NEWCON | 4536 | 1 | Abu Nakhla / Mukainess (81 ) | 8 | 8 |  | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2146 | 2146 | Invoiced | Invoiced | 2 | 111 |  |  |  | 2025-10-01 | completed | Invoiced
112 | 240096 | 112 | 2025-09-28 | 2025-09-27 | 2025-10-08 | 2025-12-28 | 2025-11-19 | BP | BP#150157 | 42 | 1148545 | Completed | 804494 | Approved/Printed | 2025-10-29 | 2026-04-09 | NEWCON | 4319 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 11 | 11 | 0 |  | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2567 | 2567 | Invoiced | Invoiced | 4 | 112 |  |  |  | 2025-11-01 | completed | Invoiced
113 | 240097 | 113 | 2025-09-28 | 2025-09-27 | 2025-10-08 | 2025-12-28 | 2026-02-24 | BP | BP#150207 | 139 | 1148550 | Completed | 804494/ 809352/ 817716 | Approved/Printed | 2025-10-29 | 2026-04-09 | NEWCON | 19528 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 189 | 189 | 32 | 32 | 0 | 0 | 35 | 35 | 0 | 0 | 40 | 40 | ` |  | 0 | 0 | 2 | 2 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 23335 | 23335 | Invoiced | Invoiced | 10 | 113 |  |  |  | 2026-01-01 | completed | Invoiced
114 | 240104 | 114 | 2025-09-29 | 2025-09-28 | 2025-10-09 | 2025-12-29 | 2025-11-09 | BP | BP# N/2025/3053 (PIN35116023) | 31 | 1148798 | Completed | 804716 | Approved/Printed | 2025-10-16 | 2026-04-09 | NEWCON | 2163 | 1 | Kulaib (35 ) | 145 | 145 | 0 | 0 | 0 | 0 | 128 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 17336 | 17336 | Invoiced | Invoiced | 4 | 114 |  |  |  | 2025-11-01 | completed | Invoiced
115 | 240132 | 115 | 2025-09-29 | 2025-09-28 | 2025-10-09 | 2025-10-09 | 2026-09-12 | DS | MOC-196352 | 338 | 1148927 | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NEWCON | 31472 | 1 | New District Of Doha (69 ) | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 1267 | 0 | Cancelled | Cancelled | Cancelled | 115 |  |  |  |  | Cancelled | Cancelled
116 | 240135 | 116 | 2025-09-29 | 2025-09-28 | 2025-10-09 | 2025-10-09 | 2025-10-08 | DS | MOC-202672 | -1 | 1148929 | Completed | RO NA | RO NA | NA | NA | NEWCON | 31471 | 1 | New District Of Doha (69 ) | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 0 | 0 | 520 | 520 | Invoiced | Invoiced | 5 | 116 |  |  |  | 2025-10-01 | Completed | Invoiced
117 | 240148 | 117 | 2025-09-29 | 2025-09-28 | 2025-10-09 | 2025-12-29 | 2025-11-23 | BP | BP#N/2025/0389 (PIN57010687) | 45 | 1148974 | Completed | 804711 | Approved/Printed | 2025-10-30 | 2026-04-09 | NEWCON | 23480 | 1 | Industrial Area (57 ) | 330 | 330 | 0 |  | 0 | 0 | 96 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 2 | 2 | 2 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 26572 | 26572 | Invoiced | Invoiced | 4 | 117 |  |  |  | 2025-11-01 | completed | Invoiced
118 | 240150 | 118 | 2025-09-29 | 2025-09-28 | 2025-10-09 | 2025-12-29 | 2025-12-22 | BP | BP#N/2025/1241 (PIN35016024) | 74 | 1148995 | Completed | 804717 | Approved/Printed | 2025-10-27 | 2026-04-09 | NEWCON | 22354 | 1 | Kulaib (35 ) | 488 | 488 |  |  | 0 | 0 | 275 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47495 | 47495 | Invoiced | Invoiced | 6 | 118 |  |  |  | 2025-12-01 | Completed | Invoiced
119 | 240170 | 119 | 2025-09-30 | 2025-09-29 | 2025-10-10 | 2025-10-10 | 2025-11-18 | DS | C-981745; (MSA-18035890) | 39 | 1149368 | Completed | 804985 | Approved/Printed | 2025-10-19 | 2026-04-09 | NEWCON | 5125 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 10 | 10 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 |  | 1 | 1 | 3442 | 3442 | Invoiced | Invoiced | 4 | 119 |  |  |  | 2025-11-01 | completed | Invoiced
120 | 240168 | 120 | 2025-09-30 | 2025-09-29 | 2025-10-10 | 2025-10-10 | 2025-10-13 | DS | C-1059163A (MSA-18035797) | 3 | 1149366 | Completed | 804645 | Approved/Printed | 2025-10-04 | 2025-10-19 | NEWCON | 12301 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 6 | 6 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1798 | 1798 | Invoiced | Invoiced | 4 | 120 |  |  |  | 2025-10-01 | completed | Invoiced
121 | 240169 | 121 | 2025-09-30 | 2025-09-29 | 2025-10-10 | 2025-10-10 | 2025-10-12 | DS | MOC-247907 | 2 | 1149367 | Completed | 804493 | Approved/Printed | 2025-10-02 | 2025-10-17 | NEWCON | 32428 | 1 | Al Shahhniya (80 ) | 9 | 9 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1690 | 1690 | Invoiced | Invoiced | 1 | 121 |  |  |  | 2025-10-01 | completed | Invoiced
122 | 240176 | 122 | 2025-09-30 | 2025-09-29 | 2025-10-10 | 2025-11-30 | 2025-10-23 | MOC | MOC-239274 | 13 | 1149387 | Completed | 804985 | Approved/Printed | 2025-10-19 | 2026-04-09 | NEWCON | 26025 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 40 | 40 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 5340 | 5340 | Invoiced | Invoiced | 2 | 122 |  |  |  | 2025-10-01 | completed | Invoiced
123 | 240218 | 123 | 2025-09-30 | 2025-09-29 | 2025-10-10 | 2025-12-30 | 2025-11-05 | BP | BP#N/2024/6525 (PIN56090759) | 26 | 1149444 | Completed | 805337 | Approved/Printed | 2025-10-20 | 2026-04-16 | NEWCON | 19256 | 1 | Al Khulaifat Al Jadeeda/Al Maa(56 ) | 40 | 40 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 3680 | 3680 | Invoiced | Invoiced | 2 | 123 |  |  |  | 2025-11-01 | completed | Invoiced
124 | 240246 | 124 | 2025-10-01 | 2025-09-30 | 2025-10-11 | 2025-10-11 | 2025-10-26 | DS | MSA-18036029+MSA-18030324 | 15 | 1149878 | Completed | 805336 | Approved/Printed | 2025-10-12 | 2025-10-27 | NEWCON | 4550 | 2 | Abu Nakhla / Mukainess (81 ) | 15 | 15 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 3491 | 3491 | Invoiced | Invoiced | 6 | 124 |  |  |  | 2025-10-01 | Completed | Invoiced
125 | 240247 | 125 | 2025-10-01 | 2025-09-30 | 2025-10-11 | 2025-10-11 | 2025-10-13 | DS | C-1006188 (MSA-18035989) | 2 | 1149879 | Completed | 805130 | Approved/Printed | 2025-10-08 | 2025-10-23 | NEWCON | 2286 | 1 | Al Rayyan Al Jadeed/Muaither N(53 ) | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1678 | 1678 | Invoiced | Invoiced | 2 | 125 |  |  |  | 2025-10-01 | completed | Invoiced
126 | 240250 | 126 | 2025-10-01 | 2025-09-30 | 2025-10-11 | 2025-10-11 | 2025-10-21 | DS | MOC-217262+MOC -217263+MOC-217264 | 10 | 1149880 | Completed | 805130 | Approved/Printed | 2025-10-08 | 2025-10-23 | NEWCON | 30727 | 3 | Al Rayyan Al Jadeed/Muaither N(53 ) | 18 | 18 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 4530 | 4530 | Invoiced | Invoiced | 2 | 126 |  |  |  | 2025-10-01 | completed | Invoiced
127 | 240269 | 127 | 2025-10-01 | 2025-09-30 | 2025-10-11 | 2025-12-31 | 2025-10-19 | OL | OL-TX-9848 | 8 | 1149963 | Completed | 805377 | Approved/Printed | 2025-10-11 | 2025-10-26 | NEWCON | 9847 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 8 | 8 | 0 |  | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2591 | 2591 | Invoiced | Invoiced | 2 | 127 |  |  |  | 2025-10-01 | completed | Invoiced
128 | 240271 | 128 | 2026-02-05 | 2026-02-04 | 2026-02-15 | 2026-05-05 | 2026-04-14 | OL | OL-TX2 -F8-3904 | 58 | 1149980 | completed | 805338 | Approved/Printed | 2025-11-03 | 2026-04-16 | NEWCON | 3904 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 10 | 10 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2265 | 2265 | Invoiced | Invoiced | 10 | 128 |  |  |  | 2025-11-23 | completed | Invoiced
129 | 240272 | 129 | 2025-10-01 | 2025-09-30 | 2025-10-11 | 2025-12-31 | 2025-10-20 | OL | OL-TX1-3878 | 9 | 1149981 | Completed | 805377 | Approved/Printed | 2025-10-11 | 2025-10-26 | NEWCON | 3878 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 10 | 10 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 1 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2570 | 2570 | Invoiced | Invoiced | 2 | 129 |  |  |  | 2025-10-01 | completed | Invoiced
130 | 240276 | 130 | 2025-10-02 | 2025-10-01 | 2025-10-12 | 2026-01-01 | 2025-12-03 | OL | OLTX214797 | 52 | 1150079 | Completed | 805338 | Approved/Printed | 2025-11-03 | 2026-04-16 | NEWCON | 4850 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 67 | 67 | 0 |  | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 2 | 2 | 0 |  | 0 |  | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 7000 | Invoiced | Invoiced | 5 | 130 |  |  |  | 2025-12-01 | Completed | Invoiced
131 | 240285 | 131 | 2025-10-02 | 2025-10-01 | 2025-10-12 | 2026-01-01 | 2025-10-19 | OL | OL F9+F11-3230 | 7 | 1150227 | Completed | 805377 | Approved/Printed | 2025-10-11 | 2025-10-26 | NEWCON | 3230 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 31 | 31 | 0 |  | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 5375 | 5375 | Invoiced | Invoiced | 3 | 131 |  |  |  | 2025-10-01 | completed | Invoiced
132 | 240286 | 132 | 2025-10-02 | 2025-10-01 | 2025-10-12 | 2026-01-01 | 2025-12-02 | OL | OLTX1F6F102663 | 51 | 1150257 | Completed | 805338 | Approved/Printed | 2025-11-03 | 2026-04-16 | NEWCON | 3585 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 178 | 178 | 0 |  | 0 | 0 | 178 | 178 | 0 | 0 | 0 | 0 | 2 | 2 | 0 |  | 2 | 2 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 23786 | 23786 | Invoiced | Invoiced | 5 | 132 |  |  |  | 2025-12-01 | completed | Invoiced
133 | 240300 | 133 | 2025-10-02 | 2025-10-01 | 2025-10-12 | 2026-01-01 | 2025-12-23 | OL | OL-TX2-0062 | 72 | 1150365 | Completed | 805353 | Approved/Printed | 2025-10-20 | 2026-04-16 | NEWCON | 14193 | 1 | Al Luqta/Al Rayyan Al Qadeem (52 ) | 208 | 208 | 0 |  | 0 | 0 | 106 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 20392 | 20392 | Invoiced | Invoiced | 6 | 133 |  |  |  | 2025-12-01 | completed | Invoiced
134 | 240328 | 134 | 2025-10-05 | 2025-10-04 | 2025-10-15 | 2025-12-04 | 2025-11-12 | MOC | C-130791 (MSA-18034740) | 28 | 1150802 | Completed | 805646 | Approved/Printed | 2025-10-27 | 2026-04-16 | NEWCON | 5188 | 1 | Al Duhail (30 ) | 55 | 55 | 0 | 0 | 0 | 0 | 55 | 55 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 8335 | 8335 | Invoiced | Invoiced | 3 | 134 |  |  |  | 2025-11-01 | completed | Invoiced
135 | 240346 | 135 | 2025-10-05 | 2025-10-04 | 2025-10-15 | 2026-01-04 | 2025-11-12 | BP | BP#150349 | 28 | 1151061 | Completed | 805337 | Approved/Printed | 2025-10-20 | 2026-04-16 | NEWCON | 25636 | 1 | Al Khulaifat Al Jadeeda/Al Maa(56 ) | 241 | 241 | 0 |  | 0 | 0 | 141 | 141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 23187 | 23187 | Invoiced | Invoiced | 3 | 135 |  |  |  | 2025-11-01 | completed | Invoiced
136 | 2+BB136+B140:H142 | 136 | 2025-10-05 | 2025-10-04 | 2025-10-15 | 2025-10-15 | 2025-10-08 | DS | MOC-200861 | -7 | 1151191 | Completed | RO NA | RO NA | NA | NA | NEWCON | 31465 | 1 | New District Of Doha 69 (69 ) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 0 | 0 | 520 | 520 | Invoiced | Invoiced | 5 | 136 |  |  |  | 2025-10-01 | Completed | Invoiced
137 | 240376 | 137 | 2025-10-05 | 2025-10-04 | 2025-10-15 | 2025-12-05 | 2025-11-10 | MOC | MOC 225207+8+9+10+11+12+13+14 | 26 | 1151236 | Completed | 805339 | Approved/Printed | 2025-10-15 | 2026-04-16 | NEWCON | 29769 | 8 | Umm Slal/Al Kharaitiyat (71 ) | 341 | 341 | 0 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 8 | 8 | 1 | 1 | 3 | 3 | 3 | 3 | 10 | 10 | 0 | 0 | 8 | 8 | 0 | 0 | 33986 | 33986 | Invoiced | Invoiced | 3 | 137 |  |  |  | 2025-11-01 | completed | Invoiced
138 | 240465 | 138 | 2025-10-06 | 2025-10-05 | 2025-10-16 | 2025-10-16 | 2025-10-15 | DS | C-981257 (MSA-18036116) | -1 | 1151637 | Completed | 805130 | Approved/Printed | 2025-10-08 | 2025-10-23 | NEWCON | 5065 | 1 | Al Rayyan Al Jadeed/Muaither N(53 ) | 15 | 15 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 1 | 4685 | 4685 | Invoiced | Invoiced | 5 | 138 |  |  |  | 2025-10-01 | Completed | Invoiced
139 | 240466 | 139 | 2025-10-06 | 2025-10-05 | 2025-10-16 | 2025-10-16 | 2025-10-15 | DS | MOC-240298 | -1 | 1151638 | Completed | 805130 | Approved/Printed | 2025-10-08 | 2025-10-23 | NEWCON | 4083 | 1 | Al Rayyan Al Jadeed/Muaither N(53 ) | 6 | 6 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1510 | 1510 | Invoiced | Invoiced | 4 | 139 |  |  |  | 2025-10-01 | completed | Invoiced
140 | 240467 | 140 | 2025-10-16 | 2025-10-15 | 2025-10-26 | 2025-12-16 | 2025-11-16 | MOC | MOC-240298 | 21 | 1151639 | Completed | 806342 | Approved/Printed | 2025-10-28 | 2026-04-23 | NEWCON | 36985 | 1 | Al Shahhniya (80 ) | 65 | 65 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 5700 | 5700 | Invoiced | Invoiced | 4 | 140 |  |  |  | 2025-11-01 | completed | Invoiced
141 | 240483 | 141 | 2025-10-07 | 2025-10-06 | 2025-10-17 | 2026-01-06 | 2025-12-01 | OL | OL TX1-9920 | 45 | 1151738 | Completed | 805647 | Approved/Printed | 2025-11-05 | 2026-04-23 | NEWCON | 25897 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 67 | 67 | 0 | 0 | 0 | 0 | 65 | 65 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 2 | 2 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 9715 | 9715 | Invoiced | Invoiced | 5 | 141 |  |  |  | 2025-12-01 | Completed | Invoiced
142 | 240485 | 142 | 2025-10-07 | 2025-10-06 | 2025-10-17 | 2026-01-07 | 2025-11-26 | OL | OL-F9-14071 | 40 | 1151740 | Completed | 805648 | Approved/Printed | 2025-11-05 | 2026-04-16 | NEWCON | 14071 | 1 | Al Kheesa (70 ) | 11 | 11 | 0 | 0 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 0 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2147 | 2147 | Invoiced | Invoiced | 5 | 142 |  |  |  | 2025-11-01 | Completed | Invoiced
143 | 240488 | 143 | 2025-10-07 | 2025-10-06 | 2025-10-17 | 2026-01-06 | 2025-12-01 | OL | OL-F9-15707 | 45 | 1151746 | Completed | 805648 | Approved/Printed | 2025-11-05 | 2026-04-16 | NEWCON | 15707 | 1 | Al Kheesa (70 ) | 41 | 41 | 0 | 0 | 0 | 0 | 41 | 41 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2 | 2 | 1 | 1 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 6037 | 6037 | Invoiced | Invoiced | 5 | 143 |  |  |  | 2025-11-01 | Completed | Invoiced
144 | 240525 | 144 | 2025-10-07 | 2025-10-06 | 2025-10-17 | 2025-10-17 | 2025-10-26 | DS | MOC-238011 | 9 | 1152087 | Completed | 805649 | Approved/Printed | 2025-10-14 | 2025-10-29 | NEWCON | 3448 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1735 | 1735 | Invoiced | Invoiced | 3 | 144 |  |  |  | 2025-10-01 | completed | Invoiced
145 | 240526 | 145 | 2025-10-07 | 2025-10-06 | 2025-10-17 | 2025-10-17 | 2025-10-27 | DS | MOC-217394 | 10 | 1152088 | Completed | 805649 | Approved/Printed | 2025-10-14 | 2025-10-29 | NEWCON | 35033 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 6 | 6 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1510 | 1510 | Invoiced | Invoiced | 2 | 145 |  |  |  | 2025-10-01 | completed | Invoiced
146 | 240527 | 146 | 2025-10-07 | 2025-10-06 | 2025-10-17 | 2025-10-17 | 2025-10-28 | DS | MOC-234718 | 11 | 1152089 | Completed | 805335 | Approved/Printed | 2025-10-16 | 2025-10-31 | NEWCON | 33909 | 1 | Al Kheesa (70 ) | 7 | 7 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1570 | 1570 | Invoiced | Invoiced | 2 | 146 |  |  |  | 2025-10-01 | completed | Invoiced
147 | 240528 | 147 | 2025-10-07 | 2025-10-06 | 2025-10-17 | 2025-10-17 | 2025-10-27 | DS | MOC-236793 | 10 | 1152090 | Completed | 805738 | Approved/Printed | 2025-10-15 | 2025-10-30 | NEWCON | 9620 | 1 | Al Shahhniya (80 ) | 6 | 6 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1340 | 1340 | Invoiced | Invoiced | 4 | 147 |  |  |  | 2025-10-01 | completed | Invoiced
148 | 240580 | 148 | 2025-10-07 | 2025-10-06 | 2025-10-17 | 2025-10-18 | 2025-10-28 | DS | MOC-245541 | 11 | 1152474 | Completed | 805583 | Approved/Printed | 2025-10-13 | 2025-10-28 | NEWCON | 19054 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 16 | 16 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3692 | 3692 | Invoiced | Invoiced | 3 | 148 |  |  |  | 2025-10-01 | completed | Invoiced
149 | 240592 | 149 | 2025-10-08 | 2025-10-07 | 2025-10-18 | 2025-10-18 | 2025-10-26 | DS | C- 90707A (MSA-18036280) | 8 | 1152668 | Completed | 805649 | Approved/Printed | 2025-10-14 | 2025-10-29 | NEWCON | 4206 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1795 | 1795 | Invoiced | Invoiced | 2 | 149 |  |  |  | 2025-10-01 | completed | Invoiced
150 | 240593 | 150 | 2025-10-08 | 2025-10-07 | 2025-10-18 | 2025-10-18 | 2025-10-27 | DS | C-123993 (MSA-18036170) | 9 | 1152669 | Completed | 805649 | Approved/Printed | 2025-10-14 | 2025-10-29 | NEWCON | 39090 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 4 | 4 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1450 | 1450 | Invoiced | Invoiced | 2 | 150 |  |  |  | 2025-10-01 | completed | Invoiced
151 | 240594 | 151 | 2025-10-08 | 2025-10-07 | 2025-10-18 | 2025-10-18 | 2025-10-27 | DS | C-1081912 (MSA-18031303) | 9 | 1152680 | Completed | 805649 | Approved/Printed | 2025-10-14 | 2025-10-29 | NEWCON | 12890 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 5 | 5 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1510 | 1510 | Invoiced | Invoiced | 2 | 151 |  |  |  | 2025-10-01 | completed | Invoiced
152 | 240643 | 152 | 2025-10-09 | 2025-10-08 | 2025-10-19 | 2025-10-19 | 2025-10-25 | DS | MOC-224680+1+2+3+ 4+5+6+7 | 6 | 1153051 | Completed | RO NA | RO NA | NA | NA | NEWCON | 18477 | 8 | New District Of Doha 69 (69 ) | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 8 | 8 | 0 | 0 | 4160 | 4160 | Invoiced | Invoiced | 5 | 152 |  |  |  | 2025-10-01 | Completed | Invoiced
153 | 240644 | 153 | 2025-10-09 | 2025-10-08 | 2025-10-19 | 2025-10-19 | 2025-10-25 | DS | MOC-221244 | 6 | 1153055 | Completed | RO NA | RO NA | NA | NA | NEWCON | 17265 | 1 | New District Of Doha 69 (69 ) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 520 | 520 | Invoiced | Invoiced | 7 | 153 |  |  |  | 2025-10-01 | Completed | Invoiced
154 | 240648 | 154 | 2025-10-09 | 2025-10-08 | 2025-10-19 | 2025-10-19 | 2025-11-06 | DS | MOC-225760 | 18 | 1153076 | Completed | 806481 | Approved/Printed | 2025-10-25 | 2025-11-09 | NEWCON | 33991 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1735 | 1735 | Invoiced | Invoiced | 2 | 154 |  |  |  | 2025-10-01 | completed | Invoiced
155 | 240650 | 155 | 2025-10-09 | 2025-10-08 | 2025-10-19 | 2025-10-19 | 2025-10-27 | DS | C-1061682 (MSA-18036084) | 8 | 1153079 | Completed | 805649 | Approved/Printed | 2025-10-14 | 2025-10-29 | NEWCON | 12676 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1912 | 1912 | Invoiced | Invoiced | 3 | 155 |  |  |  | 2025-10-01 | completed | Invoiced
156 | 240651 | 156 | 2025-10-09 | 2025-10-08 | 2025-10-19 | 2025-10-19 | 2025-11-02 | DS | MOC-237959+237960 | 14 | 1153081 | Completed | 806589 | Approved/Printed | 2025-10-25 | 2025-11-09 | NEWCON | 0754 | 2 | Al Rayyan Al Jadeed/Muaither N(53 ) | 14 | 14 | 0 | 0 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 |  | 0 |  | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 3938 | 3938 | Invoiced | Invoiced | 3 | 156 |  |  |  | 2025-10-01 | completed | Invoiced
157 | 240652 | 157 | 2025-10-09 | 2025-10-08 | 2025-10-19 | 2025-10-19 | 2025-10-27 | DS | MOC-243614 | 8 | 1153082 | Completed | 805738 | Approved/Printed | 2025-10-15 | 2025-10-30 | NEWCON | 25414 | 1 | Al Shahhniya (80 ) | 6 | 6 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1510 | 1510 | Invoiced | Invoiced | 5 | 157 |  |  |  | 2025-10-01 | Completed | Invoiced
158 | 240653 | 158 | 2025-10-09 | 2025-10-08 | 2025-10-19 | 2025-12-09 | 2026-01-07 | MOC + BP | 233552+N/2020/3838(PIN24140013) | 80 | 1153083 | Completed | 806343/ 814754/ 822296 | Approved/Printed | 2026-04-16 | 2026-06-27 | NEWCON | 27120 | 1 | Al Muntazah (24 ) | 318 | 318 | 96 | 96 | 0 | 0 | 268 | 268 | 44 | 44 | 120 | 120 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 2 | 69741 | 69741 | Invoiced | Invoiced | 12 | 158 |  |  |  | 2026-01-01 | completed | Invoiced
159 | 240663 | 159 | 2025-10-12 | 2025-10-11 | 2025-10-22 | 2025-12-12 | 2025-11-24 | MOC | MOC-236040 | 33 | 1153688 | Completed | 806344 | Approved/Printed | 2025-11-05 | 2026-04-23 | NEWCON | 3 3991 | 1 | Al Luqta/Al Rayyan Al Qadeem (52 ) | 73 | 73 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 8785 | 8785 | Invoiced | Invoiced | 4 | 159 |  |  |  | 2025-11-01 | completed | Invoiced
160 | 240664 | 160 | 2025-10-12 | 2025-10-11 | 2025-10-22 | 2025-10-22 | 2025-10-18 | DS | MOC-239350 | -4 | 1153693 | Completed | RO NA | RO NA | NA | NA | NEWCON | 31474 | 1 | New District Of Doha 69 (69 ) | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 1 | 1 | 0 | 0 | 520 | 520 | Invoiced | Invoiced | 6 | 160 |  |  |  | 2025-10-01 | Completed | Invoiced
161 | 240666 | 161 | 2025-10-12 | 2025-10-11 | 2025-10-22 | 2025-10-22 | 2025-11-05 | MOC | 238148 + 46 + 47 | 14 | 1153811 | Completed | 805739 | Approved/Printed | 2025-10-19 | 2026-04-16 | NEWCON | 35043 | 3 | Al Soudan South/Al Aziziya/Al (55 ) | 375 | 375 | 0 | 0 | 60 | 60 | 0 |  | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 29530 | 29530 | Invoiced | Invoiced | 2 | 161 |  |  |  | 2025-11-01 | completed | Invoiced
162 | 240669 | 162 | 2025-10-12 | 2025-10-11 | 2025-10-22 | 2025-10-22 | 2026-09-12 | MOC | MOC-230894 | 325 | 1153819 | Completed | 806345 | Approved/Printed | 2025-10-28 | 2026-04-23 | NEWCON | 12537 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 150 | 150 | 0 | 0 | 0 | 0 | 150 | 150 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 21260 | 21260 | Invoiced | Invoiced | 4 | 162 |  |  |  | 2025-11-01 | completed | Invoiced
163 | 240665 | 163 | 2025-10-12 | 2025-10-11 | 2025-10-22 | 2026-01-11 | 2025-11-27 | BP | BP#N/2024/7831 (PIN57040091) | 36 | 1153799 | Completed | 806346 | Approved/Printed | 2025-11-09 | 2026-04-23 | NEWCON | 10017 | 1 | Industrial Area (57 ) | 392 | 392 | 0 |  | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 27193 | 27193 | Invoiced | Invoiced | 4 | 163 |  |  |  | 2025-11-01 | completed | Invoiced
164 | 240667 | 164 | 2025-10-12 | 2025-10-11 | 2025-10-22 | 2026-01-11 | 2025-12-24 | BP | BP# N/2025/3903 (PIN35040003) | 63 | 1153809 | Completed | 806347 | Approved/Printed | 2025-11-08 | 2026-04-23 | NEWCON | 24869 | 1 | Kulaib (35 ) | 260 | 260 | 0 |  | 0 | 0 | 228 | 228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 29936 | 29936 | Invoiced | Invoiced | 6 | 164 |  |  |  | 2025-12-01 | completed | Invoiced
165 | 240668 | 165 | 2025-10-12 | 2025-10-11 | 2025-10-22 | 2026-01-11 | 2026-02-23 | BP | BP#150398 | 124 | 1153817 | Completed | 810947 | Approved/Printed | 2025-12-31 | 2026-06-25 | NEWCON | 4198 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 214 | 214 | 0 |  | 0 | 0 | 214 | 214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 27558 | 27558 | Invoiced | Invoiced | 8 | 165 |  |  |  | 2026-02-01 | Completed | Invoiced
166 | 240689 | 166 | 2026-01-13 | 2026-01-12 | 2026-01-23 | 2026-03-13 | 2026-02-14 | MOC | IN-113876 | 22 | 1153897 | Completed | 810945 | Approved/Printed | 2025-12-29 | 2026-06-25 | NEWCON | 3170 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 105 | 105 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 20 | 20 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 11200 | 11200 | Invoiced | Invoiced | 13 | 166 |  |  |  | 2026-02-01 | Completed | Invoiced
167 | 240702 | 167 | 2025-10-12 | 2025-10-11 | 2025-10-22 | 2025-10-22 | 2025-11-15 | DS | MOC-235197+98 | 24 | 1154055 | Completed | 806076 | Approved/Printed | 2025-11-06 | 2026-04-16 | NEWCON | 10288 | 2 | Umm Slal/Al Kharaitiyat (71 ) | 16 | 16 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 0 | 0 | 1 | 1 | 1 | 1 | 4835 | 4835 | Invoiced | Invoiced | 4 | 167 |  |  |  | 2025-11-01 | completed | Invoiced
168 | 240704 | 168 | 2025-10-12 | 2025-10-11 | 2025-10-22 | 2025-12-12 | 2025-11-17 | MOC | MOC-245195+96 | 26 | 1154088 | Completed | 806076 | Approved/Printed | 2025-11-06 | 2026-04-16 | NEWCON | 25315 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 95 | 95 | 0 | 0 | 0 | 0 | 95 | 95 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 |  | 1 | 1 | 3 | 3 | 0 | 0 | 2 | 2 | 0 | 0 | 14105 | 14105 | Invoiced | Invoiced | 4 | 168 |  |  |  | 2025-11-01 | completed | Invoiced
169 | 240888 | 169 | 2025-10-15 | 2025-10-14 | 2025-10-25 | 2025-12-15 | 2025-11-12 | MOC | MOC-181454 | 18 | 1155843 | Completed | 806349 | Approved/Printed | 2025-10-29 | 2026-04-23 | NEWCON | 23649 | 1 | Fareeq Al Amir/Muraykh/Al Soud(54 ) | 140 | 140 | 0 | 0 | 0 | 0 | 11 | 11 | 36 | 36 | 40 | 40 | 2 | 2 | 0 | 0 | 3 | 3 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 22367 | 22367 | Invoiced | Invoiced | 9 | 169 |  |  |  | 2025-11-01 | completed | Invoiced
170 | 240898 | 170 | 2025-11-20 | 2025-11-19 | 2025-11-30 | 2026-01-20 | 2026-01-07 | MOC | MOC-246044 | 38 | 1156076 | Completed | 809921 | Approved/Printed | 2025-12-08 | 2026-06-04 | NEWCON | 13470 | 1 | Al Kheesa (70 ) | 167 | 167 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 12450 | 12450 | Invoiced | Invoiced | 7 | 170 |  |  |  | 2026-01-01 | completed | Invoiced
171 | 240899 | 171 | 2025-10-16 | 2025-10-15 | 2025-10-26 | 2026-01-16 | 2026-03-30 | BP | BP150148 | 155 | 1156120 | Completed | 810557 | Approved/Printed | 2025-12-25 | 2026-06-11 | NEWCON | 25228 | 1 | Al Khor (74 ) | 14 | 14 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 3505 | 3505 | Invoiced | Invoiced | 10 | 171 |  |  |  | 2026-03-31 | completed | Invoiced
172 | 240745 | 172 | 2025-10-13 | 2025-10-12 | 2025-10-23 | 2025-12-01 | 2026-01-06 | BP | BP#150363 | 75 | 1154395 | Completed | 810943 | Approved/Printed | 2025-12-30 | 2026-06-25 | NEWCON | 23479 | 1 | Al Kheesa (70 ) | 100 | 100 | 0 |  | 0 | 0 | 88 | 88 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 13446 | 13446 | Invoiced | Invoiced | 7 | 172 |  |  |  | 2026-01-01 | completed | Invoiced
173 | 240763 | 173 | 2025-10-13 | 2025-10-12 | 2025-10-23 | 2025-12-01 | 2026-02-01 | BP | BP# N/2025/3189 (PIN71053807) | 101 | 1154429 | Completed | 810945 | Approved/Printed | 2025-12-29 | 2026-06-25 | NEWCON | 10815 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 288 | 288 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 18560 | 18560 | Invoiced | Invoiced | 7 | 173 |  |  |  | 2026-01-01 | completed | Invoiced
174 | 240768 | 174 | 2025-10-13 | 2025-10-12 | 2025-10-23 | 2025-12-13 | 2025-11-17 | MOC | C- 981711 ( MSA-18036154 ) | 25 | 1154438 | Completed | 806345 | Approved/Printed | 2025-10-28 | 2026-04-23 | NEWCON | 40939 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 16 | 16 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 |  | 1 | 1 | 4372 | 4372 | Invoiced | Invoiced | 5 | 174 |  |  |  | 2025-11-01 | Completed | Invoiced
175 | 240776 | 175 | 2025-10-13 | 2025-10-12 | 2025-10-23 | 2025-10-23 | 2025-10-23 | DS | MOC-239711 | 0 | 1154470 | Completed | 806207 | Approved/Printed | 2025-10-20 | 2025-11-04 | NEWCON | 40733 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 6 | 6 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1510 | 1510 | Invoiced | Invoiced | 2 | 175 |  |  |  | 2025-10-01 | completed | Invoiced
176 | 240796 | 176 | 2025-10-14 | 2025-10-13 | 2025-10-24 | 2025-12-14 | 2025-11-24 | MOC | MOC-242207 | 31 | 1154600 | Completed | 806352 | Approved/Printed | 2025-11-04 | 2026-04-23 | NEWCON | 19539 | 1 | Madinat Khalifa (South) (34 ) | 32 | 32 | 0 | 0 | 0 | 0 | 26 | 26 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 4 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 7832 | 7832 | Invoiced | Invoiced | 4 | 176 |  |  |  | 2025-11-01 | completed | Invoiced
177 | 240798 | 177 | 2025-10-14 | 2025-10-13 | 2025-10-24 | 2025-12-14 | 2025-12-25 | MOC | C-1206702 ( MSA-18036300 ) | 62 | 1154609 | Completed | 806353 | Approved/Printed | 2025-11-11 | 2026-04-23 | NEWCON | 5968 | 1 | Fareeq Al Amir/Muraykh/Al Soud(54 ) | 48 | 48 | 0 | 0 | 0 | 0 | 27 | 27 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 7179 | 7179 | Invoiced | Invoiced | 7 | 177 |  |  |  | 2025-12-01 | completed | Invoiced
178 | 240843 | 178 | 2025-10-14 | 2025-10-13 | 2025-10-24 | 2026-01-14 | 2026-01-26 | BP | BP # N/2025/3035 ( PIN71570031) | 94 | 1155036 | Completed | 810945 | Approved/Printed | 2025-12-29 | 2026-06-25 | NEWCON | 13634 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 208 | 208 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 13505 | 13505 | Invoiced | Invoiced | 6 | 178 |  |  |  | 2026-01-26 | completed | Invoiced
179 | 240904 | 179 | 2025-10-16 | 2025-10-15 | 2025-10-26 | 2026-01-16 | 2026-04-23 | BP | BP#N/2024/7040 ( PIN74090423 ) | 179 | 1156135 | Completed | 810557/ 821171/ 825161 | Approved/Printed | 2025-12-25 | 2026-05-23 | NEWCON | 12489 | 1 | Al Khor (74 ) | 83 | 83 | 32 | 32 | 0 | 0 | 26 | 26 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 17152 | 17152 | Invoiced | Invoiced | 11 | 179 |  |  |  | 2026-04-19 | completed | Invoiced
180 | 240906 | 180 | 2025-10-16 | 2025-10-15 | 2025-10-26 | 2026-01-16 | 2026-02-01 | BP | BP150178 | 98 | 1156143 | Completed | 810557 | Approved/Printed | 2025-12-25 | 2026-06-11 | AL MORAQUIB | 2317 | 1 | Al Khor (74 ) | 114 | 114 | 0 | 0 | 0 | 0 | 114 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 14028 | 14028 | Invoiced | Invoiced | 9 | 180 |  |  |  | 2026-02-01 | Completed | Invoiced
181 | 240941 | 181 | 2025-10-19 | 2025-10-18 | 2025-10-29 | 2026-01-19 | 2026-02-28 | BP | BP#N/2024/6502 ( PIN71510659 ) | 122 | 1157042 | Completed | 810946 | Approved/Printed | 2025-12-23 | 2026-06-25 | NEWCON | 24024 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 130 | 130 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 0 | 0 |  |  | 0 | 0 | 10169 | 10169 | Invoiced | Invoiced | 7 | 181 |  |  |  | 2026-02-18 | completed | Invoiced
182 | 240942 | 182 | 2025-10-19 | 2025-10-18 | 2025-10-29 | 2026-01-19 | 2026-04-13 | BP | BP#N/2025/3063 ( PIN74050382 ) | 166 | 1157049 | Completed | 810553 | Approved/Printed | 2025-12-25 | 2026-06-11 | NEWCON | 3199 | 1 | Al Khor (74 ) | 84 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5690 | 5690 | Invoiced | Invoiced | 9 | 182 |  |  |  | 2026-04-07 | completed | Invoiced
183 | 240944 | 183 | 2025-10-19 | 2025-10-18 | 2025-10-29 | 2026-01-19 | 2026-02-12 | BP | BP-N/2025/3336 ( PIN74180136 ) | 106 | 1157055 | completed | 810552 | Approved/Printed | 2025-12-25 | 2026-06-11 | KUSHI | 2949 | 1 | Al Khor (74 ) | 276 | 276 | 0 | 0 | 0 | 0 | 242 | 242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 |  | 0 | 0 | 34214 | 34214 | Invoiced | Invoiced | 8 | 183 |  |  |  | 2026-02-01 | completed | Invoiced
184 | 240945 | 184 | 2025-10-19 | 2025-10-18 | 2025-10-29 | 2026-01-19 | 2026-04-02 | BP | BP150896 | 155 | 1157058 | Completed | 810951 | Approved/Printed | 2026-01-12 | 2026-06-25 | NEWCON | 22493 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 |  |  | 0 | 0 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 10630 | 10630 | Invoiced | Invoiced | 10 | 184 |  |  |  | 2026-03-29 | completed | Invoiced
185 | 240952 | 185 | 2025-10-19 | 2025-10-18 | 2025-10-29 | 2026-01-19 | 2026-09-12 | MOC | 235380+81+234282 | 318 | 1157109 | Cancelled | 806606 | RO Approved/Job Cancelled | 2025-10-28 | 2026-04-23 | NEWCON | 35050 | 3 | Al Soudan South/Al Aziziya/Al (55 ) | 290 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 |  | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 22971 | 0 | Cancelled | Cancelled | Cancelled | 185 |  |  |  |  | Cancelled | Cancelled
186 | 240964 | 186 | 2025-10-19 | 2025-10-18 | 2025-10-29 | 2025-12-19 | 2025-11-11 | MOC | MOC-245909 | 13 | 1157233 | Completed | 806342 | Approved/Printed | 2025-10-28 | 2026-04-23 | NEWCON | 34294 | 1 | Al Shahhniya (80 ) | 39 | 39 | 0 | 0 | 10 | 10 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 3 | 5 | 5 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 6945 | 6945 | Invoiced | Invoiced | 3 | 186 |  |  |  | 2025-11-01 | completed | Invoiced
187 | 240986 | 187 | 2025-10-20 | 2025-10-19 | 2025-10-30 | 2025-12-20 | 2025-11-26 | MOC | MOC-216383 | 27 | 1157663 | Completed | 806707 | Approved/Printed | 2025-11-06 | 2026-04-30 | NEWCON | 36809 | 1 | Al Kheesa (70 ) | 60 | 60 | 0 | 0 | 0 | 0 | 56 | 56 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 5 | 5 | 4 | 4 | 0 | 0 | 1 | 1 | 0 | 0 | 10302 | 10302 | Invoiced | Invoiced | 6 | 187 |  |  |  | 2025-12-07 | Pending | Invoiced
188 | 240994 | 188 | 2025-10-20 | 2025-10-19 | 2025-10-30 | 2025-12-20 | 2025-11-23 | MOC | MOC-246461 | 24 | 1157679 | Completed | 806708 | Approved/Printed | 2025-11-06 | 2026-04-30 | NEWCON | 12842 | 1 | New District Of Doha 67 (67 ) | 75 | 75 | 0 | 0 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 10615 | 10615 | Invoiced | Invoiced | 4 | 188 |  |  |  | 2025-11-01 | Completed | Invoiced
189 | 241022 | 189 | 2025-10-21 | 2025-10-20 | 2025-10-31 | 2026-01-21 | 2026-04-23 | BP | BP150443 | 174 | 1158022 | Completed | 806939/ 821825 | Approved/Printed | 2025-12-11 | 2026-04-30 | NEWCON | 15497 | 1 | Al Thakhira (75 ) | 26 | 26 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8780 | 8780 | Invoiced | Invoiced | 10 | 189 |  |  |  | 2026-04-19 | completed | Invoiced
190 | 241027 | 190 | 2025-10-21 | 2025-10-20 | 2025-10-31 | 2026-01-21 | 2026-09-12 | BP | BP-150437+ BP-150439 | 316 | 1158077 | Not Clear | Hold | Hold | Pending | Pending | NEWCON | 9802 | 2 | Al Kheesa (70 ) | 175 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2 |  | 2 |  | 2 |  | 0 | 0 | 0 |  | 0 | 0 | 13060 | 0 | Hold | Pending | Pending | 190 |  |  |  |  | Pending | Pending
191 | 241028 | 191 | 2025-10-21 | 2025-10-20 | 2025-10-31 | 2026-01-21 | 2025-11-19 | BP | BP#N/2024/6464 ( PIN82020609 ) | 19 | 1158094 | Completed | 806940 | Approved/Printed | 2025-11-05 | 2026-04-30 | NEWCON | 31736 | 1 | RAUDAT RASHID (82 ) | 48 | 48 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 3570 | 3570 | Invoiced | Invoiced | 3 | 191 |  |  |  | 2025-11-01 | completed | Invoiced
192 | 241029 | 192 | 2025-10-21 | 2025-10-20 | 2025-10-31 | 2026-01-21 | 2026-06-08 | BP | BP#N/2025/3831 ( PIN74160095 ) | 220 | 1158098 | Completed | 810552 | Approved/Printed | 2025-12-25 | 2026-06-11 | NEWCON | 1329 | 1 | Al Khor (74 ) | 67 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4455 | 4455 | Invoiced | Invoiced | 12 | 192 |  |  |  | 2026-06-04 | completed | Invoiced
193 | 241030 | 193 | 2025-10-21 | 2025-10-20 | 2025-10-31 | 2026-01-21 | 2026-03-09 | BP | BP150457 | 129 | 1158103 | Completed | 810943 | Approved/Printed | 2025-12-30 | 2026-06-25 | NEWCON | 5160 | 1 | Al Kheesa (70 ) | 46 | 46 | 0 | 0 | 0 | 0 | 46 | 46 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 | 1 | 1 | 1 |  |  | 0 | 0 |  |  | 0 | 0 | 6032 | 6032 | Invoiced | Invoiced | 10 | 193 |  |  |  | 2026-03-08 | completed | Invoiced
194 | 241031 | 194 | 2025-10-21 | 2025-10-20 | 2025-10-31 | 2026-01-21 | 2025-11-19 | BP | BP-N/2024/6465 ( PIN82020606 ) | 19 | 1158120 | Completed | 806940 | Approved/Printed | 2025-11-05 | 2026-04-30 | NEWCON | 21941 | 1 | RAUDAT RASHID (82 ) | 57 | 57 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 4110 | 4110 | Invoiced | Invoiced | 3 | 194 |  |  |  | 2025-11-01 | completed | Invoiced
195 | 241046 | 195 | 2025-10-21 | 2025-10-20 | 2025-10-31 | 2026-12-21 | 2025-05-06 | MOC | MOC-208057 | -178 | 1158164 | Completed | 806709 | Approved/Printed | 2025-11-20 | 2026-05-14 | NEWCON | 36967 | 1 | Al Duhail South (31 ) | 96 | 96 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 1 | 2 | 2 | 0 | 0 | 0 |  | 1 | 1 | 8200 | 8200 | Invoiced | Invoiced | 5 | 195 |  |  |  | 2025-12-01 | Completed | Invoiced
196 | 241070 | 196 | 2025-10-21 | 2025-10-20 | 2025-10-19 | 2025-10-18 | 2025-10-25 | DS | MOC-219281 | 6 | 1158300 | Completed | RO NA | RO NA | NA | NA | NEWCON | 17763 | 1 | New District Of Doha 69 (69 ) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 1 | 1 | 0 | 0 | 520 | 520 | Invoiced | Invoiced | 7 | 196 |  |  |  | 2025-10-01 | Completed | Invoiced
197 | 241083 | 197 | 2025-10-22 | 2025-10-21 | 2025-11-01 | 2026-01-22 | 2026-04-20 | BP | BP149247 | 170 | 1158643 | Completed | 810552 | Approved/Printed | 2025-12-25 | 2026-06-11 | NEWCON | 10319 | 1 | Al Khor (74 ) | 135 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 9650 | 9650 | Invoiced | Invoiced | 11 | 197 |  |  |  | 2026-04-14 | completed | Invoiced
198 | 241084 | 198 | 2025-10-22 | 2025-10-21 | 2025-11-01 | 2026-01-22 | 2026-02-15 | BP | BP150130 | 106 | 1158652 | Completed | 810948 | Approved/Printed | 2026-01-07 | 2026-06-25 | NEWCON | 41134 | 1 | Al Kheesa (70 ) | 153 | 153 | 0 | 0 | 40 | 40 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 0 |  | 1 | 1 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 11135 | 11135 | Invoiced | Invoiced | 8 | 198 |  |  |  | 2026-02-01 | completed | Invoiced
199 | 241085 | 199 | 2025-10-22 | 2025-10-21 | 2025-11-01 | 2026-01-22 | 2026-04-20 | BP | BP150827 | 170 | 1158655 | Completed | 810951 | Approved/Printed | 2026-01-12 | 2026-06-25 | NEWCON | 4160 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 30 | 30 | 0 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 4200 | Invoiced | Invoiced | 10 | 199 |  |  |  | 2026-04-06 | completed | Invoiced
200 | 241122 | 200 | 2026-03-09 | 2026-03-08 | 2026-03-19 | 2026-05-09 | 2026-05-14 | MOC | MOC-241549+50+51 | 56 | 1158843 | Completed | 806939/ 820332 | Approved/Printed | 2026-04-01 | 2026-05-31 | AL MORAQUIB | 2537 | 3 | Al Thakhira (75 ) | 230 | 230 | 64 | 64 | 0 | 0 | 100 | 100 | 0 | 0 | 80 | 80 | 3 | 3 | 0 | 0 | 1 | 1 | 1 | 1 | 4 | 4 | 0 | 0 | 3 | 3 | 0 | 0 | 41750 | 41750 | Invoiced | Invoiced | 11 | 200 |  |  |  | 2026-04-06 | Completed | Invoiced
201 | 241128 | 201 | 2025-10-23 | 2025-10-22 | 2025-11-02 | 2026-01-23 | 2025-12-04 | BP | BP124431 | 32 | 1159078 | Completed | 806943 | Approved/Printed | 2025-11-17 | 2026-04-30 | NEWCON | 4284 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 64 | 64 | 0 | 0 | 0 | 0 | 64 | 64 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 8178 | 8178 | Invoiced | Invoiced | 5 | 201 |  |  |  | 2025-12-25 | completed | Invoiced
202 | 241129 | 202 | 2025-10-23 | 2025-10-22 | 2025-11-02 | 2026-01-23 | 2026-09-12 | BP | BP146560 | 314 | 1159080 | Cancelled | NA | NA | Cancelled | Cancelled | NEWCON | 12831 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 60 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 5457 | 0 | Cancelled | Cancelled | Cancelled | 202 |  |  |  |  | Cancelled | Cancelled
203 | 241131 | 203 | 2025-10-23 | 2025-10-22 | 2025-11-02 | 2026-01-23 | 2026-03-31 | BP | BP#N/2024/6004 ( PIN74050006 ) | 149 | 1159099 | Completed | 810553 | Approved/Printed | 2025-12-25 | 2026-06-11 | AL MORAQUIB | 9914 | 1 | Al Khor (74 ) | 202 | 202 | 0 | 0 | 0 | 0 | 53 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16381 | 16381 | Invoiced | Invoiced | 10 | 203 |  |  |  | 2026-03-25 | completed | Invoiced
204 | 241136 | 204 | 2025-10-23 | 2025-10-22 | 2025-11-02 | 2025-12-23 | 2025-11-16 | MOC | MOC-229557 | 14 | 1159122 | Completed | 806945 | Approved/Printed | 2025-11-01 | 2026-04-30 | NEWCON | 34485 | 1 | Al Shahhniya (80 ) | 78 | 78 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 5 | 5 | 4 | 4 | 0 | 0 | 1 | 1 | 0 | 0 | 9200 | 9200 | Invoiced | Invoiced | 3 | 204 |  |  |  | 2025-11-01 | completed | Invoiced
205 | 241154 | 205 | 2025-10-23 | 2025-10-22 | 2025-11-02 | 2025-12-23 | 2025-11-18 | MOC | MOC-241521 | 16 | 1159349 | Completed | 806946 | Approved/Printed | 2025-11-05 | 2026-04-30 | NEWCON | 27385 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 122 | 122 | 0 | 0 | 0 | 0 | 61 | 61 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2 | 2 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 13327 | 13327 | Invoiced | Invoiced | 5 | 205 |  |  |  | 2025-11-01 | Completed | Invoiced
206 | 241180 | 206 | 2025-10-26 | 2025-10-25 | 2025-11-05 | 2025-12-26 | 2025-11-11 | MOC | MOC-248112 | 6 | 1160176 | Completed | 806945 | Approved/Printed | 2025-11-01 | 2026-04-30 | NEWCON | 34522 | 1 | Al Shahhniya (80 ) | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 |  | 3050 | 3050 | Invoiced | Invoiced | 3 | 206 |  |  |  | 2025-11-01 | completed | Invoiced
207 | 241305 | 207 | 2025-10-30 | 2025-10-29 | 2025-11-09 | 2026-01-29 | 2026-04-08 | BP | BP#150785 | 150 | 1161899 | completed | 808145 | Approved/Printed | 2025-12-22 | 2026-05-14 | NEWCON | 1787 | 1 | New District Of Doha 63 (63 ) | 74 | 74 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 292 | 292 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 50561 | 50561 | Invoiced | Invoiced | 11 | 207 |  |  |  | 2026-04-06 | completed | Invoiced
208 | 241336 | 208 | 2025-10-30 | 2025-10-29 | 2025-11-09 | 2025-12-30 | 2025-12-04 | MOC | MOC-248059+115 | 25 | 1162036 | Completed | 808146 | Approved/Printed | 2025-11-19 | 2026-05-14 | NEWCON | 25011 | 2 | Al Kheesa (70 ) | 147 | 147 | 0 | 0 | 0 | 0 | 56 | 56 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 3 | 3 | 6 | 6 | 4 | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 17702 | 17702 | Invoiced | Invoiced | 5 | 208 |  |  |  | 2025-12-01 | Completed | Invoiced
209 | 241345 | 209 | 2025-11-02 | 2025-11-01 | 2025-11-12 | 2026-01-02 | 2025-11-13 | MOC | C-161312 ( MSA-18031658 ) | 1 | 1162633 | Completed | 807816 | Approved/Printed | 2025-11-08 | 2025-11-23 | NEWCON | 4553 | 1 | Al Duhail South (31 ) | 27 | 27 | 0 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 4945 | 4945 | Invoiced | Invoiced | 3 | 209 |  |  |  | 2025-11-01 | completed | Invoiced
210 | 241347 | 210 | 2025-11-02 | 2025-11-01 | 2025-11-12 | 2026-01-02 | 2025-01-15 | MOC | C-76307 ( MSA-18036234 ) | -301 | 1162716 | Completed | 810728 | Approved/Printed | 2025-12-17 | 2026-02-14 | NEWCON | 1286 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 24 | 24 | 40 | 40 | 0 | 0 | 22 | 22 | 0 | 0 | 40 | 40 | 1 | 1 | 0 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 13954 | 13954 | Invoiced | Invoiced | 6 | 210 |  |  |  | 2026-01-01 | Completed | Invoiced
211 | 241361 | 211 | 2025-11-02 | 2025-11-01 | 2025-11-12 | 2026-02-02 | 2026-01-04 | BP | BP142389 | 53 | 1162781 | Completed | 803662 | Approved/Printed | 2025-12-10 | 2026-05-21 | NEWCON | 4413 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 100 | 100 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 7334 | 7334 | Invoiced | Invoiced | 6 | 211 |  |  |  | 2026-01-01 | completed | Invoiced
212 | 241362 | 212 | 2026-01-15 | 2026-01-14 | 2026-01-25 | 2026-02-02 | 2026-03-28 | MOC | MOC-241606 | 62 | 1162787 | Completed | 815386 | Approved/Printed | 2026-02-24 | 2026-07-30 | AL MORAQUIB | 1993 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 156 | 156 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 12819 | 12819 | Invoiced | Invoiced | 10 | 212 |  |  |  | 2026-03-26 | completed | Invoiced
213 | 241363 | 213 | 2025-11-02 | 2025-11-01 | 2025-11-12 | 2026-02-02 | 2026-09-12 | BP | BP129769 | 304 | 1162808 | Not Clear | Hold | Hold | Pending | Pending | NEWCON | 13184 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 233 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 15837 | 0 | Hold | Pending | Pending | 213 |  |  |  |  | Pending | Pending
214 | 241376 | 214 | 2025-11-03 | 2025-11-02 | 2025-11-13 | 2026-02-03 | 2026-09-12 | BP | BP150468 | 303 | 1162956 | LIVE TDP | Hold | Hold | Pending | Pending | NEWCON | 40657 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 92 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 7377 | 0 | Hold | Pending | Pending | 214 |  |  |  |  | Pending | Pending
215 | 241380 | 215 | 2026-05-14 | 2026-05-13 | 2026-05-24 | 2026-07-05 | 2026-06-07 | MOC | IN-115294 MOC-252752 | 14 | 1162971 | Completed | 810951/ 827903 | Approved/Printed | 2026-05-20 | 2026-11-15 | NEWCON | 27609 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 254 | 254 | 0 | 0 | 0 | 0 | 254 | 254 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 32108 | 32108 | Invoiced | Invoiced | 12 | 215 |  |  |  | 2026-06-01 | Completed | Invoiced
216 | 241404 | 216 | 2025-11-03 | 2025-11-02 | 2025-11-13 | 2026-02-03 | 2026-09-12 | BP | BP# N/2025/8302 ( PIN71204010) | 303 | 1163094 | Cancelled | 810946 | Approved/Printed | 2025-12-23 | 2026-06-25 | Cancelled | 23953 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 39 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 4197 | 0 | Cancelled | Cancelled | Cancelled | 216 |  |  |  |  | Cancelled | Cancelled
217 | 241409 | 217 | 2025-11-03 | 2025-11-02 | 2025-11-13 | 2026-02-03 | 2026-01-15 | BP | BP150490 | 63 | 1163189 | Completed | 810946 | Approved/Printed | 2025-12-23 | 2026-06-25 | NEWCON | 27119 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 63 | 63 | 0 | 0 | 0 | 0 | 129 | 129 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 13793 | 13793 | Invoiced | Invoiced | 11 | 217 |  |  |  | 2026-01-01 | completed | Invoiced
218 | 241410 | 218 | 2026-07-07 | 2026-07-06 | 2026-07-17 | 2026-09-07 | 2026-08-18 | MOC | IN-116324 MOC-246711 | 32 | 1163194 | Completed | 810569/ 832431 | Approved/Printed | 2026-07-20 | 2026-12-25 | NEWCON | 18505 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 135 | 135 | 0 | 0 | 0 | 0 | 84 | 84 | 20 | 20 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 3 | 3 | 4 | 4 | 0 | 0 | 0 |  | 0 | 0 | 17088 | 17088 | Completed | Pending | Pending | 218 |  |  |  | 2026-08-12 | Pending | Pending
219 | 241415 | 219 | 2025-11-03 | 2025-11-02 | 2025-11-13 | 2026-02-03 | 2026-03-24 | BP | BP150500 | 131 | 1163202 | Completed | 810946 | Approved/Printed | 2025-12-23 | 2026-06-25 | NEWCON | 23903 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 68 | 68 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5112 | 5112 | Invoiced | Invoiced | 10 | 219 |  |  |  | 2026-03-11 | completed | Invoiced
220 | 241420 | 220 | 2025-11-03 | 2025-11-02 | 2025-11-13 | 2026-02-03 | 2026-04-14 | BP | BP150497 | 152 | 1163216 | Completed | 810948 | Approved/Printed | 2026-01-07 | 2026-06-25 | AL MORAQUIB | 19401 | 1 | Al Kheesa (70 ) | 96 | 96 | 0 | 0 | 0 | 0 | 96 | 96 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 13662 | 13662 | Invoiced | Invoiced | 12 | 220 |  |  |  | 2026-04-12 | completed | Invoiced
221 | 241423 | 221 | 2025-11-03 | 2025-11-02 | 2025-11-13 | 2026-02-03 | 2026-01-14 | BP | BP150496 | 62 | 1163219 | Completed | 810552 | Approved/Printed | 2025-12-25 | 2026-06-11 | NEWCON | 26577 | 1 | Al Khor (74 ) | 75 | 75 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 5150 | 5150 | Invoiced | Invoiced | 7 | 221 |  |  |  | 2026-01-01 | Completed | Invoiced
222 | 241402 | 222 | 2025-11-03 | 2025-11-02 | 2025-11-13 | 2026-02-03 | 2026-01-18 | OL | OL-F2-3537 | 66 | 1163073 | Completed | 810567 | Approved/Printed | 2026-01-04 | 2026-06-18 | NEWCON | 3537 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1392 | 1392 | Invoiced | Invoiced | 7 | 222 |  |  |  | 2026-01-01 | completed | Invoiced
223 | 241403 | 223 | 2025-11-03 | 2025-11-02 | 2025-11-13 | 2026-02-03 | 2026-01-18 | OL | OL-F1-3506 | 66 | 1163085 | Completed | 810567 | Approved/Printed | 2026-01-04 | 2026-06-18 | NEWCON | 3506 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 115 | 115 | 0 | 0 | 0 | 0 | 115 | 115 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2 | 2 | 1 | 1 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 14695 | 14695 | Invoiced | Invoiced | 7 | 223 |  |  |  | 2026-01-01 | Completed | Invoiced
224 | 241426 | 224 | 2025-11-03 | 2025-11-02 | 2025-11-13 | 2026-02-03 | 2026-02-12 | OL | OL-F6-F10-2949 | 91 | 1163261 | Completed | 810552 | Approved/Printed | 2025-12-25 | 2026-06-11 | KOSHI | 21563 | 1 | Al Khor (74 ) | 132 | 132 | 0 |  | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4 | 4 | 2 | 2 | 0 | 0 | 0 |  | 0 | 0 | 11455 | 11455 | Invoiced | Invoiced | 8 | 224 |  |  |  | 2026-02-01 | completed | Invoiced
225 | 241428 | 225 | 2025-11-04 | 2025-11-03 | 2025-11-14 | 2026-02-04 | 2026-09-12 | OL | OL-F9F10-3100 | 302 | 1163350 | Pending | 808895 | Approved/Expired | 2025-12-25 | 2026-05-28 | NEWCON | 3100 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 70 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 3 |  | 2 |  | 0 | 0 | 1 |  | 0 | 0 | 6750 | 0 | Pending | Pending | Pending | 225 |  |  |  |  | Pending | Pending
226 | 241433 | 226 | 2025-11-04 | 2025-11-03 | 2025-11-14 | 2026-02-04 | 2026-09-12 | OL | OL-F7F10-2807 | 302 | 1163366 | Pending | 810568 | Approved/Expired | 2026-01-11 | 2026-06-18 | NEWCON | 2807 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 8 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 2 |  | 2 |  | 0 | 0 | 1 |  | 0 | 0 | 2970 | 0 | Pending | Pending | Pending | 226 |  |  |  |  | Pending | Pending
227 | 241437 | 227 | 2025-11-04 | 2025-11-03 | 2025-11-14 | 2026-02-04 | 2026-09-12 | OL | OL-F9-2797 | 302 | 1163387 | Pending | 810568 | Approved/Expired | 2026-01-11 | 2026-06-18 | NEWCON | 2797 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 63 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 2 |  | 0 | 0 | 1 |  | 0 | 0 | 5680 | 0 | Pending | Pending | Pending | 227 |  |  |  |  | Pending | Pending
228 | 241484 | 228 | 2025-11-04 | 2025-11-03 | 2025-11-14 | 2026-02-04 | 2026-09-12 | OL | OL-F5-36396 | 302 | 1163745 | Cancelled | 810567 | Approved/Printed | 2026-01-04 | 2026-06-18 | AL MORAQUIB | 27531 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 10 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 2 |  | 2 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 3107 | 0 | Cancelled | Cancelled | Cancelled | 228 |  |  |  |  | Cancelled | Cancelled
229 | 241438 | 229 | 2025-11-04 | 2025-11-03 | 2025-11-14 | 2026-02-04 | 2025-12-24 | BP | BP#CE/2025/0242 ( PIN82020447) | 40 | 1163409 | Completed | 808890/ 810940 | Approved/Printed | 2025-12-02 | 2026-05-28 | NEWCON | 37770 | 1 | RAUDAT RASHID (82 ) | 259 | 259 | 40 | 40 | 0 | 0 | 0 |  | 0 | 0 | 40 | 40 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 25965 | 25965 | Invoiced | Invoiced | 6 | 229 |  |  |  | 2025-12-01 | completed | Invoiced
230 | 241439 | 230 | 2025-11-04 | 2025-11-03 | 2025-11-14 | 2026-02-04 | 2026-01-21 | BP | BP149983 | 68 | 1163421 | Completed | 810729 | Approved/Printed | 2025-12-14 | 2026-06-11 | NEWCON | 1543 | 1 | Al Jemailiya (73 ) | 206 | 206 | 0 | 0 | 0 | 0 | 115 | 115 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 19565 | 19565 | Invoiced | Invoiced | 7 | 230 |  |  |  | 2026-01-01 | completed | Invoiced
231 | 241440 | 231 | 2026-03-10 | 2026-03-09 | 2026-03-20 | 2026-05-10 | 2026-04-01 | MOC | IN-114563+93 MOC-242630+31 | 12 | 1163491 | completed | 810946/ 820335 | Approved/Printed | 2026-03-31 | 2026-09-11 | NEWCON | 1894 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 113 | 113 | 0 | 0 | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 4 | 4 | 4 | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 12786 | 12786 | Invoiced | Invoiced | 10 | 231 |  |  |  | 2026-03-31 | completed | Invoiced
232 | 241441 | 232 | 2025-11-04 | 2025-11-03 | 2025-11-14 | 2026-02-04 | 2026-02-18 | BP | BP147611 | 96 | 1163530 | Completed | 810948 | Approved/Printed | 2026-01-07 | 2026-06-25 | NEWCON | 39712 | 1 | Al Kheesa (70 ) | 75 | 75 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 5646 | 5646 | Invoiced | Invoiced | 9 | 232 |  |  |  | 2026-02-01 | completed | Invoiced
233 | 241442 | 233 | 2025-12-28 | 2025-12-27 | 2026-01-07 | 2026-02-04 | 2025-12-29 | MOC | MOC-249766 | 45 | 1163566 | Completed | 810024 | Approved/Printed | 2025-12-17 | 2026-06-04 | NEWCON | 0616 | 1 | Al Doha Al Jadeeda (15 ) | 99 | 99 | 0 | 0 | 0 | 0 | 99 | 99 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 14023 | 14023 | Invoiced | Invoiced | 8 | 233 |  |  |  | 2026-01-01 | completed | Invoiced
234 | 241453 | 234 | 2025-11-04 | 2025-11-03 | 2025-11-14 | 2026-02-04 | 2026-09-12 | BP | BP# N/2025/1909 ( PIN70214024) | 302 | 1163679 | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | AL MORAQUIB | 14054 | 1 | Al Kheesa (70 ) | 65 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 5757 | 0 | Cancelled | Cancelled | Cancelled | 234 |  |  |  |  | Cancelled | Cancelled
235 | 241462 | 235 | 2025-11-04 | 2025-11-03 | 2025-11-14 | 2026-02-04 | 2025-12-31 | BP | BP150515 | 47 | 1163706 | Completed | 810952 | Approved/Printed | 2026-01-11 | 2026-06-25 | NEWCON | 22541 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 45 | 45 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 3350 | 3350 | Invoiced | Invoiced | 6 | 235 |  |  |  | 2025-12-01 | completed | Invoiced
236 | 241465 | 236 | 2025-11-04 | 2025-11-03 | 2025-11-14 | 2026-02-04 | 2025-12-31 | BP | BP150516 | 47 | 1163713 | Completed | 810952 | Approved/Printed | 2026-01-11 | 2026-06-25 | NEWCON | 22541 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 115 | 115 | 0 | 0 | 0 | 0 | 34 | 34 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 9488 | 9488 | Completed | Pending | Pending | 236 |  |  |  | 2025-12-01 | completed | Job Completed With 286
237 | 241468 | 237 | 2025-11-04 | 2025-11-03 | 2025-11-14 | 2026-02-04 | 2026-04-21 | BP | BP150513 | 158 | 1163721 | Completed | 809921 | Approved/Printed | 2025-12-08 | 2026-06-04 | NEWCON | 13471 | 1 | Al Kheesa (70 ) | 290 | 290 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 19820 | 19820 | Invoiced | Invoiced | 10 | 237 |  |  |  | 2026-04-15 | Completed | Invoiced
238 | 241470 | 238 | 2025-11-04 | 2025-11-03 | 2025-11-14 | 2026-02-04 | 2026-06-22 | BP | BP150518 | 220 | 1163723 | Completed | 810949 | Approved/Printed | 2026-01-07 | 2026-06-25 | NEWCON | 39832 | 1 | Al Kheesa (70 ) | 73 | 73 | 0 | 0 | 0 | 0 | 73 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 9231 | 9231 | Invoiced | Invoiced | 13 | 238 |  |  |  | 2026-06-21 | Completed | Invoiced
239 | 241473 | 239 | 2025-11-04 | 2025-11-03 | 2025-11-14 | 2026-02-04 | 2026-06-16 | BP | BP150511 | 214 | 1163727 | Completed | 810948 | Approved/Printed | 2026-01-07 | 2026-06-25 | AL MORAQUIB | 9979 | 1 | Al Kheesa (70 ) | 188 | 188 | 0 | 0 | 32 | 32 | 85 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 19411 | 19411 | Invoiced | Invoiced | 13 | 239 |  |  |  | 2026-06-11 | Completed | Invoiced
240 | 241475 | 240 | 2025-11-04 | 2025-11-03 | 2025-11-14 | 2026-02-04 | 2026-09-12 | BP | BP150543 | 302 | 1163731 | Pending | 810952 | Approved/Expired | 2026-01-11 | 2026-06-25 | NEWCON | 33546 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 4890 | 0 | Pending | Pending | Pending | 240 |  |  |  |  | Pending | Pending
241 | 241493 | 241 | 2025-11-05 | 2025-11-04 | 2025-11-15 | 2025-02-05 | 2026-09-12 | BP | BP# M/2024/503 ( PIN25630008 ) | 301 | 1164032 | Pending | 810025 | Approved/Expired | 2025-12-16 | 2026-06-04 | NEWCON | 1125 | 1 | Al Mansoura/Bin Dirhem (25 ) | 170 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 11480 | 0 | Pending | Pending | Pending | 241 |  |  |  |  | Pending | Pending
242 | 241494 | 242 | 2025-11-05 | 2025-11-04 | 2025-11-15 | 2025-02-05 | 2026-09-12 | BP | BP142508+ BP142524 | 301 | 1164040 | LIVE TDP | Hold | Hold | Pending | Pending | NEWCON | 4785 | 2 | Al Soudan South/Al Aziziya/Al (55 ) | 82 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 0 | 2 |  | 2 |  | 2 |  | 0 | 0 | 2 |  | 0 | 0 | 8634 | 0 | Hold | Pending | Pending | 242 |  |  |  |  | Pending | Pending
243 | 241495 | 243 | 2025-11-05 | 2025-11-04 | 2025-11-15 | 2025-02-05 | 2026-09-12 | BP | BP143732 | 301 | 1164043 | Cancelled | 810026 | RO Cancelled | Cancelled | Cancelled | AL MORAQUIB | 22815 | 1 | Al Wukair (91 ) | 237 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 16077 | 0 | Cancelled | Pending | Pending | 243 |  |  |  |  | Cancelled | Cancelled
244 | 241496 | 244 | 2026-08-27 | 2026-08-26 | 2026-09-06 | 2026-10-27 | 2026-09-12 | MOC | IN-116955 MOC-242502 | 6 | 1164048 | Pending | 803662/ 842942 | Approved/Printed | 2025-12-10 | 2027-03-04 | NEWCON | 5700 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 192 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 12800 | 0 | Pending | Pending | Pending | 244 |  |  |  |  | Pending | Pending
245 | 241497 | 245 | 2025-11-05 | 2025-11-04 | 2025-11-15 | 2025-02-05 | 2025-12-20 | BP | BP147567 | 35 | 1164057 | Completed | 810027 | Approved/Printed | 2025-12-08 | 2026-06-04 | NEWCON | 1241 | 1 | Al Wakra (90 ) | 168 | 168 | 0 | 0 | 0 | 0 | 168 | 168 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 20306 | 20306 | Invoiced | Invoiced | 6 | 245 |  |  |  | 2025-12-01 | Completed | Invoiced
246 | 241498 | 246 | 2025-11-05 | 2025-11-04 | 2025-11-15 | 2025-02-05 | 2026-09-12 | BP | BP147791 + BP147793 | 301 | 1164069 | Cancelled | 808150 | RO Cancelled | Cancelled | Cancelled | AL MORAQUIB | 21342 | 2 | Umm Slal/Al Kharaitiyat (71 ) | 174 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 12467 | 0 | Cancelled | Cancelled | Cancelled | 246 |  |  |  |  | Cancelled | Cancelled
247 | 241499 | 247 | 2025-11-05 | 2025-11-04 | 2025-11-15 | 2025-02-05 | 2026-09-12 | BP | BP#N/2023/5602 ( PIN45090151 ) | 301 | 1164075 | Cancelled | NA | NA | Cancelled | Cancelled | AL MORAQUIB | 18231 | 1 | Al Matar Al Qadeem (45 ) | 55 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 5157 | 0 | Cancelled | Cancelled | Cancelled | 247 |  |  |  |  | Cancelled | Cancelled
248 | 241500 | 248 | 2025-11-05 | 2025-11-04 | 2025-11-15 | 2025-02-05 | 2026-09-12 | BP | BP#N/2023/3528 ( PIN45140344 ) | 301 | 1164077 | Pending | 810028 | Approved/Expired | 2026-02-08 | 2026-07-23 | AL MORAQUIB | 24239 | 1 | Al Matar Al Qadeem (45 ) | 155 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 10580 | 0 | Pending | Pending | Pending | 248 |  |  |  |  | Pending | Pending
249 | 241503 | 249 | 2025-11-05 | 2025-11-04 | 2025-11-15 | 2025-02-05 | 2026-09-12 | BP | BP-N/2024/4224 ( PIN54580246 ) | 301 | 1164085 | Pending | 810731 | Approved/Expired | 2026-01-12 | 2026-06-11 | NEWCON | 5975 | 1 | Fareeq Al Amir/Muraykh/Al Soud(54 ) | 205 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 13580 | 0 | Pending | Pending | Pending | 249 |  |  |  |  | Pending | Pending
250 | 241505 | 250 | 2025-11-05 | 2025-11-04 | 2025-11-15 | 2025-02-05 | 2026-09-12 | BP | BP# N/2023/8074 ( PIN44124023) | 301 | 1164090 | Cancelled | NA | NA | Cancelled | Cancelled | AL MORAQUIB | 2022 | 1 | Al Nuaija (East) (44 ) | 16 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 2817 | 0 | Cancelled | Cancelled | Cancelled | 250 |  |  |  |  | Cancelled | Cancelled
251 | 241536 | 251 | 2025-11-06 | 2025-11-05 | 2025-11-16 | 2025-02-06 | 2026-04-20 | BP | BP# N/2025/3470 ( PIN51933344) | 155 | 1164377 | Completed | 810567 | Approved/Printed | 2026-01-04 | 2026-06-18 | NEWCON | 25782 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 89 | 89 | 0 | 0 | 0 | 0 | 89 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 11103 | 11103 | Invoiced | Invoiced | 11 | 251 |  |  |  | 2026-04-12 | completed | Invoiced
252 | 241539 | 252 | 2026-02-17 | 2026-02-16 | 2026-02-27 | 2026-04-17 | 2026-04-05 | MOC | C-981354 (MSA-18037113) | 37 | 1164462 | Completed | 810028 | Approved/Printed | 2026-02-08 | 2026-07-23 | NEWCON | 38779 | 1 | Al Matar Al Qadeem (45 ) | 175 | 175 | 0 | 0 | 0 | 0 | 125 | 125 | 0 | 0 | 129 | 129 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 41085 | 41085 | Invoiced | Invoiced | 13 | 252 |  |  |  | 2026-03-29 | completed | Invoiced
253 | 241541 | 253 | 2026-01-08 | 2026-01-07 | 2026-01-18 | 2026-03-10 | 2026-03-30 | MOC | IN#113509 MOC#245552 | 71 | 1164470 | Completed | 814022/ 816009/ 818117 | Approved/Printed | 2026-02-03 | 2026-04-30 | NEWCON | 0139 | 1 | Kulaib (35 ) | 235 | 235 | 76 | 76 | 0 | 0 | 141 | 141 | 0 | 0 | 190 | 190 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 61187 | 61187 | Invoiced | Invoiced | 9 | 253 |  |  |  | 2026-02-01 | completed | Invoiced
254 | 241543 | 254 | 2025-11-06 | 2025-11-05 | 2025-11-16 | 2025-02-06 | 2026-09-12 | BP | BP# N/2025/3467 ( PIN25180053) | 300 | 1164526 | Pending | 810025 | Approved/Expired | 2025-12-16 | 2026-06-04 | NEWCON | 21458 | 1 | Al Mansoura/Bin Dirhem (25 ) | 135 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 9380 | 0 | Pending | Pending | Pending | 254 |  |  |  |  | Pending | Pending
255 | 241589 | 255 | 2025-11-09 | 2025-11-08 | 2025-11-19 | 2026-02-08 | 2026-04-08 | OL | OL-F12-0020 | 140 | 1165311 | Completed | 810569 | Approved/Printed | 2026-01-18 | 2026-06-18 | NEWCON | 0020 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 115 | 115 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 15 | 15 | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 14295 | 14295 | Completed | Pending | Pending | 255 |  |  |  | 2026-04-09 | Pending | Pending
256 | 241597 | 256 | 2025-11-09 | 2025-11-08 | 2025-11-19 | 2026-02-08 | 2026-09-12 | OL | OL-F1-27218 | 297 | 1165324 | Pending | 808891 | Approved/Expired | 2025-12-17 | 2026-05-28 | NEWCON | 27218 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 1 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1885 | 0 | Pending | Pending | Pending | 256 |  |  |  |  | Pending | Pending
257 | 241624 | 257 | 2025-11-10 | 2025-11-09 | 2025-11-20 | 2026-02-09 | 2026-09-12 | OL | OL-F4-12064 | 296 | 1165495 | Pending | 808891 | Approved/Expired | 2025-12-17 | 2026-05-28 | NEWCON | 12064 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 110 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 2 |  | 7 |  | 5 |  | 0 | 0 | 1 |  | 0 | 0 | 11870 | 0 | Pending | Pending | Pending | 257 |  |  |  |  | Pending | Pending
258 | 241625 | 258 | 2025-11-10 | 2025-11-09 | 2025-11-20 | 2026-02-09 | 2026-09-12 | OL | OL-F2-10776 | 296 | 1165503 | Pending | 808896 | Approved/Expired | 2025-12-11 | 2026-05-28 | NEWCON | 10776 | 1 | Al Khor (74 ) | 135 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 2 |  | 4 |  | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 11660 | 0 | Pending | Pending | Pending | 258 |  |  |  |  | Pending | Pending
259 | 241630 | 259 | 2025-11-10 | 2025-11-09 | 2025-11-20 | 2026-02-10 | 2025-12-28 | BP | BP150736 | 38 | 1165602 | Completed | 808892 | Approved/Printed | 2025-12-11 | 2026-05-28 | NEWCON | 25830 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 96 | 96 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 7674 | 7674 | Invoiced | Invoiced | 5 | 259 |  |  |  | 2025-12-01 | Completed | Invoiced
260 | 241631 | 260 | 2026-08-31 | 2026-08-30 | 2026-09-10 | 2026-10-31 | 2026-09-12 | MOC+BP | IN-116966 MOC-247154+BP150742 | 2 | 1165623 | Pending | 810568/ 821172/ 832431 | Approved/Printed | 2026-01-11 | 2026-12-25 | NEWCON | 19472 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 100 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 0 | 0 | 0 | 2 |  | 2 |  | 0 | 0 | 1 |  | 0 | 0 | 8070 | 0 | Pending | Pending | Pending | 260 |  |  |  |  | Pending | Pending
261 | 241635 | 261 | 2025-11-10 | 2025-11-09 | 2025-11-20 | 2026-02-10 | 2026-09-12 | BP | BP150710/ MOC-247154 | 296 | 1165665 | Pending | 810568/ 834116 | Approved/Printed | 2026-08-04 | 2027-01-09 | NEWCON | 10814 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 86 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 6440 | 0 | Pending | Pending | Pending | 261 |  |  |  |  | Pending | Pending
262 | 241640 | 262 | 2026-02-08 | 2026-02-07 | 2026-02-18 | 2026-05-08 | 2026-03-26 | OL | OL-F6-17895 | 36 | 1165683 | Completed | 808893 | Approved/Printed | 2025-12-15 | 2026-05-28 | NEWCON | 17895 | 1 | Madinat Khalifa (North) (32 ) | 45 | 45 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 3 | 3 |  | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 8535 | 8535 | Invoiced | Invoiced | 9 | 262 |  |  |  | 2026-03-24 | Completed | Invoiced
263 | 241649 | 263 | 2025-11-10 | 2025-11-09 | 2025-11-20 | 2026-02-09 | 2026-09-12 | OL | OL-F5-F6-4553 | 296 | 1165787 | Pending | 809096 | Approved/Expired | 2026-02-03 | 2026-05-28 | NEWCON | 4553 | 2 | Al Duhail South (31 ) | 155 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 2 |  | 3 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 12375 | 0 | Pending | Pending | Pending | 263 |  |  |  |  | Pending | Pending
264 | 241657 | 264 | 2025-11-10 | 2025-11-09 | 2025-11-20 | 2025-02-10 | 2026-03-02 | BP | BP#115392, PIN#70058040 | 102 | 1165812 | Completed | 810949 | Approved/Printed | 2026-01-07 | 2026-06-25 | NEWCON | 4936 | 1 | Al Kheesa (70 ) | 207 | 207 | 0 | 0 | 0 | 0 | 190 | 190 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 24650 | 24650 | Invoiced | Invoiced | 9 | 264 |  |  |  | 2026-02-01 | completed | Invoiced
265 | 241659 | 265 | 2025-11-11 | 2025-11-10 | 2025-11-21 | 2026-02-10 | 2026-09-12 | OL | OL-TX2&F7-10474 | 295 | 1165913 | Pending | 808896 | Approved/Expired | 2025-12-11 | 2026-05-28 | NEWCON | 16096 | 1 | Al Khor (74 ) | 73 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 2 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5970 | 0 | Pending | Pending | Pending | 265 |  |  |  |  | Pending | Pending
266 | 241662 | 266 | 2025-11-11 | 2025-11-10 | 2025-11-21 | 2026-01-11 | 2026-01-13 | MOC | MOC-230703 | 53 | 1166000 | Completed | 811652 | Approved/Printed | 2025-12-24 | 2026-06-18 | NEWCON | 32745 | 1 | Madinat Khalifa (North) (32 ) | 71 | 71 | 0 | 0 | 0 | 0 | 71 | 71 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 3 | 3 | 4 | 4 | 0 | 0 | 1 | 1 | 0 | 0 | 12117 | 12117 | Invoiced | Invoiced | 8 | 266 |  |  |  | 2026-01-01 | completed | Invoiced
267 | 241694 | 267 | 2025-11-11 | 2025-11-10 | 2025-11-21 | 2026-02-10 | 2026-09-12 | OL | OL-F2-9846 | 295 | 1166136 | Pending | 808896 | Approved/Expired | 2025-12-11 | 2026-05-28 | NEWCON | 9846 | 1 | Al Khor (74 ) | 77 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 6 |  | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8970 | 0 | Pending | Pending | Pending | 267 |  |  |  |  | Pending | Pending
268 | 241713 | 268 | 2025-11-12 | 2025-11-11 | 2025-11-22 | 2026-02-11 | 2026-09-12 | OL | OL F5-20737 | 294 | 1166366 | Pending | 810030 | Approved/Expired | 2025-12-24 | 2026-06-04 | NEWCON | 20737 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 150 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 4 |  | 3 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 12420 | 0 | Pending | Pending | Pending | 268 |  |  |  |  | Pending | Pending
269 | 241719 | 269 | 2025-11-12 | 2025-11-11 | 2025-11-22 | 2026-02-11 | 2025-12-30 | MOC | MOC-247449 | 38 | 1166531 | Completed | 809123 | Approved/Printed | 2025-12-01 | 2026-05-28 | NEWCON | 11699 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 101 | 101 | 0 | 0 | 0 | 0 | 55 | 55 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 7 | 7 | 7 | 7 | 4 | 4 | 0 | 0 | 1 | 1 | 0 | 0 | 17295 | 17295 | Invoiced | Invoiced | 7 | 269 |  |  |  | 2025-12-01 | Completed | Invoiced
270 | 241743 | 270 | 2025-11-12 | 2025-11-11 | 2025-11-22 | 2026-02-11 | 2026-01-28 | OL | OL-F7-12925 | 67 | 1166627 | Completed | 808891 | Approved/Printed | 2025-12-17 | 2026-05-28 | NEWCON | 24895 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 18 | 18 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 3 | 3 | 0 |  | 0 |  | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4002 | 4002 | Invoiced | Invoiced | 6 | 270 |  |  |  | 2026-01-01 | Completed | Invoiced
271 | 241760 | 271 | 2026-02-05 | 2026-02-04 | 2026-02-15 | 2026-05-05 | 2026-04-27 | OL | OL F3-3440 | 71 | 1166791 | Completed | 808893/ 818118 | Approved/Printed | 2026-03-24 | 2026-05-02 | NEWCON | 3440 | 1 | Madinat Khalifa (North) (32 ) | 44 | 44 | 32 | 32 | 0 | 0 | 44 | 44 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 15188 | 15188 | Invoiced | Invoiced | 10 | 271 |  |  |  | 2026-04-23 | completed | Invoiced
272 | 241762 | 272 | 2025-11-12 | 2025-11-11 | 2025-11-22 | 2026-02-12 | 2026-03-30 | BP | BP#150948 + BP#150949 | 128 | 1166797 | Completed | 810031/ 818119 | Approved/Printed | 2026-03-02 | 2026-08-27 | KAR | 10632 | 2 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 158 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 10170 | 10170 | Invoiced | Invoiced | 10 | 272 |  |  |  | 2026-03-24 | Completed | Invoiced
273 | 241763 | 273 | 2025-11-12 | 2025-11-11 | 2025-11-22 | 2026-02-12 | 2025-12-30 | BP | BP151022 | 38 | 1166798 | Completed | 808892 | Approved/Printed | 2025-12-11 | 2026-05-28 | NEWCON | 18502 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 9 | 9 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2682 | 2682 | Invoiced | Invoiced | 5 | 273 |  |  |  | 2025-12-01 | Completed | Invoiced
274 | 241766 | 274 | 2025-11-13 | 2025-11-12 | 2025-11-23 | 2026-02-12 | 2026-09-12 | OL | OL-F1-12220+OLTX2-24949 | 293 | 1166975 | Completed | 808896 | Approved/Printed | 2025-12-11 | 2026-05-28 | NEWCON | 24949 | 1 | Al Khor (74 ) | 70 | 70 |  |  | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 2 | 2 | 6 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 9855 | 9855 | Invoiced | Invoiced | 6 | 274 |  |  |  | 2026-01-01 | completed | Invoiced
275 | 241797 | 275 | 2025-11-13 | 2025-11-12 | 2025-11-23 | 2026-02-12 | 2026-09-12 | OL | OL-F9-0136 | 293 | 1167110 | Pending | 809124 | Approved/Expired | 2025-12-11 | 2026-05-28 | NEWCON | 0136 | 1 | Madinat Khalifa (South) (34 ) | 26 | 26 | 0 | 0 | 0 | 0 | 26 | 26 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4592 | 4592 | Pending | Pending | Pending | 275 |  |  |  |  | Pending | Pending
276 | 241798 | 276 | 2025-11-13 | 2025-11-12 | 2025-11-23 | 2026-02-12 | 2026-01-21 | OL | OL-F12-39403 | 59 | 1167128 | Completed | 810030 | Approved/Printed | 2025-12-24 | 2026-06-04 | NEWCON | 39403 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 0 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1445 | 1445 | Invoiced | Invoiced | 6 | 276 |  |  |  | 2026-01-01 | Completed | Invoiced
277 | 241800 | 277 | 2025-11-13 | 2025-11-12 | 2025-11-23 | 2025-01-13 | 2026-01-08 | MOC | MOC-239840 | -314 | 1167246 | Completed | 809125 | Approved/Printed | 2025-12-15 | 2026-05-28 | NEWCON | 25859 | 1 | Al Khor (74 ) | 42 | 42 | 0 | 0 | 0 | 0 | 42 | 42 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 6064 | 6064 | Invoiced | Invoiced | 6 | 277 |  |  |  | 2026-01-01 | completed | Invoiced
278 | 241801 | 278 | 2026-04-09 | 2026-04-08 | 2026-04-19 | 2026-07-09 | 2026-09-12 | OL | OL F4-4489 | 81 | 1167286 | Pending | 809096 | Approved/Expired | 2026-02-03 | 2026-05-28 | NEWCON | 4492 | 1 | Al Duhail South (31 ) | 320 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 4 |  | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 22800 | 0 | Pending | Pending | Pending | 278 |  |  |  |  | Pending | Pending
279 | 241804 | 279 | 2025-11-13 | 2025-11-12 | 2025-11-23 | 2026-02-13 | 2026-01-04 | BP | BP151094 | 82 | 1167351 | Completed | 808892 | Approved/Printed | 2025-12-11 | 2026-05-28 | NEWCON | 25158 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 38 | 38 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 0 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2715 | 2715 | Invoiced | Invoiced | 7 | 279 |  |  |  | 2026-01-01 | completed | Invoiced
280 | 241805 | 280 | 2025-11-13 | 2025-11-12 | 2025-11-23 | 2026-02-13 | 2026-02-26 | BP | BP# N/2025/3142 ( PIN30090162) | 82 | 1167352 | Completed | 809126 | Approved/Printed | 2025-12-22 | 2026-05-28 | NEWCON | 9563 | 1 | Al Duhail (30 ) | 84 | 84 | 0 | 0 | 0 | 0 | 84 | 84 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 | 1 | 1 | 1 |  |  | 0 | 0 |  |  | 0 | 0 | 10478 | 10478 | Invoiced | Invoiced | 11 | 280 |  |  |  | 2026-02-01 | completed | Invoiced
281 | 241806 | 281 | 2025-11-16 | 2025-11-15 | 2025-11-26 | 2026-02-15 | 2026-01-12 | OL | OL-F11-12832 | 81 | 1167681 | Completed | 810030 | Approved/Printed | 2025-12-24 | 2026-06-04 | NEWCON | 38086 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 5 | 5 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 950 | Invoiced | Invoiced | 7 | 281 |  |  |  | 2026-01-01 | Completed | Invoiced
282 | 241841 | 282 | 2025-11-16 | 2025-11-15 | 2025-11-26 | 2026-02-15 | 2026-05-25 | OL | OL F3-4478 | 81 | 1168251 | Completed | 809096 | Approved/Printed | 2026-02-03 | 2026-05-28 | SMART ELEVATION | 4540 | 1 | Al Duhail South (31 ) | 89 | 89 | 0 | 0 | 0 | 0 | 85 | 85 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 11825 | 11825 | Invoiced | Invoiced | 12 | 282 |  |  |  | 2026-05-20 | completed | Invoiced
283 | 241846 | 283 | 2025-11-17 | 2025-11-16 | 2025-11-27 | 2026-02-16 | 2026-09-12 | OL | OL F2-4529 | 81 | 1168413 | Pending | 809096 | Approved/Expired | 2026-02-03 | 2026-05-28 | NEWCON | 4529 | 1 | Al Duhail South (31 ) | 141 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 2 |  | 3 |  | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 12165 | 0 | Pending | Pending | Pending | 283 |  |  |  |  | Pending | Pending
284 | 241850 | 284 | 2025-11-17 | 2025-11-16 | 2025-11-27 | 2026-01-17 | 2026-01-11 | MOC | MOC-248898 | 51 | 1168665 | Completed | 809353 | Approved/Printed | 2025-12-21 | 2026-05-28 | NEWCON | 4324 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 25 | 25 | 0 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 |  | 2 | 2 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 5625 | 5625 | Invoiced | Invoiced | 6 | 284 |  |  |  | 2026-01-01 | Completed | Invoiced
285 | 241851 | 285 | 2025-12-22 | 2025-12-21 | 2026-01-01 | 2026-02-21 | 2026-01-11 | MOC | MOC-249291+249668 | 51 | 1168692 | Completed | 809353 | Approved/Printed | 2025-12-21 | 2026-05-28 | NEWCON | 13634 | 2 | Umm Slal/Al Kharaitiyat (71 ) | 80 | 80 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 |  | 1 | 1 | 3 | 3 | 0 | 0 | 2 | 2 | 0 | 0 | 7790 | 7790 | Invoiced | Invoiced | 6 | 285 |  |  |  | 2026-01-01 | completed | Invoiced
286 | 241899 | 286 | 2025-11-17 | 2025-11-16 | 2025-11-27 | 2026-02-17 | 2025-12-31 | BP | BP151125 | 82 | 1168842 | Completed | 809354 | Approved/Printed | 2025-12-11 | 2026-05-28 | NEWCON | 22541 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 168 | 168 | 0 | 0 | 0 | 0 | 54 | 54 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 4 | 4 | 3 | 3 | 0 | 0 | 2 | 2 | 0 | 0 | 16918 | 16918 | Invoiced | Invoiced | 7 | 286 |  |  |  | 2025-12-01 | Completed | Invoiced
287 | 241909 | 287 | 2025-11-18 | 2025-11-17 | 2025-11-28 | 2026-02-18 | 2026-09-12 | BP | BP # N/2025/643 ( PIN35080087) | 82 | 1169156 | Pending | 837394 | Approved/Printed | 2026-08-23 | 2027-02-04 | NEWCON | 30523 | 1 | Kulaib (35 ) | 251 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 16917 | 0 | Pending | Pending | Pending | 287 |  |  |  |  | Pending | Pending
288 | 241924 | 288 | 2025-11-18 | 2025-11-17 | 2025-11-28 | 2026-02-18 | 2025-12-30 | BP | BP# N/2025/5352( PIN51770061) | 82 | 1169214 | Completed | 810031 | Approved/Printed | 2025-12-11 | 2026-06-04 | NEWCON | 18332 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 40 | 40 | 0 | 0 | 0 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 5216 | 5216 | Invoiced | Invoiced | 7 | 288 |  |  |  | 2025-12-01 | Completed | Invoiced
289 | 241937 | 289 | 2025-11-18 | 2025-11-17 | 2025-11-28 | 2026-02-18 | 2026-09-12 | BP | BP-N/2025/2662 ( PIN37330062 ) | 82 | 1169236 | Pending | 811741 | Approved/Expired | 2026-01-08 | 2026-06-25 | NEWCON | 13668 | 1 | Bin Omran/Al Hitmi Al Jadeed (37 ) | 61 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 4940 | 0 | Pending | Pending | Pending | 289 |  |  |  |  | Pending | Pending
290 | 241940 | 290 | 2025-11-18 | 2025-11-17 | 2025-11-28 | 2026-02-17 | 2026-09-12 | OL | OL-F2-0022 | 81 | 1169240 | Pending | 810030 | Approved/Expired | 2025-12-24 | 2026-06-04 | NEWCON | 0022 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 80 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6330 | 0 | Pending | Pending | Pending | 290 |  |  |  |  | Pending | Pending
291 | 241951 | 291 | 2026-03-24 | 2026-03-23 | 2026-04-03 | 2026-06-22 | 2026-09-12 | OL | OL F4 F5-0203 | 80 | 1169276 | Pending | 814351 | Approved/Expired | 2026-02-19 | 2026-07-23 | NEWCON | 1903 | 1 | Kulaib (35 ) | 90 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6930 | 0 | Pending | Pending | Pending | 291 |  |  |  |  | Pending | Pending
292 | 241960 | 292 | 2025-11-19 | 2025-11-18 | 2025-11-29 | 2026-02-19 | 2026-01-03 | BP | BP151248 | 82 | 1169516 | Completed | 810031 | Approved/Printed | 2025-12-11 | 2026-06-04 | NEWCON | 20645 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 88 | 88 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2 | 2 | 1 | 1 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 6520 | 6520 | Invoiced | Invoiced | 6 | 292 |  |  |  | 2026-01-01 | Completed | Invoiced
293 | 241983 | 293 | 2025-11-19 | 2025-11-18 | 2025-11-29 | 2026-02-19 | 2026-04-13 | BP | BP151348 | 82 | 1169604 | Completed | 816323 | Approved/Printed | 2026-02-19 | 2026-08-13 | NEWCON | 19411 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 63 | 63 | 0 | 0 | 0 | 0 | 63 | 63 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 9801 | 9801 | Invoiced | Invoiced | 10 | 293 |  |  |  | 2026-04-09 | Completed | Invoiced
294 | 242002 | 294 | 2025-11-20 | 2025-11-19 | 2025-11-30 | 2026-01-20 | 2026-09-12 | MOC | C-981337; MSA-18034679 | 51 | 1170066 | Returned | 810033 | Approved/Printed | 2025-12-10 | 2026-06-04 | NEWCON | 23295 | 1 | Al Duhail South (31 ) | 20 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 3000 | 0 | Pending | Pending | Pending | 294 |  |  |  |  | Pending | Pending
295 | 242051 | 295 | 2025-11-23 | 2025-11-22 | 2025-12-03 | 2026-02-23 | 2026-04-02 | BP | BP144549 | 82 | 1170952 | Completed | 810952/ 816110 | Approved/Printed | 2026-01-11 | 2026-06-25 | NEWCON | 20942 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 40 | 40 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 11850 | 11850 | Invoiced | Invoiced | 10 | 295 |  |  |  | 2026-03-26 | Completed | Invoiced
296 | 242117 | 296 | 2025-11-24 | 2025-11-23 | 2025-12-04 | 2026-02-24 | 2026-03-12 | BP | BP-151421+BP-151685 | 82 | 1171621 | Completed | 810952 | Approved/Printed | 2026-01-11 | 2026-06-25 | NEWCON | 40779 | 2 | Umm Slal/Al Kharaitiyat (71 ) | 295 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18940 | 18940 | Invoiced | Invoiced | 10 | 296 |  |  |  | 2026-02-01 | completed | Invoiced
297 | 242171 | 297 | 2025-11-24 | 2025-11-23 | 2025-12-04 | 2026-02-24 | 2026-09-12 | BP | BP151513 | 82 | 1171830 | Cancelled | NA | NA | Cancelled | Cancelled | AL MORAQUIB | 19054 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 11150 | 0 | Cancelled | Cancelled | Cancelled | 297 |  |  |  |  | Cancelled | Cancelled
298 | 242173 | 298 | 2025-11-24 | 2025-11-23 | 2025-12-04 | 2026-02-24 | 2026-03-10 | BP | BP149778 | 82 | 1171833 | Completed | 810949 | Approved/Printed | 2026-01-07 | 2026-06-25 | NEWCON | 18886 | 1 | Al Kheesa (70 ) | 172 | 172 | 0 | 0 | 0 | 0 | 172 | 172 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 1 | 1 | 1 | 1 | 0 | 0 |  |  | 0 | 0 | 20814 | 20814 | Invoiced | Invoiced | 9 | 298 |  |  |  | 2026-03-04 | Completed | Invoiced
299 | 242197 | 299 | 2025-11-25 | 2025-11-24 | 2025-12-05 | 2026-02-25 | 2026-09-12 | BP | BP151711 | 82 | 1172171 | Pending | 810564 | Approved/Expired | 2025-12-14 | 2026-06-11 | NEWCON | 4866 | 1 | Al Duhail South (31 ) | 293 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 18860 | 0 | Pending | Pending | Pending | 299 |  |  |  |  | Pending | Pending
300 | 242199 | 300 | 2025-11-25 | 2025-11-24 | 2025-12-05 | 2026-02-25 | 2026-01-24 | BP | BP151776 | 82 | 1172173 | Completed | 810950 | Approved/Printed | 2025-12-30 | 2026-06-25 | NEWCON | 21258 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 93 | 93 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 6230 | 6230 | Invoiced | Invoiced | 7 | 300 |  |  |  | 2026-01-01 | Completed | Invoiced
301 | 242229 | 301 | 2025-11-26 | 2025-11-25 | 2025-12-06 | 2026-02-26 | 2026-06-20 | BP | BP # N/2025/1554( PIN71288079) | 82 | 1172453 | Cancelled | 810953 | Approved/Printed | 2026-01-12 | 2026-06-25 | NEWCON | 9887 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | Cancelled | Cancelled | Cancelled | 301 |  |  |  |  | Cancelled | Job Completed With 566
302 | 242230 | 302 | 2025-11-26 | 2025-11-25 | 2025-12-06 | 2026-02-26 | 2026-06-15 | BP | BP150486 | 82 | 1172486 | Completed | 810953/ 816110 | Approved/Printed | 2026-01-12 | 2026-06-25 | NEWCON | 27260 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 86 | 86 | 36 | 36 | 0 | 0 | 23 | 23 | 30 | 30 | 45 | 45 | 0 | 0 | 0 | 0 | 4 | 4 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 21746 | 21746 | Invoiced | Invoiced | 13 | 302 |  |  |  | 2026-06-11 | completed | Invoiced
303 | 242247 | 303 | 2026-02-24 | 2026-02-23 | 2026-03-06 | 2026-04-24 | 2026-03-11 | MOC | IN-114611 MOC-248548+49 | 49 | 1172659 | Completed | 810568 | Approved/Printed | 2026-01-11 | 2026-06-18 | NEWCON | 22043 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 13200 | 13200 | Invoiced | Invoiced | 8 | 303 |  |  |  | 2026-03-04 | Completed | Invoiced
304 | 242248 | 304 | 2026-05-06 | 2026-05-05 | 2026-05-16 | 2026-07-06 | 2026-06-09 | MOC | C-141566 MSA-18036794 | 51 | 1172660 | Completed | 811736 | Approved/Printed | 2026-01-13 | 2026-06-25 | NEWCON | 30390 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 151 | 151 | 0 | 0 | 0 | 0 | 148 | 148 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 19296 | 19296 | Invoiced | Invoiced | 12 | 304 |  |  |  | 2026-04-06 | Completed | Invoiced
305 | 242262 | 305 | 2026-02-15 | 2026-02-14 | 2026-02-25 | 2026-04-15 | 2026-05-13 | MOC+OL | C-972211+OLF4F110081 | 49 | 1172806 | Completed | 818743/ 826407 | Approved/Printed | 2026-03-10 | 2026-06-20 | Smart Elevation | 0081 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 252 | 252 | 68 | 68 | 0 | 0 | 73 | 73 | 0 | 0 | 85 | 85 | 2 | 2 | 0 | 0 | 2 | 2 | 7 | 7 | 7 | 7 | 0 | 0 | 1 | 1 | 0 | 0 | 44596 | 44596 | Invoiced | Invoiced | 12 | 305 |  |  |  | 2026-04-23 | Completed | Invoiced
306 | 242263 | 306 | 2025-11-26 | 2025-11-25 | 2025-12-06 | 2026-02-26 | 2026-09-12 | BP | BP151913 | 82 | 1172807 | Completed | 811737 | Approved/Printed | 2025-12-25 | 2026-06-25 | NEWCON | 9986 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1912 | 1912 | Invoiced | Invoiced | 6 | 306 |  |  |  | 2026-01-01 | Completed | Invoiced
307 | 242264 | 307 | 2025-11-26 | 2025-11-25 | 2025-12-06 | 2026-02-26 | 2026-02-15 | BP | BP151914 | 82 | 1172808 | Completed | 810567 | Approved/Printed | 2026-01-04 | 2026-06-18 | NEWCON | 26579 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 110 | 110 | 0 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 9000 | 9000 | Invoiced | Invoiced | 7 | 307 |  |  |  | 2026-02-01 | Completed | Invoiced
308 | 242265 | 308 | 2025-11-26 | 2025-11-25 | 2025-12-06 | 2026-02-26 | 2026-02-08 | BP | BP152003 | 82 | 1172810 | Completed | 810950 | Approved/Printed | 2025-12-30 | 2026-06-25 | NEWCON | 22541 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 122 | 122 | 0 | 0 |  | 0 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 10792 | 10792 | Invoiced | Invoiced | 9 | 308 |  |  |  | 2026-02-01 | Completed | Invoiced
309 | 242266 | 309 | 2025-11-26 | 2025-11-25 | 2025-12-06 | 2026-02-26 | 2026-09-12 | BP | BP151864 | 82 | 1172811 | Pending | 810953 | Approved/Expired | 2026-01-12 | 2026-06-25 | NEWCON | 2660 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 65 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 5180 | 0 | Pending | Pending | Pending | 309 |  |  |  |  | Pending | Pending
310 | 242267 | 310 | 2025-11-26 | 2025-11-25 | 2025-12-06 | 2026-02-26 | 2026-09-12 | BP | BP151912 | 82 | 1172812 | Pending | 810950 | Approved/Expired | 2025-12-30 | 2026-06-25 | NEWCON | 23272 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 59 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 4820 | 0 | Pending | Pending | Pending | 310 |  |  |  |  | Pending | Pending
311 | 242346 | 311 | 2025-11-30 | 2025-11-29 | 2025-12-10 | 2026-01-30 | 2026-01-24 | MOC | MOC-234792 | 51 | 1174116 | Completed | 814667 | Approved/Printed | 2026-01-15 | 2026-01-30 | NEWCON | 14071 | 1 | Al Kheesa (70 ) | 31 | 31 | 0 | 0 | 0 | 0 | 31 | 31 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 4777 | 4777 | Invoiced | Invoiced | 6 | 311 |  |  |  | 2026-01-01 | Completed | Invoiced
312 | 242360 | 312 | 2026-07-07 | 2026-07-06 | 2026-07-17 | 2026-09-07 | 2026-07-19 | MOC | IN-116291 MOC-249038 | 52 | 1174236 | Completed | 810565/ 835043 | Approved/Printed | 2025-12-24 | 2026-07-13 | NEWCON | 0146 | 1 | Madinat Khalifa (South) (34 ) | 35 | 35 | 0 | 0 | 0 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 5895 | 5895 | Invoiced | Invoiced | 13 | 312 |  |  |  | 2026-07-19 | Completed | Invoiced
313 | 242383 | 313 | 2025-12-01 | 2025-11-30 | 2025-12-11 | 2026-03-02 | 2026-09-12 | OL | OL-TX1F2F5-1322 | 81 | 1174365 | Pending | 810557 | Approved/Expired | 2025-12-25 | 2026-06-11 | NEWCON | 1322 | 1 | Al Khor (74 ) | 82 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 2 |  | 11 |  | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 12050 | 0 | Pending | Pending | Pending | 313 |  |  |  |  | Pending | Pending
314 | 242382 | 314 | 2025-12-01 | 2025-11-30 | 2025-12-11 | 2026-03-02 | 2026-06-08 | OL | OL-F8F9-12464 | 81 | 1174371 | Completed | 810557 | Approved/Printed | 2025-12-25 | 2026-06-11 | NEWCON | 12464 | 1 | Al Khor (74 ) | 52 | 52 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 3 | 3 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 7298 | 7298 | Invoiced | Invoiced | 12 | 314 |  |  |  | 2026-06-03 | completed | Invoiced
315 | 242385 | 315 | 2025-12-01 | 2025-11-30 | 2025-12-11 | 2026-03-01 | 2026-06-07 | OL | OL-F11-11416 | 80 | 1174374 | Completed | 810553 | Approved/Printed | 2025-12-25 | 2026-06-11 | NEWCON | 11416 | 1 | Al Khor (74 ) | 57 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4660 | 4660 | Invoiced | Invoiced | 12 | 315 |  |  |  | 2026-06-02 | completed | Invoiced
316 | 242445 | 316 | 2025-12-01 | 2025-11-30 | 2025-12-11 | 2026-03-01 | 2026-09-12 | OL | OL-F11-11177 | 80 | 1174458 | Not Clear | Hold | Hold | Pending | Pending | NEWCON | 23428 | 1 | Al Kheesa (70 ) | 101 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 2 |  | 2 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8240 | 0 | Hold | Pending | Pending | 316 |  |  |  |  | Pending | Pending
317 | 242446 | 317 | 2025-12-01 | 2025-11-30 | 2025-12-11 | 2026-03-01 | 2026-06-11 | OL | OL-F6-36809 | 80 | 1174462 | Completed | 810943 | Approved/Printed | 2025-12-30 | 2026-06-25 | NEWCON | 36809 | 1 | Al Kheesa (70 ) | 14 | 14 | 0 |  | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3018 | 3018 | Invoiced | Invoiced | 13 | 317 |  |  |  | 2026-06-14 | Completed | Invoiced
318 | 242453 | 318 | 2025-12-01 | 2025-11-30 | 2025-12-11 | 2026-03-01 | 2026-01-28 | OL | OL-F2-13524 | 80 | 1174466 | Completed | 810944 | Approved/Printed | 2025-12-23 | 2026-06-25 | KAR | 13524 | 1 | Al Kheesa (70 ) | 121 | 121 | 0 |  | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 11135 | 11135 | Invoiced | Invoiced | 7 | 318 |  |  |  | 2026-01-01 | Completed | Invoiced
319 | 242388 | 319 | 2025-12-01 | 2025-11-30 | 2025-12-11 | 2026-03-01 | 2026-03-25 | BP | BP152035 | 80 | 1174376 | Completed | 811084 | Approved/Printed | 2026-01-18 | 2026-06-25 | NEWCON | 12863 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 120 | 120 | 0 | 0 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 14730 | 14730 | Invoiced | Invoiced | 10 | 319 |  |  |  | 2026-03-12 | Completed | Invoiced
320 | 242486 | 320 | 2025-12-01 | 2025-11-30 | 2025-12-11 | 2026-03-01 | 2026-09-12 | OL | OL-F7-13432 | 80 | 1174522 | Completed | 810945 | Approved/Printed | 2025-12-29 | 2026-06-25 | NEWCON | 13432 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 44 | 44 | 0 |  | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 5216 | 5216 | Invoiced | Invoiced | 6 | 320 |  |  |  | 2026-01-01 | Completed | Invoiced
321 | 242487 | 321 | 2025-12-01 | 2025-11-30 | 2025-12-11 | 2026-03-01 | 2026-09-12 | OL | OL-F5F6-13427 | 80 | 1174522 | Pending | 810946 | Approved/Expired | 2025-12-23 | 2026-06-25 | NEWCON | 26012 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 70 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 2 |  | 4 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7130 | 0 | Pending | Pending | Pending | 321 |  |  |  |  | Pending | Pending
322 | 242488 | 322 | 2025-12-01 | 2025-11-30 | 2025-12-11 | 2026-03-01 | 2026-06-16 | OL | OL-F7-F9-3942 | 80 | 1174525 | Completed | 810947 | Approved/Printed | 2025-12-31 | 2026-06-25 | SMART ELEVATION | 3942 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 138 | 138 | 0 | 0 | 0 | 0 | 133 | 133 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 18651 | 18651 | Invoiced | Invoiced | 12 | 322 |  |  |  | 2026-06-10 | Completed | Invoiced
323 | 242551 | 323 | 2025-12-02 | 2025-12-01 | 2025-12-12 | 2026-03-02 | 2026-09-12 | BP | BP152044 | 80 | 1175097 | Pending | 811737/ 834721 | Approved/Printed | 2026-08-04 | 2027-01-09 | NEWCON | 10374 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 190 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 12680 | 0 | Pending | Pending | Pending | 323 |  |  |  |  | Pending | Pending
324 | 242552 | 324 | 2025-12-02 | 2025-12-01 | 2025-12-12 | 2026-03-02 | 2026-02-26 | BP | BP150992 | 80 | 1175099 | Completed | 810950 | Approved/Printed | 2025-12-30 | 2026-06-25 | AL MORAQUIB | 24958 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 131 | 131 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 8510 | 8510 | Invoiced | Invoiced | 7 | 324 |  |  |  | 2026-02-01 | completed | Invoiced
325 | 242554 | 325 | 2025-12-03 | 2025-12-02 | 2025-12-13 | 2026-03-03 | 2026-09-12 | OL | OL-F2-13481 | 80 | 1175203 | Pending | 810948 | Approved/Expired | 2026-01-07 | 2026-06-25 | NEWCON | 13481 | 1 | Al Kheesa (70 ) | 99 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 2 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8160 | 0 | Pending | Pending | Pending | 325 |  |  |  |  | Pending | Pending
326 | 242555 | 326 | 2025-12-03 | 2025-12-02 | 2025-12-13 | 2026-03-03 | 2026-09-12 | OL | OL TX1F1F3-19001 | 80 | 1175208 | Pending | 810949 | Approved/Expired | 2026-01-07 | 2026-06-25 | NEWCON | 19001 | 1 | Al Kheesa (70 ) | 108 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 2 |  | 4 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 9410 | 0 | Pending | Pending | Pending | 326 |  |  |  |  | Pending | Pending
327 | 242563 | 327 | 2025-12-03 | 2025-12-02 | 2025-12-13 | 2026-03-03 | 2026-06-18 | OL | OL-F8-4155 | 80 | 1175378 | Completed | 810951 | Approved/Printed | 2026-01-12 | 2026-06-25 | NEWCON | 4155 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 25 | 25 | 0 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4955 | 4955 | Invoiced | Invoiced | 12 | 327 |  |  |  | 2026-06-14 | completed | Invoiced
328 | 242566 | 328 | 2025-12-03 | 2025-12-02 | 2025-12-13 | 2026-03-03 | 2026-06-18 | OL | OL-F4-3512 | 80 | 1175390 | Completed | 810951 | Approved/Printed | 2026-01-12 | 2026-06-25 | NEWCON | 3512 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 40 | 40 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 |  | 0 | 0 | 0 | 0 | 0 | 6230 | 6230 | Invoiced | Invoiced | 12 | 328 |  |  |  | 2026-06-17 | completed | Invoiced
329 | 242560 | 329 | 2025-12-03 | 2025-12-02 | 2025-12-13 | 2026-03-03 | 2026-02-05 | OL | OL-F5-26106 | 80 | 1175373 | Completed | 810950 | Approved/Printed | 2025-12-30 | 2026-06-25 | NEWCON | 18964 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 6 | 6 | 0 |  | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1888 | 1888 | Invoiced | Invoiced | 7 | 329 |  |  |  | 2026-02-01 | completed | Invoiced
330 | 242596 | 330 | 2025-12-03 | 2025-12-02 | 2025-12-13 | 2026-03-03 | 2026-06-22 | OL | OL-F9F10-4707 | 80 | 1175484 | Completed | 810951 | Approved/Printed | 2026-01-12 | 2026-06-25 | NEWCON | 4707 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 50 | 50 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 7702 | 7702 | Invoiced | Invoiced | 13 | 330 |  |  |  | 2026-06-22 | Completed | Invoiced
331 | 242597 | 331 | 2025-12-03 | 2025-12-02 | 2025-12-13 | 2026-03-03 | 2026-09-12 | OL | OL-F3-20611 | 80 | 1175490 | Pending | 810952 | Approved/Expired | 2026-01-11 | 2026-06-25 | NEWCON | 20611 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 60 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 3 |  | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6510 | 0 | Pending | Pending | Pending | 331 |  |  |  |  | Pending | Pending
332 | 242600 | 332 | 2025-12-03 | 2025-12-02 | 2025-12-13 | 2026-03-03 | 2026-09-12 | OL | OL-F1F8F11-2658 | 80 | 1175497 | Pending | 810953 | Approved/Expired | 2026-01-12 | 2026-06-25 | NEWCON | 2658 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 82 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 7 |  | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 9330 | 0 | Pending | Pending | Pending | 332 |  |  |  |  | Pending | Pending
333 | 242601 | 333 | 2025-12-03 | 2025-12-02 | 2025-12-13 | 2026-03-03 | 2026-09-12 | OL | OL-F3-3638 | 80 | 1175504 | Pending | 810953 | Approved/Expired | 2026-01-12 | 2026-06-25 | NEWCON | 4530 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 55 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 2 |  | 2 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5480 | 0 | Pending | Pending | Pending | 333 |  |  |  |  | Pending | Pending
334 | 242621 | 334 | 2025-12-04 | 2025-12-03 | 2025-12-14 | 2025-12-14 | 2025-12-16 | MOC | C-122539 MSA-18036886 | 2 | 1175767 | Completed | 806346 | Approved/Printed | 2025-11-09 | 2026-04-23 | NEWCON | 10017 | 1 | Industrial Area (57 ) | 10 | 10 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 0 |  | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1750 | 1750 | Invoiced | Invoiced | 7 | 334 |  |  |  | 2025-12-01 | Completed | Invoiced
335 | 242624 | 335 | 2025-12-04 | 2025-12-03 | 2025-12-14 | 2026-02-03 | 2025-12-29 | MOC | MOC-215027 | 51 | 1175776 | Completed | 810941 | Approved/Printed | 2025-12-17 | 2026-06-11 | NEWCON | 13309 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 30 | 30 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 4284 | 4284 | Invoiced | Invoiced | 6 | 335 |  |  |  | 2025-12-01 | Completed | Invoiced
336 | 242685 | 336 | 2026-02-18 | 2026-02-17 | 2026-02-28 | 2026-05-19 | 2026-08-16 | OL | OL-F1F4-24512 | 80 | 1176555 | Completed | 818860 | Approved/Printed | 2026-03-15 | 2026-09-11 | AL MORAQUIB | 24512 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 159 | 159 | 0 | 0 | 0 | 0 | 120 | 120 | 22 | 22 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 21090 | 21090 | Completed | Pending | Pending | 336 |  |  |  | 2026-08-10 | Pending | Pending
337 | 242784 | 337 | 2025-12-08 | 2025-12-07 | 2025-12-18 | 2026-03-08 | 2026-06-17 | BP | BP152099 | 80 | 1177256 | Completed | 809907 | Approved/Printed | 2026-01-12 | 2026-06-25 | BD Dhaka | 37182 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 190 | 190 | 0 | 0 | 0 | 0 | 190 | 190 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 24070 | 24070 | Invoiced | Invoiced | 12 | 337 |  |  |  | 2026-06-10 | Completed | Invoiced
338 | 242789 | 338 | 2025-12-08 | 2025-12-07 | 2025-12-18 | 2026-03-08 | 2026-04-19 | BP | BP152222 | 80 | 1177262 | Completed | 810730 | Approved/Printed | 2026-01-07 | 2026-06-25 | NEWCON | 5830 | 1 | New District Of Doha 64 (64 ) | 30 | 30 | 0 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 5465 | 5465 | Invoiced | Invoiced | 11 | 338 |  |  |  | 2026-04-16 | Completed | Invoiced
339 | 242838 | 339 | 2025-12-08 | 2025-12-07 | 2025-12-18 | 2026-02-08 | 2026-01-12 | MOC | MOC-249507 | 52 | 1177400 | Completed | 809904 | Approved/Printed | 2025-12-21 | 2026-06-18 | NEWCON | 15165 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 126 | 126 | 0 | 0 | 0 | 0 | 73 | 73 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 13561 | 13561 | Invoiced | Invoiced | 6 | 339 |  |  |  | 2026-01-01 | Completed | Invoiced
340 | 242839 | 340 | 2025-12-08 | 2025-12-07 | 2025-12-18 | 2026-02-08 | 2026-09-12 | MOC | C-1494733 ( MSA-18035896 ) | 52 | 1177402 | Completed | 809905 | Approved/Printed | 2025-12-31 | 2026-06-18 | NEWCON | 25793 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 544 | 544 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 3 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 35620 | 35620 | Invoiced | Invoiced | 6 | 340 |  |  |  | 2026-01-01 | Completed | Invoiced
341 | 242890 | 341 | 2025-12-09 | 2025-12-08 | 2025-12-19 | 2026-03-08 | 2026-09-12 | OL | OL-F1F5-0040 | 79 | 1177758 | Pending | 811084 | Approved/Expired | 2026-01-18 | 2026-06-25 | NEWCON | 0040 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 65 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 3 |  | 4 |  | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8050 | 0 | Pending | Pending | Pending | 341 |  |  |  |  | Pending | Pending
342 | 242910 | 342 | 2025-12-09 | 2025-12-08 | 2025-12-19 | 2026-03-08 | 2026-09-12 | OL | OL-F10-16573 | 79 | 1177802 | Pending | 813146 | Approved/Expired | 2026-02-03 | 2026-07-09 | NEWCON | 22289 | 1 | Al Duhail South (31 ) | 60 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 3 |  | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6510 | 0 | Pending | Pending | Pending | 342 |  |  |  |  | Pending | Pending
343 | 242913 | 343 | 2025-12-09 | 2025-12-08 | 2025-12-19 | 2026-03-08 | 2026-09-12 | OL | OL-F6-19898 | 79 | 1177804 | Pending | 811084 | Approved/Expired | 2026-01-18 | 2026-06-25 | NEWCON | 19898 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 15 | 15 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 1 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3165 | 3165 | Pending | Pending | Pending | 343 |  |  |  |  | Pending | Pending
344 | 242971 | 344 | 2025-12-10 | 2025-12-09 | 2025-12-20 | 2026-03-09 | 2026-09-12 | OL | OL-F10-11853 | 79 | 1178083 | Pending | 813731 | Approved/Expired | 2026-01-25 | 2026-07-09 | NEWCON | 11853 | 1 | Al Khor (74 ) | 8 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 2 |  | 2 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2660 | 0 | Pending | Pending | Pending | 344 |  |  |  |  | Pending | Pending
345 | 242977 | 345 | 2025-12-10 | 2025-12-09 | 2025-12-20 | 2026-03-09 | 2026-09-12 | OL | OL-F13F15-0137 | 79 | 1178091 | Pending | 812427 | Approved/Expired | 2026-02-03 | 2026-07-02 | NEWCON | 0137 | 1 | Madinat Khalifa (South) (34 ) | 11 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 2 |  | 5 |  | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4280 | 0 | Pending | Pending | Pending | 345 |  |  |  |  | Pending | Pending
346 | 242991 | 346 | 2025-12-10 | 2025-12-09 | 2025-12-20 | 2026-03-09 | 2026-09-12 | OL | OL-F3-3417 | 79 | 1178105 | Pending | 811699 | Approved/Expired | 2026-01-07 | 2026-06-25 | NEWCON | 3417 | 1 | Al Markhiya (33 ) | 70 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 2 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6420 | 0 | Pending | Pending | Pending | 346 |  |  |  |  | Pending | Pending
347 | 242994 | 347 | 2025-12-10 | 2025-12-09 | 2025-12-20 | 2026-03-09 | 2026-09-12 | OL | OL F4-3937 | 79 | 1178108 | Not Clear | Hold | Hold | Pending | Pending | NEWCON | 31556 | 1 | Kulaib (35 ) | 220 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 2 |  | 3 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 16070 | 0 | Hold | Pending | Pending | 347 |  |  |  |  | Pending | Pending
348 | 242999 | 348 | 2025-12-11 | 2025-12-10 | 2025-12-21 | 2026-02-10 | 2026-09-12 | MOC | MOC-90798 | 51 | 1178167 | Completed | 811700 | Approved/Printed | 2026-01-01 | 2026-06-18 | NEWCON | 26866 | 1 | Al Rayyan Al Jadeed/Muaither N(53 ) | 132 | 132 | 0 |  | 0 | 0 | 132 | 132 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 17834 | 17834 | Invoiced | Invoiced | 6 | 348 |  |  |  | 2026-01-01 | Completed | Invoiced
349 | 243001 | 349 | 2025-12-11 | 2025-12-10 | 2025-12-21 | 2026-02-10 | 2026-01-27 | MOC | MOC-237887 | 51 | 1178172 | Completed | 811701 | Approved/Printed | 2026-01-04 | 2026-06-18 | NEWCON | 40937 | 1 | Al Kheesa (70 ) | 42 | 42 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 4320 | 4320 | Invoiced | Invoiced | 7 | 349 |  |  |  | 2026-01-01 | Completed | Invoiced
350 | 243003 | 350 | 2025-12-11 | 2025-12-10 | 2025-12-21 | 2026-02-10 | 2026-01-27 | MOC | MOC-249742 | 51 | 1178175 | Completed | 811701 | Approved/Printed | 2026-01-04 | 2026-06-18 | NEWCON | 33910 | 1 | Al Kheesa (70 ) | 26 | 26 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3360 | 3360 | Invoiced | Invoiced | 7 | 350 |  |  |  | 2026-01-01 | Completed | Invoiced
351 | 243014 | 351 | 2025-12-11 | 2025-12-10 | 2025-12-21 | 2026-02-10 | 2026-03-30 | MOC | MOC-224839 | 51 | 1178214 | Completed | 811702/ 818117 | Approved/Printed | 2026-01-11 | 2026-06-18 | NEWCON | 0139 | 1 | Kulaib (35 ) | 69 | 69 | 28 | 28 | 0 | 0 | 12 | 12 | 0 | 0 | 150 | 150 | 1 | 1 | 0 | 0 | 3 | 3 | 5 | 5 | 4 | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 36024 | 36024 | Invoiced | Invoiced | 9 | 351 |  |  |  | 2026-03-26 | Completed | Invoiced
352 | 243062 | 352 | 2025-12-14 | 2025-12-13 | 2025-12-24 | 2026-03-14 | 2026-09-12 | OL | OL-F3-15614 | 80 | 1178789 | Pending | 812428 | Approved/Expired | 2026-01-13 | 2026-07-02 | NEWCON | 25784 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 1 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1885 | 0 | Pending | Pending | Pending | 352 |  |  |  |  | Pending | Pending
353 | 243064 | 353 | 2025-12-14 | 2025-12-13 | 2025-12-24 | 2026-03-14 | 2026-09-12 | OL | OL-F3-20596 | 80 | 1178898 | Pending | 812428 | Approved/Expired | 2026-01-13 | 2026-07-02 | NEWCON | 20596 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1590 | 0 | Pending | Pending | Pending | 353 |  |  |  |  | Pending | Pending
354 | 243078 | 354 | 2025-12-14 | 2025-12-13 | 2025-12-24 | 2026-03-14 | 2026-09-12 | OL | OL-F4-0093 | 80 | 1179052 | Pending | 812428 | Approved/Expired | 2026-01-13 | 2026-07-02 | NEWCON | 0093 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 8 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2010 | 0 | Pending | Pending | Pending | 354 |  |  |  |  | Pending | Pending
355 | 243085 | 355 | 2025-12-14 | 2025-12-13 | 2025-12-24 | 2026-03-14 | 2026-09-12 | OL | OL-F4-14389 | 80 | 1179059 | Pending | 812428 | Approved/Expired | 2026-01-13 | 2026-07-02 | NEWCON | 14389 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 4 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1770 | 0 | Pending | Pending | Pending | 355 |  |  |  |  | Pending | Pending
356 | 243123 | 356 | 2025-12-14 | 2025-12-13 | 2025-12-24 | 2026-03-14 | 2026-09-12 | OL | OL-F4-0081 | 80 | 1179163 | Cancelled | NA | NA | Cancelled | Cancelled | AL MORAQUIB | 0081 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 17 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2607 | 0 | Cancelled | Cancelled | Cancelled | 356 |  |  |  |  | Cancelled | Cancelled
357 | 243129 | 357 | 2025-12-14 | 2025-12-13 | 2025-12-24 | 2026-02-13 | 2026-01-29 | MOC | MOC-229441 | 51 | 1179174 | Completed | 812429 | Approved/Printed | 2026-01-07 | 2026-07-02 | NEWCON | 17542 | 1 | Al Markhiya (33 ) | 16 | 16 | 0 |  | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3672 | 3672 | Invoiced | Invoiced | 7 | 357 |  |  |  | 2026-01-01 | Completed | Invoiced
358 | 243142 | 358 | 2025-12-15 | 2025-12-14 | 2025-12-25 | 2026-03-14 | 2026-05-12 | BP | BP#151867 | 79 | 1179305 | Completed | 812428 | Approved/Printed | 2026-01-13 | 2026-07-02 | NEWCON | 10779 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 122 | 122 | 0 | 0 | 0 | 0 | 122 | 122 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 15824 | 15824 | Invoiced | Invoiced | 12 | 358 |  |  |  | 2026-04-14 | Completed | Invoiced
359 | 243145 | 359 | 2025-12-15 | 2025-12-14 | 2025-12-25 | 2026-03-14 | 2026-04-14 | BP | BP#152224 | 79 | 1179318 | Completed | 812427 | Approved/Printed | 2026-02-03 | 2026-07-02 | NEWCON | 0148 | 1 | Madinat Khalifa (South) (34 ) | 135 | 135 | 0 | 0 | 0 | 0 | 41 | 41 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 11352 | 11352 | Invoiced | Invoiced | 10 | 359 |  |  |  | 2026-04-12 | Completed | Invoiced
360 | 243148 | 360 | 2025-12-15 | 2025-12-14 | 2025-12-25 | 2026-03-14 | 2026-09-12 | BP | BP#151968 | 79 | 1179329 | Pending | 812964 | Approved/Expired | 2026-01-15 | 2026-07-09 | NEWCON | 35456 | 1 | Al Duhail South (31 ) | 196 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 13495 | 0 | Pending | Pending | Pending | 360 |  |  |  |  | Pending | Pending
361 | 243238 | 361 | 2025-12-16 | 2025-12-15 | 2025-12-26 | 2026-02-15 | 2026-01-24 | MOC | MOC-235137+38 | 51 | 1179757 | Completed | 812433 | Approved/Printed | 2025-12-31 | 2026-07-02 | NEWCON | 13437 | 2 | Umm Slal/Al Kharaitiyat (71 ) | 92 | 92 | 0 |  | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 3 | 3 | 4 | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 10420 | 10420 | Invoiced | Invoiced | 8 | 361 |  |  |  | 2026-01-01 | Completed | Invoiced
362 | 243239 | 362 | 2025-12-16 | 2025-12-15 | 2025-12-26 | 2026-02-15 | 2026-02-03 | MOC | MOC-18037019 | 51 | 1179758 | Completed | 812434 | Approved/Printed | 2026-01-06 | 2026-07-02 | NEWCON | 4700 | 1 | Al Kheesa (70 ) | 60 | 60 |  |  | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 3 | 3 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 6680 | 6680 | Invoiced | Invoiced | 8 | 362 |  |  |  | 2026-01-01 | Completed | Invoiced
363 | 243325 | 363 | 2025-12-17 | 2025-12-16 | 2025-12-27 | 2026-03-16 | 2026-09-12 | BP | BP#150239 | 79 | 1180142 | Pending | 812427 | Approved/Expired | 2026-02-03 | 2026-07-02 | NEWCON | 3205 | 1 | Madinat Khalifa (South) (34 ) | 140 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10135 | 0 | Pending | Pending | Pending | 363 |  |  |  |  | Pending | Pending
364 | 243326 | 364 | 2025-12-17 | 2025-12-16 | 2025-12-27 | 2026-03-16 | 2026-09-12 | BP | BP#N/2025/3796 PIN#05130037 | 79 | 1180144 | Cancelled | NA | NA | Cancelled | Cancelled | AL MORAQUIB | 1815 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 2 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1813 | 0 | Cancelled | Cancelled | Cancelled | 364 |  |  |  |  | Cancelled | Cancelled
365 | 243366 | 365 | 2025-12-17 | 2025-12-16 | 2025-12-27 | 2026-02-16 | 2026-01-25 | MOC | MOC-243509+10+11+12 | 51 | 1180310 | Completed | 812435 | Approved/Printed | 2026-01-06 | 2026-06-25 | AL MORAQUIB | 1815 | 4 | Al Khor (74 ) | 135 | 135 | 0 |  | 0 | 0 | 85 | 85 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 1 | 1 | 3 | 3 | 6 | 6 | 0 | 0 | 4 | 4 | 0 | 0 | 19575 | 19575 | Invoiced | Invoiced | 8 | 365 |  |  |  | 2026-01-01 | Completed | Invoiced
366 | 243373 | 366 | 2025-12-17 | 2025-12-16 | 2025-12-27 | 2026-02-16 | 2026-01-22 | MOC | MOC#153138 | 51 | 1180323 | Completed | 812434 | Approved/Printed | 2026-01-06 | 2026-07-02 | NEWCON | 10057 | 1 | Al Kheesa (70 ) | 181 | 181 | 0 |  | 0 | 0 | 181 | 181 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 24257 | 24257 | Invoiced | Invoiced | 7 | 366 |  |  |  | 2026-01-01 | Completed | Invoiced
367 | 243396 | 367 | 2025-12-21 | 2025-12-20 | 2025-12-31 | 2026-03-20 | 2026-09-12 | OL | OL-F1-3536 | 79 | 1180770 | Cancelled | 813141 | Approved/Printed | 2026-01-25 | 2026-07-09 | AL MORAQUIB | 3536 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 2 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2337 | 0 | Cancelled | Cancelled | Cancelled | 367 |  |  |  |  | Cancelled | Cancelled
368 | 243397 | 368 | 2025-12-21 | 2025-12-20 | 2025-12-31 | 2026-03-20 | 2026-02-17 | OL | OL-F6-3111 | 79 | 1180788 | Completed | 811702 | Approved/Printed | 2026-01-11 | 2026-06-18 | NEWCON | 3111 | 1 | Kulaib (35 ) | 10 | 10 | 0 |  | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2430 | 2430 | Invoiced | Invoiced | 12 | 368 |  |  |  | 2026-02-01 | Completed | Invoiced
369 | 243398 | 369 | 2025-12-21 | 2025-12-20 | 2025-12-31 | 2026-03-20 | 2026-09-12 | OL | OL-F1-2163 | 79 | 1180802 | Pending | 814351 | Approved/Expired | 2026-02-19 | 2026-07-23 | NEWCON | 3553 | 1 | Kulaib (35 ) | 12 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 2 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2940 | 0 | Pending | Pending | Pending | 369 |  |  |  |  | Pending | Pending
370 | 243399 | 370 | 2025-12-21 | 2025-12-20 | 2025-12-31 | 2026-03-20 | 2026-09-12 | OL | OL-F4-0131 | 79 | 1180808 | Pending | 814585 | Approved/Expired | 2026-02-03 | 2026-07-23 | NEWCON | 0131 | 1 | Madinat Khalifa(South)(34) | 90 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 2 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6990 | 0 | Pending | Pending | Pending | 370 |  |  |  |  | Pending | Pending
371 | 243400 | 371 | 2025-12-21 | 2025-12-20 | 2025-12-31 | 2026-03-20 | 2026-09-12 | OL | OL-F2-0053 | 79 | 1180846 | Pending | 814585 | Approved/Expired | 2026-02-03 | 2026-07-23 | NEWCON | 0053 | 1 | Madinat Khalifa(South)(34) | 50 | 0 | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 2 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5220 | 0 | Pending | Pending | Pending | 371 |  |  |  |  | Pending | Pending
372 | 243412 | 372 | 2026-01-13 | 2026-01-12 | 2026-01-23 | 2026-04-13 | 2026-09-12 | OL | OL-TX1F1F6-11404 | 80 | 1180912 | Pending | 814585 | Approved/Expired | 2026-02-03 | 2026-07-23 | NEWCON | 11404 | 1 | Madinat Khalifa(South)(34) | 83 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 2 |  | 2 |  | 2 |  | 0 | 0 | 1 |  | 0 | 0 | 8060 | 0 | Pending | Pending | Pending | 372 |  |  |  |  | Pending | Pending
373 | 243433 | 373 | 2025-12-21 | 2025-12-20 | 2025-12-31 | 2026-03-20 | 2026-03-26 | OL | OL-F3-20169 | 79 | 1181079 | Completed | 814585 | Approved/Printed | 2026-02-03 | 2026-07-23 | NEWCON | 20169 | 1 | Madinat Khalifa(South)(34) | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1562 | 1562 | Invoiced | Invoiced | 8 | 373 |  |  |  | 2026-03-24 | completed | Invoiced
374 | 243435 | 374 | 2025-12-21 | 2025-12-20 | 2025-12-31 | 2026-03-20 | 2026-09-12 | OL | OL-F11-31674 | 79 | 1181098 | Pending | 814585 | Approved/Expired | 2026-02-03 | 2026-07-23 | NEWCON | 31674 | 1 | Madinat Khalifa(South)(34) | 53 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4710 | 0 | Pending | Pending | Pending | 374 |  |  |  |  | Pending | Pending
375 | 243426 | 375 | 2025-12-21 | 2025-12-20 | 2025-12-31 | 2026-02-20 | 2026-02-11 | MOC | MOC-235270 | 51 | 1181004 | Completed | 812435 | Approved/Printed | 2026-01-06 | 2026-06-25 | AL MORAQUIB | 11416 | 1 | Al Khor (74 ) | 232 | 232 | 0 |  | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 17265 | 17265 | Invoiced | Invoiced | 7 | 375 |  |  |  | 2026-02-01 | completed | Invoiced
376 | 243501 | 376 | 2025-12-23 | 2025-12-22 | 2026-01-02 | 2026-03-22 | 2026-09-12 | OL | OL-TX1-3727 | 79 | 1181966 | Pending | 812966 | Approved/Expired | 2026-01-21 | 2026-07-09 | NEWCON | 17210 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 160 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 2 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 11395 | 0 | Pending | Pending | Pending | 376 |  |  |  |  | Pending | Pending
377 | 243623 | 377 | 2025-12-24 | 2025-12-23 | 2026-01-03 | 2026-03-23 | 2026-09-12 | OL | OL-F11-16542 | 79 | 1182619 | Pending | 813146 | Approved/Expired | 2026-02-03 | 2026-07-09 | NEWCON | 16542 | 1 | Al Duhail South (31 ) | 25 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3235 | 0 | Pending | Pending | Pending | 377 |  |  |  |  | Pending | Pending
378 | 243675 | 378 | 2025-12-28 | 2025-12-27 | 2026-01-07 | 2026-03-27 | 2026-09-12 | OL | OL-F5-1393 | 79 | 1183654 | Pending | 814432 | Approved/Expired | 2026-01-27 | 2026-07-23 | NEWCON | 1393 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 7 | 7 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2059 | 2059 | Pending | Pending | Pending | 378 |  |  |  |  | Pending | Pending
379 | 243676 | 379 | 2025-12-28 | 2025-12-27 | 2026-01-07 | 2026-03-27 | 2026-07-21 | OL | OL-F5F12-12723 | 79 | 1183711 | Completed | 814432 | Approved/Printed | 2026-01-27 | 2026-07-23 | NEWCON | 12723 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 13 | 13 | 0 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3621 | 3621 | Completed | Pending | Pending | 379 |  |  |  | 2026-07-09 | completed | Pending
380 | 243677 | 380 | 2025-12-28 | 2025-12-27 | 2026-01-07 | 2026-03-27 | 2026-09-12 | OL | OL-F6-19959 | 79 | 1183753 | Pending | 813141 | Approved/Expired | 2026-01-25 | 2026-07-09 | NEWCON | 19959 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 60 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5130 | 0 | Pending | Pending | Pending | 380 |  |  |  |  | Pending | Pending
381 | 243678 | 381 | 2025-12-28 | 2025-12-27 | 2026-01-07 | 2026-03-27 | 2026-09-12 | OL | OL-F22-22287 | 79 | 1183770 | Pending | 813141 | Approved/Expired | 2026-01-25 | 2026-07-09 | NEWCON | 22287 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 5 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 2 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2715 | 0 | Pending | Pending | Pending | 381 |  |  |  |  | Pending | Pending
382 | 243680 | 382 | 2025-12-28 | 2025-12-27 | 2026-01-07 | 2026-03-27 | 2026-09-12 | OL | OL-F2-11694 | 79 | 1183781 | Pending | 813141 | Approved/Expired | 2026-01-25 | 2026-07-09 | NEWCON | 11694 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 1 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1885 | 0 | Pending | Pending | Pending | 382 |  |  |  |  | Pending | Pending
383 | 243687 | 383 | 2025-12-28 | 2025-12-27 | 2026-01-07 | 2026-03-27 | 2026-09-12 | OL | OL-F1-12892 | 79 | 1183831 | Pending | 813141 | Approved/Expired | 2026-01-25 | 2026-07-09 | NEWCON | 12892 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 42 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 2 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4740 | 0 | Pending | Pending | Pending | 383 |  |  |  |  | Pending | Pending
384 | 243715 | 384 | 2025-12-28 | 2025-12-27 | 2026-01-07 | 2026-03-28 | 2026-04-18 | BP | BPN/2025/2547 PIN51631799 | 80 | 1183891 | Completed | 813143 | Approved/Printed | 2026-01-13 | 2026-07-09 | NEWCON | 19511 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 556 | 556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 36120 | 36120 | Invoiced | Invoiced | 10 | 384 |  |  |  | 2026-03-05 | Completed | Invoiced
385 | 243710 | 385 | 2025-12-28 | 2025-12-27 | 2026-01-07 | 2026-03-28 | 2026-06-30 | BP | BP-151214,PIN-74091358 | 80 | 1183880 | Completed | 813731 | Approved/Printed | 2026-01-25 | 2026-07-09 | NEWCON | 10532 | 1 | Al Khor (74 ) | 308 | 308 | 0 | 0 | 0 | 0 | 85 | 85 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 25355 | 25355 | Invoiced | Invoiced | 13 | 385 |  |  |  | 2026-06-25 | Completed | Invoiced
386 | 243726 | 386 | 2025-12-28 | 2025-12-27 | 2026-01-07 | 2026-03-28 | 2026-03-09 | BP | BP-147566+BP-151203 | 80 | 1183910 | Completed | 813141 | Approved/Printed | 2026-01-25 | 2026-07-09 | NEWCON | 40380 | 2 | Umm Slal/Al Kharaitiyat (71 ) | 76 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5210 | 5210 | Invoiced | Invoiced | 9 | 386 |  |  |  | 2026-03-09 | Completed | Invoiced
387 | 243825 | 387 | 2025-12-30 | 2025-12-29 | 2026-01-09 | 2026-03-01 | 2026-02-09 | MOC | MOC#230730 | 51 | 1184749 | Completed | 813542 | Approved/Printed | 2026-01-13 | 2026-07-09 | KAR | 9939 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 138 | 138 | 0 |  | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 10308 | 10308 | Invoiced | Invoiced | 7 | 387 |  |  |  | 2026-02-01 | Completed | Invoiced
388 | 243937 | 388 | 2026-01-01 | 2025-12-31 | 2026-01-11 | 2026-04-02 | 2026-09-12 | OL | OL-F1F5-4999 | 81 | 1185429 | Pending | 813962 | Approved/Expired | 2026-01-26 | 2026-07-16 | NEWCON | 4999 | 1 | Al Khor (74 ) | 10 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 3 |  | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 0 | Pending | Pending | Pending | 388 |  |  |  |  | Pending | Pending
389 | 243940 | 389 | 2026-01-01 | 2025-12-31 | 2026-01-11 | 2026-04-02 | 2026-09-12 | OL | OL-TX2-F8-12195 | 81 | 1185537 | Pending | 813962 | Approved/Expired | 2026-01-26 | 2026-07-16 | NEWCON | 12195 | 1 | Al Khor (74 ) | 8 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 4 |  | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4080 | 0 | Pending | Pending | Pending | 389 |  |  |  |  | Pending | Pending
390 | 244013 | 390 | 2026-01-01 | 2025-12-31 | 2026-01-11 | 2026-04-02 | 2026-09-12 | OL | OL-F11-24542 | 81 | 1185770 | Pending | 813962 | Approved/Expired | 2026-01-26 | 2026-07-16 | NEWCON | 24542 | 1 | Al Khor (74 ) | 11 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 2 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2880 | 0 | Pending | Pending | Pending | 390 |  |  |  |  | Pending | Pending
391 | 244017 | 391 | 2026-01-01 | 2025-12-31 | 2026-01-11 | 2026-04-02 | 2026-09-12 | OL | OL-F9-20591 | 81 | 1185775 | Pending | 813962 | Approved/Expired | 2026-01-26 | 2026-07-16 | NEWCON | 20591 | 1 | Al Khor (74 ) | 3 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1710 | 0 | Pending | Pending | Pending | 391 |  |  |  |  | Pending | Pending
392 | 244169 | 392 | 2026-01-06 | 2026-01-05 | 2026-01-16 | 2026-04-06 | 2026-09-12 | OL | OL-F1-1264 | 80 | 1187034 | Pending | 814969 | Approved/Expired | 2026-02-11 | 2026-07-30 | NEWCON | 1264 | 1 | Madinat Khalifa(North)(32) | 1 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 1860 | 0 | Pending | Pending | Pending | 392 |  |  |  |  | Pending | Pending
393 | 244180 | 393 | 2026-01-06 | 2026-01-05 | 2026-01-16 | 2026-04-06 | 2026-07-12 | OL | OL-F5-20151 | 80 | 1187109 | Completed | 814969 | Approved/Printed | 2026-02-11 | 2026-07-30 | NEWCON | 20151 | 1 | Madinat Khalifa(North)(32) | 6 | 6 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1640 | 1640 | Completed | Pending | Pending | 393 |  |  |  | 2026-07-06 | Pending | Pending
394 | 244184 | 394 | 2026-01-06 | 2026-01-05 | 2026-01-16 | 2026-04-06 | 2026-07-20 | OL | OL-F4-0046 | 80 | 1187115 | Completed | 814969 | Approved/Printed | 2026-02-11 | 2026-07-30 | NEWCON | 0046 | 1 | Madinat Khalifa(North)(32) | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1982 | 1982 | Completed | Pending | Pending | 394 |  |  |  | 2026-07-06 | Pending | Pending
395 | 244306 | 395 | 2026-01-07 | 2026-01-06 | 2026-01-17 | 2026-03-09 | 2026-02-15 | MOC | IN#113590 MOC#237004 | 51 | 1187862 | Completed | 814627 | Approved/Printed | 2026-01-21 | 2026-07-16 | NEWCON | 23903 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 3450 | 3450 | Invoiced | Invoiced | 7 | 395 |  |  |  | 2026-02-01 | Completed | Invoiced
396 | 244363 | 396 | 2026-01-08 | 2026-01-07 | 2026-01-18 | 2026-03-10 | 2026-02-16 | MOC | IN#113826 MOC3232599 | 51 | 1188351 | Completed | 814628 | Approved/Printed | 2026-01-26 | 2026-07-16 | NEWCON | 1942 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 120 | 120 | 0 |  | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 17220 | 17220 | Invoiced | Invoiced | 8 | 396 |  |  |  | 2026-06-01 | Completed | Invoiced
397 | 244376 | 397 | 2026-01-11 | 2026-01-10 | 2026-01-21 | 2026-04-11 | 2026-07-20 | OL | OL-F6-3389 | 80 | 1188786 | Completed | 814969 | Approved/Printed | 2026-02-11 | 2026-07-30 | NEWCON | 3389 | 1 | Madinat Khalifa(North)(32) | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1912 | 1912 | Completed | Pending | Pending | 397 |  |  |  | 2026-07-08 | Pending | Pending
398 | 244436 | 398 | 2026-01-12 | 2026-01-11 | 2026-01-22 | 2026-04-12 | 2026-09-12 | BP | BP#N/2025/5193 PIN#34510005 | 80 | 1189375 | Pending | 814970 | Approved/Expired | 2026-02-03 | 2026-07-30 | NEWCON | 0063 | 1 | Madinat Khalifa(South)(34) | 64 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 2 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6165 | 0 | Pending | Pending | Pending | 398 |  |  |  |  | Pending | Pending
399 | 244438 | 399 | 2026-01-12 | 2026-01-11 | 2026-01-22 | 2026-04-12 | 2026-06-28 | BP | BP#150114 | 80 | 1189378 | Completed | 815574 | Approved/Printed | 2026-02-11 | 2026-07-30 | NEWCON | 9851 | 1 | Al Duhail South (31 ) | 96 | 96 | 0 | 0 | 0 | 0 | 5 | 5 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 7840 | 7840 | Invoiced | Invoiced | 13 | 399 |  |  |  | 2026-06-21 | Completed | Invoiced
400 | 244439 | 400 | 2026-01-12 | 2026-01-11 | 2026-01-22 | 2026-04-12 | 2026-03-16 | BP | BP#152303 | 80 | 1189379 | Completed | 815575 | Approved/Printed | 2026-02-19 | 2026-07-30 | NEWCON | 22541 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 110 | 110 | 12 | 12 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9350 | 9350 | Invoiced | Invoiced | 8 | 400 |  |  |  | 2026-03-15 | Completed | Invoiced
401 | 244449 | 401 | 2026-01-12 | 2026-01-11 | 2026-01-22 | 2026-03-14 | 2026-04-04 | MOC | C-1232422 MSA-18037367 | 51 | 1189395 | Completed | 814971 | Approved/Printed | 2026-02-03 | 2026-07-23 | Smart Elevation | 23036 | 1 | New District Of Doha 67 (67) | 268 | 268 | 0 | 0 | 0 | 0 | 138 | 138 | 130 | 130 | 0 | 0 | 3 | 3 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 36961 | 36961 | Invoiced | Invoiced | 10 | 401 |  |  |  | 2026-03-31 | Completed | Invoiced
402 | 244539 | 402 | 2026-01-12 | 2026-01-11 | 2026-01-22 | 2026-04-12 | 2026-09-12 | OL | OL-F9-0589 | 80 | 1189687 | Cancelled | NA | NA | Cancelled | Cancelled | NEWCON | 0589 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 71 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 2 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6537 | 0 | Cancelled | Cancelled | Cancelled | 402 |  |  |  |  | Cancelled | Cancelled
403 | 244545 | 403 | 2026-01-13 | 2026-01-12 | 2026-01-23 | 2026-04-13 | 2026-09-12 | OL | OL-F2F5-5305 | 80 | 1189873 | Pending | 816534 | Approved/Expired | 2026-03-11 | 2026-08-06 | NEWCON | 5305 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 20 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 2 |  | 3 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3440 | 0 | Pending | Pending | Pending | 403 |  |  |  |  | Pending | Pending
404 | 244617 | 404 | 2026-01-13 | 2026-01-12 | 2026-01-23 | 2026-04-13 | 2026-04-13 | BP | BP-151205+BP-152357 | 80 | 1190130 | Completed | 815575 | Approved/Printed | 2026-02-19 | 2026-07-30 | NEWCON | 13479 | 2 | Umm Slal/Al Kharaitiyat (71 ) | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 1600 | Invoiced | Invoiced | 11 | 404 |  |  |  | 2026-04-06 | Completed | Invoiced
405 | 244616 | 405 | 2026-01-13 | 2026-01-12 | 2026-01-23 | 2026-04-13 | 2026-07-09 | BP | BP-152380 | 80 | 1190131 | Completed | 815575 | Approved/Printed | 2026-02-19 | 2026-07-30 | AL MORAQUIB | 25831 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 134 | 134 | 0 |  | 0 | 0 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 12720 | 12720 | Invoiced | Invoiced | 13 | 405 |  |  |  | 2026-06-01 | Completed | Invoiced
406 | 244764 | 406 | 2026-01-15 | 2026-01-14 | 2026-01-25 | 2026-04-15 | 2026-09-12 | OL | OL-TX2-38181 | 80 | 1191041 | Pending | 816534 | Approved/Expired | 2026-03-11 | 2026-08-06 | NEWCON | 16314 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 35 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 5 |  | 4 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6375 | 0 | Pending | Pending | Pending | 406 |  |  |  |  | Pending | Pending
407 | 244766 | 407 | 2026-01-18 | 2026-01-17 | 2026-01-28 | 2026-04-18 | 2026-09-12 | OL | OL-F5-10814 | 80 | 1191582 | Pending | 816534 | Approved/Expired | 2026-03-11 | 2026-08-06 | NEWCON | 10814 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 16 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2490 | 0 | Pending | Pending | Pending | 407 |  |  |  |  | Pending | Pending
408 | 244769 | 408 | 2026-01-18 | 2026-01-17 | 2026-01-28 | 2026-04-18 | 2026-09-12 | OL | OL-F2-12517 | 80 | 1191606 | Pending | 816010 | Approved/Expired | 2026-02-11 | 2026-08-06 | NEWCON | 12517 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 10 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 2 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2820 | 0 | Pending | Pending | Pending | 408 |  |  |  |  | Pending | Pending
409 | 244778 | 409 | 2026-01-18 | 2026-01-17 | 2026-01-28 | 2026-04-18 | 2026-09-12 | OL | OL-F11-12521 | 80 | 1191645 | Pending | 816010 | Approved/Expired | 2026-02-11 | 2026-08-06 | NEWCON | 12521 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 35 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 2 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4320 | 0 | Pending | Pending | Pending | 409 |  |  |  |  | Pending | Pending
410 | 244783 | 410 | 2026-01-18 | 2026-01-17 | 2026-01-28 | 2026-04-18 | 2026-09-12 | OL | OL-F2-12523 | 80 | 1191684 | Pending | 816010 | Approved/Expired | 2026-02-11 | 2026-08-06 | NEWCON | 12516 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 90 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 2 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6990 | 0 | Pending | Pending | Pending | 410 |  |  |  |  | Pending | Pending
411 | 244784 | 411 | 2026-02-15 | 2026-02-14 | 2026-02-25 | 2026-05-16 | 2026-09-12 | OL | OL-F2-0732 | 80 | 1191781 | Pending | 818119 | Approved/Expired | 2026-03-02 | 2026-08-27 | NEWCON | 0732 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 110 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8335 | 0 | Pending | Pending | Pending | 411 |  |  |  |  | Pending | Pending
412 | 244794 | 412 | 2026-01-18 | 2026-01-17 | 2026-01-28 | 2026-04-18 | 2026-09-12 | OL | OL-F19-22865 | 80 | 1191790 | Pending | 816534 | Approved/Expired | 2026-03-11 | 2026-08-06 | NEWCON | 22865 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 54 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 2 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5565 | 0 | Pending | Pending | Pending | 412 |  |  |  |  | Pending | Pending
413 | 244828 | 413 | 2026-01-18 | 2026-01-17 | 2026-01-28 | 2026-04-18 | 2026-09-12 | OL | OL-F6-3771 | 80 | 1191869 | Pending | 816010 | Approved/Expired | 2026-02-11 | 2026-08-06 | NEWCON | 3771 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 90 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 2 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7520 | 0 | Pending | Pending | Pending | 413 |  |  |  |  | Pending | Pending
414 | 244830 | 414 | 2026-01-18 | 2026-01-17 | 2026-01-28 | 2026-04-18 | 2026-09-12 | OL | OL-F5-21938 | 80 | 1191888 | Pending | 816534 | Approved/Expired | 2026-03-11 | 2026-08-06 | NEWCON | 21938 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 30 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 2 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4045 | 0 | Pending | Pending | Pending | 414 |  |  |  |  | Pending | Pending
415 | 244833 | 415 | 2026-01-18 | 2026-01-17 | 2026-01-28 | 2026-04-18 | 2026-09-12 | OL | OL-F9-12608 | 80 | 1191927 | Pending | 816010 | Approved/Expired | 2026-02-11 | 2026-08-06 | NEWCON | 12608 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 15 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2635 | 0 | Pending | Pending | Pending | 415 |  |  |  |  | Pending | Pending
416 | 244837 | 416 | 2026-01-18 | 2026-01-17 | 2026-01-28 | 2026-04-18 | 2026-09-12 | OL | OL-F4-3860 | 80 | 1191939 | ROW | RO NA | ROW | Pending | Pending | NEWCON | 3860 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 12 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 2 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2310 | 0 | Pending | Pending | Pending | 416 |  |  |  |  | Pending | Pending
417 | 244841 | 417 | 2026-01-18 | 2026-01-17 | 2026-01-28 | 2026-04-18 | 2026-09-12 | BP | BP152421 | 80 | 1191949 | Pending | 815802 | Approved/Expired | 2026-02-11 | 2026-07-30 | NEWCON | 1630 | 1 | New District Of Doha (65) | 35 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 3380 |  | Pending | Pending | Pending | 417 |  |  |  |  | Pending | Pending
418 | 244842 | 418 | 2026-01-18 | 2026-01-17 | 2026-01-28 | 2026-04-18 | 2026-07-06 | BP | BP129666 | 80 | 1191951 | Completed | 815802 | Approved/Printed | 2026-02-11 | 2026-07-30 | NEWCON | 1644 | 1 | New District Of Doha (65) | 52 | 52 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6375 | 6375 | Invoiced | Invoiced | 13 | 418 |  |  |  | 2026-07-05 | Completed | Invoiced
419 | 244843 | 419 | 2026-01-18 | 2026-01-17 | 2026-01-28 | 2026-04-18 | 2026-07-07 | BP | BP152391 | 80 | 1191952 | Completed | 815575 | Approved/Printed | 2026-02-19 | 2026-07-30 | BD DHAKA | 22544 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 238 | 238 | 0 | 0 | 0 | 0 | 117 | 117 | 8 | 8 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 4 | 4 | 3 | 3 | 0 | 0 | 0 |  | 0 | 0 | 25029 | 25029 | Invoiced | Invoiced | 13 | 419 |  |  |  | 2026-06-01 | completed | Invoiced
420 | 244873 | 420 | 2026-01-19 | 2026-01-18 | 2026-01-29 | 2026-04-19 | 2026-09-12 | OL | OL-F4-5450 | 80 | 1192214 | Pending | 817030 | Approved/Expired | 2026-02-22 | 2026-08-13 | NEWCON | 5450 | 1 | Al Khor (74 ) | 56 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 2 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5685 | 0 | Pending | Pending | Pending | 420 |  |  |  |  | Pending | Pending
421 | 244911 | 421 | 2026-01-19 | 2026-01-18 | 2026-01-29 | 2026-04-19 | 2026-08-06 | OL | OL-F6-14441 | 80 | 1192239 | Completed | 819880 | Approved/Printed | 2026-04-06 | 2026-09-17 | NEWCON | 14441 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 97 | 97 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 5 | 5 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 12250 | 12250 | Completed | Pending | Pending | 421 |  |  |  | 2026-08-03 | Pending | Pending
422 | 244953 | 422 | 2026-01-19 | 2026-01-18 | 2026-01-29 | 2026-04-19 | 2026-07-19 | BP | BP152592 | 80 | 1192354 | Completed | 816323 | Approved/Printed | 2026-02-19 | 2026-08-13 | NEWCON | 1293 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 142 | 142 | 0 | 0 | 0 | 0 | 54 | 54 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 12288 | 12288 | Invoiced | Invoiced | 13 | 422 |  |  |  | 2026-07-12 | completed | Invoiced
423 | 244954 | 423 | 2026-01-19 | 2026-01-18 | 2026-01-29 | 2026-04-19 | 2026-07-08 | BP | BP152594 | 80 | 1192355 | Completed | 816323 | Approved/Printed | 2026-02-19 | 2026-08-13 | NEWCON | 5155 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 55 | 55 | 0 | 0 | 0 | 0 | 55 | 55 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 7125 | 7125 | Invoiced | Invoiced | 13 | 423 |  |  |  | 2026-07-05 | completed | Invoiced
424 | 244955 | 424 | 2026-01-19 | 2026-01-18 | 2026-01-29 | 2026-04-19 | 2026-08-02 | BP | BP152626 | 80 | 1192356 | Completed | 816324 | Approved/Printed | 2026-02-25 | 2026-08-13 | NEWCON | 2810 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 111 | 111 | 0 | 0 | 0 | 0 | 94 | 94 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 15388 | 15388 | Completed | Pending | Pending | 424 |  |  |  | 2026-07-26 | Pending | Pending
425 | 244956 | 425 | 2026-01-19 | 2026-01-18 | 2026-01-29 | 2026-04-19 | 2026-07-26 | BP | BP-152606+607 | 80 | 1192359 | Completed | 816325 | Approved/Printed | 2026-02-16 | 2026-08-13 | NEWCON | 3851 | 2 | Madinat Khalifa(North)(32) | 236 | 236 | 0 | 0 | 0 | 0 | 224 | 224 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 4 | 4 | 3 | 3 | 0 | 0 | 0 |  | 0 | 0 | 29648 | 29648 | Invoiced | Invoiced | 13 | 425 |  |  |  | 2026-07-20 | completed | Invoiced
426 | 244958 | 426 | 2026-03-26 | 2026-03-25 | 2026-04-05 | 2026-06-24 | 2026-08-09 | OL | OL-F1-1294 | 80 | 1192477 | Completed | 819889 | Approved/Printed | 2026-04-18 | 2026-08-22 | NEWCON | 1293 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 94 | 94 | 0 | 0 | 0 | 0 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 8616 | 8616 | Completed | Pending | Pending | 426 |  |  |  | 2026-08-03 | completed | Pending
427 | 245015 | 427 | 2026-01-20 | 2026-01-19 | 2026-01-30 | 2026-04-20 | 2026-07-14 | BP | BP152640 | 80 | 1192766 | Completed | 816323 | Approved/Printed | 2026-02-19 | 2026-08-13 | AL MORAQUIB | 13438 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 170 | 170 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 10890 | 10890 | Invoiced | Invoiced | 13 | 427 |  |  |  | 2026-07-08 | Completed | Invoiced
428 | 245022 | 428 | 2026-01-20 | 2026-01-19 | 2026-01-30 | 2026-04-20 | 2026-07-29 | BP | BP152647 | 80 | 1192774 | Completed | 816324 | Approved/Printed | 2026-02-25 | 2026-08-13 | NEWCON | 2798 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 66 | 66 | 0 | 0 | 0 | 0 | 55 | 55 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 7785 | 7785 | Invoiced | Invoiced | 13 | 428 |  |  |  | 2026-07-21 | Completed | Invoiced
429 | 245024 | 429 | 2026-01-20 | 2026-01-19 | 2026-01-30 | 2026-04-20 | 2026-07-05 | BP | BP152678 | 80 | 1192777 | Completed | 816323 | Approved/Printed | 2026-02-19 | 2026-08-13 | NEWCON | 21335 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 122 | 122 | 0 | 0 | 0 | 0 | 18 | 18 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9521 | 9521 | Completed | Pending | Pending | 429 |  |  |  | 2026-06-30 | Pending | Pending
430 | 245025 | 430 | 2026-01-20 | 2026-01-19 | 2026-01-30 | 2026-04-20 | 2026-07-13 | BP | BP152731 | 80 | 1192809 | Completed | 816324 | Approved/Printed | 2026-02-25 | 2026-08-13 | BD DHAKA | 2810 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 124 | 124 | 0 | 0 | 0 | 0 | 106 | 106 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14722 | 14722 | Invoiced | Invoiced | 13 | 430 |  |  |  | 2026-07-09 | Completed | Invoiced
431 | 245026 | 431 | 2026-01-20 | 2026-01-19 | 2026-01-30 | 2026-04-20 | 2026-07-27 | BP | BP152603 | 80 | 1192813 | Completed | 816325 | Approved/Printed | 2026-02-16 | 2026-08-13 | NEWCON | 4025 | 1 | Madinat Khalifa(North)(32) | 75 | 75 | 0 | 0 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9425 | 9425 | Completed | Pending | Pending | 431 |  |  |  | 2026-07-22 | Pending | Pending
432 | 245111 | 432 | 2026-01-21 | 2026-01-20 | 2026-01-31 | 2026-03-21 | 2026-04-30 | MOC | IN-113016 MOC-232382 | 49 | 1193226 | Completed | 817031 | Approved/Printed | 2026-03-09 | 2026-08-13 | NEWCON | 39300 | 1 | Al Kheesa (70 ) | 108 | 108 | 0 | 0 | 0 | 0 | 60 | 60 | 40 | 40 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 15600 | 15600 | Invoiced | Invoiced | 13 | 432 |  |  |  | 2026-05-07 | Completed | Invoiced
433 | 245113 | 433 | 2026-01-21 | 2026-01-20 | 2026-01-31 | 2026-04-21 | 2026-09-12 | BP | BP 152758+152759 | 80 | 1193229 | LIVE TDP | Hold | Hold | Pending | Pending | NEWCON | 19278 | 2 | Umm Slal/Al Kharaitiyat (71 ) | 31 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2 |  | 2 |  | 2 |  | 0 | 0 | 0 |  | 0 | 0 | 4420 | 0 | Hold | Pending | Pending | 433 |  |  |  |  | Pending | Pending
434 | 245114 | 434 | 2026-02-16 | 2026-02-15 | 2026-02-26 | 2026-04-16 | 2026-04-28 | MOC | MOC-250106 | 49 | 1193230 | Completed | 816324 | Approved/Printed | 2026-02-25 | 2026-08-13 | Smart Elevation | 38181 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 54 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 5940 | 5940 | Invoiced | Invoiced | 10 | 434 |  |  |  | 2026-04-27 | Completed | Invoiced
435 | 245287 | 435 | 2026-01-25 | 2026-01-24 | 2026-02-04 | 2026-03-25 | 2026-02-05 | MOC | C-1263406 (MSA-18037563) | 49 | 1194430 | Completed | 816164 | Approved/Printed | 2026-01-29 | 2026-02-13 | NEWCON | 32699 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 208 | 208 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 3 | 3 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 15412 | 15412 | Invoiced | Invoiced | 7 | 435 |  |  |  | 2026-02-01 | Completed | Invoiced
436 | 245289 | 436 | 2026-01-25 | 2026-01-24 | 2026-02-04 | 2026-04-25 | 2026-09-12 | BP | BP 152855 | 80 | 1194432 | Hold | Pending | Waiting for Proposal Revision | Pending | Pending | NEWCON | 4311 | 1 | Madinat Khalifa(North)(32) | 173 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 11660 | 0 | Hold | Pending | Pending | 436 |  |  |  |  | Pending | Pending
437 | 245290 | 437 | 2026-07-06 | 2026-07-05 | 2026-07-16 | 2026-10-06 | 2026-09-12 | BP | BP#N/2025/5019 (PIN71593674) | 82 | 1194433 | Not Clear | Hold | Hold | Pending | Pending | NEWCON | 40840 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 239 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 16197 | 0 | Hold | Pending | Pending | 437 |  |  |  |  | Pending | Pending
438 | 245219 | 438 | 2026-01-26 | 2026-01-25 | 2026-02-05 | 2026-04-26 | 2026-09-12 | OL | OL-F2-2348 | 80 | 1194112 | WORK IN PROGRESS | 819880 | Approved/Printed | 2026-04-06 | 2026-09-17 | NEWCON | 2348 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1590 | 0 | WORK IN PROGRESS | Pending | Pending | 438 |  |  |  |  | Pending | Pending
439 | 245220 | 439 | 2026-01-26 | 2026-01-25 | 2026-02-05 | 2026-04-26 | 2026-08-12 | OL | OL-F8-1296 | 80 | 1194116 | Completed | 819880 | Approved/Printed | 2026-04-06 | 2026-09-17 | NEWCON | 1296 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 10 | 10 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3082 | 3082 | Completed | Pending | Pending | 439 |  |  |  | 2026-08-05 | Completed | Pending
440 | 245223 | 440 | 2026-01-26 | 2026-01-25 | 2026-02-05 | 2026-04-26 | 2026-09-12 | OL | OL-F3-12489 | 80 | 1194121 | Pending | 818548 | Approved/Expired | 2026-03-16 | 2026-08-27 | NEWCON | 12489 | 1 | Al Khor (74 ) | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1590 | 0 | Pending | Pending | Pending | 440 |  |  |  |  | Pending | Pending
441 | 245266 | 441 | 2026-01-26 | 2026-01-25 | 2026-02-05 | 2026-04-26 | 2026-08-01 | OL | OL-F2F4-17781 | 80 | 1194315 | Completed | 819880 | Approved/Printed | 2026-04-06 | 2026-09-17 | NEWCON | 17781 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 15 | 15 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3460 | 3460 | Invoiced | Invoiced | 13 | 441 |  |  |  | 2026-07-23 | Completed | Invoiced
442 | 245272 | 442 | 2026-01-26 | 2026-01-25 | 2026-02-05 | 2026-04-26 | 2026-09-12 | OL | OL-TX2-13547 | 80 | 1194343 | Pending | 819880 | Approved/Printed | 2026-04-06 | 2026-09-17 | NEWCON | 37398 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 75 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 3 |  | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7410 | 0 | Pending | Pending | Pending | 442 |  |  |  |  | Pending | Pending
443 | 245285 | 443 | 2026-01-26 | 2026-01-25 | 2026-02-05 | 2026-04-26 | 2026-09-12 | OL | OL-TX1-35715 | 80 | 1194407 | Not Clear | Hold | Hold | Pending | Pending | NEWCON | 26022 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 137 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 9750 | 0 | Hold | Pending | Pending | 443 |  |  |  |  | Pending | Pending
444 | 245313 | 444 | 2026-01-26 | 2026-01-25 | 2026-02-05 | 2026-04-26 | 2026-09-12 | OL | OL-F3-10445 | 80 | 1194581 | Pending | 817030 | Approved/Expired | 2026-02-22 | 2026-08-13 | NEWCON | 10445 | 1 | Al Khor (74 ) | 24 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2970 | 0 | Pending | Pending | Pending | 444 |  |  |  |  | Pending | Pending
445 | 245326 | 445 | 2026-01-26 | 2026-01-25 | 2026-02-05 | 2026-04-26 | 2026-09-12 | OL | OL-F6-12490 | 80 | 1194596 | Pending | 817030 | Approved/Expired | 2026-02-22 | 2026-08-13 | NEWCON | 25902 | 1 | Al Khor (74 ) | 5 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 2 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2625 | 0 | Pending | Pending | Pending | 445 |  |  |  |  | Pending | Pending
446 | 245394 | 446 | 2026-01-26 | 2026-01-25 | 2026-02-05 | 2026-04-26 | 2026-09-12 | OL | OL-TX3F15-21563 | 80 | 1194785 | Pending | 817030 | Approved/Expired | 2026-02-22 | 2026-08-13 | NEWCON | 10319 | 1 | Al Khor (74 ) | 180 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 2 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 13020 | 0 | Pending | Pending | Pending | 446 |  |  |  |  | Pending | Pending
447 | 245401 | 447 | 2026-01-26 | 2026-01-25 | 2026-02-05 | 2026-03-26 | 2026-04-09 | MOC | IN-114247 MOC-216817 | 49 | 1194797 | Completed | 816610 | Approved/Printed | 2026-02-19 | 2026-08-13 | NEWCON | 10761 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 0 | 0 | 2 | 2 | 0 | 0 | 5150 | 5150 | Invoiced | Invoiced | 10 | 447 |  |  |  | 2026-04-08 | Completed | Invoiced
448 | 245403 | 448 | 2026-01-26 | 2026-01-25 | 2026-02-05 | 2026-04-26 | 2026-08-03 | BP | BP#N/2025/8532 (PIN51468036) | 80 | 1194894 | Completed | 817644/ 832426 | Approved/Printed | 2026-03-09 | 2026-08-20 | NEWCON | 12255 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 84 | 84 | 0 | 0 | 32 | 32 | 30 | 30 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8616 | 8616 | Completed | Pending | Pending | 448 |  |  |  | 2026-07-02 | Completed | Pending
449 | 245404 | 449 | 2026-01-26 | 2026-01-25 | 2026-02-05 | 2026-04-26 | 2026-07-23 | BP | BP 138898 | 80 | 1194920 | Completed | 817644 | Approved/Printed | 2026-03-09 | 2026-08-20 | AL MORAQUIB | 15486 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 105 | 105 | 0 | 0 | 0 | 0 | 21 | 21 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 8837 | 8837 | Completed | Pending | Pending | 449 |  |  |  | 2026-07-16 | Pending | Pending
450 | 245405 | 450 | 2026-01-26 | 2026-01-25 | 2026-02-05 | 2026-04-26 | 2026-08-10 | BP | BP 152923 | 80 | 1194922 | Completed | 817644 | Approved/Printed | 2026-03-09 | 2026-08-20 | NEWCON | 19597 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 58 | 58 | 0 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 4 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8250 | 8250 | Completed | Pending | Pending | 450 |  |  |  | 2026-08-04 | Completed | Pending
451 | 245459 | 451 | 2026-01-27 | 2026-01-26 | 2026-02-06 | 2026-04-27 | 2026-07-23 | BP | BP-M/2025/2612 (PIN71850102) | 80 | 1195212 | Completed | 816837 | Approved/Printed | 2026-02-15 | 2026-08-13 | NEWCON | 31544 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 33 | 33 | 0 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4990 | 4990 | Completed | Pending | Pending | 451 |  |  |  | 2026-07-15 | Pending | Pending
452 | 245466 | 452 | 2026-01-27 | 2026-01-26 | 2026-02-06 | 2026-04-27 | 2026-09-12 | BP | BP 153020 | 80 | 1195246 | Pending | 816837 | Approved/Expired | 2026-02-15 | 2026-08-13 | NEWCON | 19836 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 73 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 5660 | 0 | Pending | Pending | Pending | 452 |  |  |  |  | Pending | Pending
453 | 245477 | 453 | 2026-02-04 | 2026-02-03 | 2026-02-14 | 2026-04-04 | 2026-04-25 | MOC | IN-114245 MOC-234614 | 49 | 1195255 | Completed | 817305 | Approved/Printed | 2026-03-01 | 2026-08-13 | SMART ELEVATION | 9920 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 340 | 340 | 0 | 0 | 0 | 0 | 320 | 320 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 2 | 2 | 4 | 4 | 4 | 4 | 0 | 0 | 1 | 1 |  |  | 43440 | 43440 | Invoiced | Invoiced | 12 | 453 |  |  |  | 2026-04-29 | Completed | Invoiced
454 | 245484 | 454 | 2026-01-27 | 2026-01-26 | 2026-02-06 | 2026-04-27 | 2026-04-18 | BP | BP 153030 | 80 | 1195263 | Completed | 817644 | Approved/Printed | 2026-03-09 | 2026-08-20 | KAR | 26567 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 296 | 296 | 0 | 0 | 0 | 0 | 111 | 111 | 2 | 2 | 0 | 0 | 3 | 3 | 0 | 0 | 2 | 2 | 4 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 28057 | 28057 | Invoiced | Invoiced | 10 | 454 |  |  |  | 2026-04-07 | Completed | Invoiced
455 | 245490 | 455 | 2026-01-27 | 2026-01-26 | 2026-02-06 | 2026-04-27 | 2026-09-12 | BP | BP 152989 | 80 | 1195264 | WORK IN PROGRESS | 817644 | Approved/Printed | 2026-03-09 | 2026-08-20 | NEWCON | 13966 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 63 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 5060 | 0 | WORK IN PROGRESS | Pending | Pending | 455 |  |  |  |  | Pending | Feeder Mismatch(Job Not Completed)
456 | 245491 | 456 | 2026-01-27 | 2026-01-26 | 2026-02-06 | 2026-04-27 | 2026-07-26 | BP | BP 153007 | 80 | 1195270 | Completed | 816837 | Approved/Printed | 2026-02-15 | 2026-08-13 | NEWCON | 26011 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 47 | 47 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 4160 | 4160 | Invoiced | Invoiced | 13 | 456 |  |  |  | 2026-07-16 | Completed | Invoiced
457 | 245642 | 457 | 2026-01-29 | 2026-01-28 | 2026-02-08 | 2026-03-29 | 2026-05-03 | MOC | C-70145 MSA-18036568 | 49 | 1196091 | Completed | 816610 | Approved/Printed | 2026-02-19 | 2026-08-13 | NEWCON | 2663 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 35 | 35 | 0 | 0 | 0 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 5935 | 5935 | Invoiced | Invoiced | 11 | 457 |  |  |  | 2026-04-20 | Completed | Invoiced
458 | 245714 | 458 | 2026-05-21 | 2026-05-20 | 2026-05-31 | 2026-07-21 | 2026-06-14 | MOC | MOC-249483+BP-153265+153264 | 51 | 1196903 | Completed | 817994 | Approved/Printed | 2026-03-11 | 2026-08-27 | NEWCON | 16167 | 2 | Umm Slal/Al Kharaitiyat (71 ) | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 7840 | 7840 | Invoiced | Invoiced | 13 | 458 |  |  |  | 2026-06-07 | Completed | Invoiced
459 | 245716 | 459 | 2026-04-26 | 2026-04-25 | 2026-05-06 | 2026-06-26 | 2026-05-19 | MOC | IN-114815 MOC-250546+47 | 51 | 1196910 | Completed | 817645 | Approved/Printed | 2026-03-04 | 2026-08-20 | NEWCON | 0117 | 2 | Madinat Khalifa(South)(34) | 176 | 176 | 0 | 0 | 0 | 0 | 176 | 176 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 0 | 0 | 2 | 2 | 0 | 0 | 23582 | 23582 | Invoiced | Invoiced | 11 | 459 |  |  |  | 2026-05-10 | Completed | Invoiced
460 | 245719 | 460 | 2026-02-01 | 2026-01-31 | 2026-02-11 | 2026-05-01 | 2026-09-12 | BP | BP-N/2025/7618(PIN34350015) | 79 | 1196923 | Pending | 817645 | Approved/Expired | 2026-03-04 | 2026-08-20 | NEWCON | 15275 | 1 | Madinat Khalifa(South)(34) | 83 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 6260 | 0 | Pending | Pending | Pending | 460 |  |  |  |  | Pending | Pending
461 | 245720 | 461 | 2026-02-12 | 2026-02-11 | 2026-02-22 | 2026-04-12 | 2026-02-21 | MOC | IN-114462 MOC-250709 | 49 | 1196926 | Completed | 817659 | Approved/Printed | 2026-02-21 | 2026-08-20 | NEWCON | 33718 | 1 | New District Of Doha 67(67) | 40 | 40 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 1 | 1 | 2 | 2 | 0 | 0 | 0 |  | 1 | 1 | 7120 | 7120 | Invoiced | Invoiced | 7 | 461 |  |  |  | 2026-02-01 | Completed | Invoiced
462 | 245721 | 462 | 2026-02-01 | 2026-01-31 | 2026-02-11 | 2026-05-01 | 2026-09-12 | BP | BP 153247 | 79 | 1196927 | Pending | 817995 | Approved/Expired | 2026-03-08 | 2026-08-27 | NEWCON | 2812 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 85 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 6380 | 0 | Pending | Pending | Pending | 462 |  |  |  |  | Pending | Pending
463 | 245723 | 463 | 2026-02-01 | 2026-01-31 | 2026-02-11 | 2026-05-01 | 2026-09-12 | BP | BP 153210 | 79 | 1196929 | WORK IN PROGRESS | 817994 | Approved/Expired | 2026-03-11 | 2026-08-27 | NEWCON | 3133 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1290 | 0 | WORK IN PROGRESS | Pending | Pending | 463 |  |  |  |  | Pending | Pending
464 | 245726 | 464 | 2026-02-01 | 2026-01-31 | 2026-02-11 | 2026-05-01 | 2026-06-28 | BP | BP 153100 | 79 | 1196932 | Completed | 817994 | Approved/Printed | 2026-03-11 | 2026-08-27 | NEWCON | 9743 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1392 | 1392 | Invoiced | Invoiced | 13 | 464 |  |  |  | 2026-06-28 | Completed | Invoiced
465 | 245804 | 465 | 2026-02-02 | 2026-02-01 | 2026-02-12 | 2026-05-02 | 2026-07-29 | BP | BP#CE/2025/545 (PIN51468032AA) | 79 | 1197267 | Completed | 817995 | Approved/Printed | 2026-03-08 | 2026-08-27 | NEWCON | 27551 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 284 | 284 | 0 | 0 | 0 | 0 | 47 | 47 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 21549 | 21549 | Completed | Pending | Pending | 465 |  |  |  | 2026-07-26 | Pending | Pending
466 | 245805 | 466 | 2026-02-08 | 2026-02-07 | 2026-02-18 | 2026-04-08 | 2026-02-16 | MOC | IN-114279 MOC-250585+6+7+8 | 49 | 1197276 | Completed | 817543 | Approved/Printed | 2026-02-14 | 2026-03-01 | NEWCON | 12026 | 4 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 45 | 45 | 0 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 1 | 1 | 2 | 2 | 6 | 6 | 0 | 0 | 4 | 4 | 0 | 0 | 10181 | 10181 | Invoiced | Invoiced | 7 | 466 |  |  |  | 2026-02-01 | Completed | Invoiced
467 | 245806 | 467 | 2026-04-01 | 2026-03-31 | 2026-04-11 | 2026-06-01 | 2026-05-06 | MOC | IN-114861 MOC-250918 | 51 | 1197309 | Completed | 817997 | Approved/Printed | 2026-03-04 | 2026-08-27 | BD DHAKA | 16542 | 1 | Al Duhail South (31 ) | 214 | 214 | 0 | 0 | 0 | 0 | 198 | 198 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 26526 | 26526 | Invoiced | Invoiced | 11 | 467 |  |  |  | 2026-05-05 | Completed | Invoiced
468 | 246052 | 468 | 2026-02-05 | 2026-02-04 | 2026-02-15 | 2026-04-05 | 2026-04-16 | MOC | C-151990+92A(MSA-18037489+88) | 49 | 1198609 | Completed | 819013 | Approved/Printed | 2026-03-10 | 2026-09-03 | NEWCON | 3350 | 2 | New District Of Doha 66(66) | 78 | 78 | 0 | 0 | 0 | 0 | 35 | 35 | 12 | 12 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 0 | 0 | 2 | 2 | 0 | 0 | 11215 | 11215 | Invoiced | Invoiced | 10 | 468 |  |  |  | 2026-04-12 | Completed | Invoiced
469 | 246053 | 469 | 2026-02-05 | 2026-02-04 | 2026-02-15 | 2026-04-05 | 2026-03-25 | MOC | IN-114405 MOC-247651 | 49 | 1198610 | Completed | 817646 | Approved/Printed | 2026-03-09 | 2026-08-20 | BD SUB | 25391 | 1 | Al Kheesa (70 ) | 224 | 224 | 0 | 0 | 0 | 0 | 210 | 210 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 27800 | 27800 | Invoiced | Invoiced | 8 | 469 |  |  |  | 2026-03-16 | Completed | Invoiced
470 | 246121 | 470 | 2026-02-08 | 2026-02-07 | 2026-02-18 | 2026-04-08 | 2026-04-16 | MOC | IN-114423 MOC-250818 | 49 | 1199226 | Completed | 817646 | Approved/Printed | 2026-03-09 | 2026-08-20 | NEWCON | 4957 | 1 | Al Kheesa (70 ) | 80 | 80 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 11200 | 11200 | Invoiced | Invoiced | 11 | 470 |  |  |  | 2026-04-15 | Completed | Invoiced
471 | 246291 | 471 | 2026-02-11 | 2026-02-10 | 2026-02-21 | 2026-04-12 | 2026-04-12 | MOC | C-189547 MSA-18037525 | 50 | 1200210 | Completed | 817807 | Approved/Printed | 2026-03-03 | 2026-08-20 | NEWCON | 3427 | 1 | New District Of Doha 66(66) | 158 | 158 | 0 | 0 | 0 | 0 | 66 | 66 | 3 | 3 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 17407 | 17407 | Invoiced | Invoiced | 11 | 471 |  |  |  | 2026-04-12 | Completed | Invoiced
472 | 246294 | 472 | 2026-02-11 | 2026-02-10 | 2026-02-21 | 2026-04-12 | 2026-04-26 | MOC | IN#114368 MOC#247987 | 50 | 1200237 | Completed | 818120 | Approved/Printed | 2026-03-09 | 2026-08-27 | NEWCON | 1908 | 1 | Kulaib (35 ) | 40 | 40 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 175 | 175 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 31260 | 31260 | Completed | Pending | Pending | 472 |  |  |  | 2026-04-21 | Pending | Pending
473 | 246295 | 473 | 2026-02-11 | 2026-02-10 | 2026-02-21 | 2026-04-12 | 2026-05-04 | MOC | C-1494731 msa-18035899 | 50 | 1200238 | Completed | 817825 | Approved/Printed | 2026-03-26 | 2026-09-03 | NEWCON | 30465 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 183 | 183 | 0 |  | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 13960 | 13960 | Completed | Pending | Pending | 473 |  |  |  | 2026-04-21 | Pending | Pending
474 | 246302 | 474 | 2026-02-12 | 2026-02-11 | 2026-02-22 | 2026-05-13 | 2026-09-12 | BP | BP#153037 | 80 | 1200415 | Pending | 818549 | Approved/Expired | 2026-03-29 | 2026-08-27 | AL MORAQUIB | 4106 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 140 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10135 | 0 | Pending | Pending | Pending | 474 |  |  |  |  | Pending | Pending
475 | 246305 | 475 | 2026-02-12 | 2026-02-11 | 2026-02-22 | 2026-05-13 | 2026-05-02 | BP | BP#M/2025/1559 PIN#51280125 | 80 | 1200430 | Completed | 819492 | Approved/Printed | 2026-03-16 | 2026-09-17 | BD DHAKA | 0027 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 400 | 400 | 60 | 60 | 0 | 0 | 300 | 300 | 0 | 0 | 270 | 270 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89700 | 89700 | Invoiced | Invoiced | 11 | 475 |  |  |  | 2026-04-21 | Completed | Invoiced
476 | 246312 | 476 | 2026-02-12 | 2026-02-11 | 2026-02-22 | 2026-05-13 | 2026-09-12 | BP | BP#N-2025-8121 PIN#34540023 | 80 | 1200437 | Hold | Pending | Waiting for Proposal Revision | Pending | Pending | NEWCON | 22222 | 1 | Madinat Khalifa(South)(34) | 78 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6415 | 0 | Hold | Pending | Pending | 476 |  |  |  |  | Pending | Pending
477 | 246430 | 477 | 2026-02-15 | 2026-02-14 | 2026-02-25 | 2026-04-15 | 2026-04-30 | MOC | IN-113778 MOC-205630 | 49 | 1201367 | Completed | 818752 | Approved/Printed | 2026-03-10 | 2026-09-10 | NEWCON | 3524 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 71 | 71 | 0 | 0 | 0 | 0 | 71 | 71 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 10147 | 10147 | Invoiced | Invoiced | 11 | 477 |  |  |  | 2026-04-28 | Completed | Invoiced
478 | 246460 | 478 | 2026-02-16 | 2026-02-15 | 2026-02-26 | 2026-05-17 | 2026-08-20 | OL | OL-F4F7-12522 | 80 | 1201589 | Completed | 819493 | Approved/Printed | 2026-04-05 | 2026-09-17 | NEWCON | 12522 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 177 | 177 | 0 | 0 | 0 | 0 | 177 | 177 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 22949 | 22949 | Completed | Pending | Pending | 478 |  |  |  | 2026-08-20 | Pending | Pending
479 | 246532 | 479 | 2026-02-17 | 2026-02-16 | 2026-02-27 | 2026-05-18 | 2026-09-12 | OL | OL-F6-2534 | 80 | 1201841 | Pending | 818744 | Approved/Printed | 2026-03-12 | 2026-09-10 | NEWCON | 17350 | 1 | Bin Omran/Al Hitmi Al Jadeed (37 ) | 75 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 3 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6985 | 0 | Pending | Pending | Pending | 479 |  |  |  |  | Pending | Pending
480 | 246546 | 480 | 2026-02-17 | 2026-02-16 | 2026-02-27 | 2026-05-18 | 2026-09-12 | OL | OL-F5+F6-3878 | 80 | 1201912 | Pending | 819493 | Approved/Printed | 2026-04-05 | 2026-09-17 | NEWCON | 3878 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 36 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 6 |  | 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7140 | 0 | Pending | Pending | Pending | 480 |  |  |  |  | Pending | Pending
481 | 246545 | 481 | 2026-02-17 | 2026-02-16 | 2026-02-27 | 2026-05-18 | 2026-09-12 | OL | OL-F6-12410 | 80 | 1201914 | Pending | 819493 | Approved/Printed | 2026-04-05 | 2026-09-17 | NEWCON | 12410 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 121 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 2 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 9480 | 0 | Pending | Pending | Pending | 481 |  |  |  |  | Pending | Pending
482 | 246561 | 482 | 2026-02-22 | 2026-02-21 | 2026-03-04 | 2026-04-22 | 2026-04-27 | MOC | IN-114496+564 MOC-247578+488 | 49 | 1202007 | Completed | 818745 | Approved/Printed | 2026-03-14 | 2026-09-10 | NEWCON | 13445 | 1 | Al Kheesa (70 ) | 101 | 101 |  |  |  |  | 3 | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8351 | 8351 | Completed | Pending | Pending | 482 |  |  |  | 2026-04-23 | Pending | Pending
483 | 246578 | 483 | 2026-02-17 | 2026-02-16 | 2026-02-27 | 2026-05-18 | 2026-09-12 | OL | OL-F10-9820 | 80 | 1202067 | Pending | 819493 | Approved/Printed | 2026-04-05 | 2026-09-17 | NEWCON | 18211 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 44 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 2 |  | 2 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4820 | 0 | Pending | Pending | Pending | 483 |  |  |  |  | Pending | Pending
484 | 246570 | 484 | 2026-02-17 | 2026-02-16 | 2026-02-27 | 2026-05-18 | 2026-09-12 | OL | OL-F9F12-1648 | 80 | 1202025 | ROW | RO NA | ROW | Pending | Pending | NEWCON | 1648 | 1 | New District Of Doha 67(67) | 80 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 2 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7020 | 0 | Pending | Pending | Pending | 484 |  |  |  |  | Pending | Pending
485 | 246615 | 485 | 2026-02-17 | 2026-02-16 | 2026-02-27 | 2026-04-17 | 2026-04-18 | MOC | IN-114509 MOC-249440 | 49 | 1202172 | Completed | 818861 | Approved/Printed | 2026-03-09 | 2026-09-11 | NEWCON | 25154 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 68 | 68 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 6222 | 6222 | Invoiced | Invoiced | 11 | 485 |  |  |  | 2026-04-19 | Completed | Invoiced
486 | 246618 | 486 | 2026-06-15 | 2026-06-14 | 2026-06-25 | 2026-08-15 | 2026-09-06 | MOC | IN-116020 MOC-250148 | 51 | 1202176 | Completed | 819494 | Approved/Printed | 2026-03-12 | 2026-09-17 | NEWCON | 1991 | 1 | Al Soudan South/Al Aziziya/Al (55 ) | 63 | 63 | 0 | 0 | 0 | 0 | 63 | 63 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 9181 | 9181 | Completed | Pending | Pending | 486 |  |  |  | 2026-06-24 | Pending | Pending
487 | 246619 | 487 | 2026-02-17 | 2026-02-16 | 2026-02-27 | 2026-05-17 | 2026-08-18 | BP | BP153092 | 79 | 1202177 | Completed | 819495 | Approved/Printed | 2026-03-24 | 2026-09-17 | NEWCON | 2089 | 1 | Al Rayyan Al Jadeed/Muaither N(53 ) | 44 | 44 | 0 | 0 | 0 | 0 | 28 | 28 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 0 |  | 0 | 0 | 5556 | 5556 | Completed | Pending | Pending | 487 |  |  |  | 2026-08-11 | Completed | Pending
488 | 246650 | 488 | 2026-02-18 | 2026-02-17 | 2026-02-28 | 2026-05-19 | 2026-08-23 | OL | OL-F1-0140 | 80 | 1202424 | Completed | 819496 | Approved/Printed | 2026-03-24 | 2026-09-17 | NEWCON | 0140 | 1 | Madinat Khalifa(South)(34) | 11 | 11 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 4296 | 4296 | Completed | Pending | Pending | 488 |  |  |  | 2026-08-24 | Pending | Pending
489 | 246669 | 489 | 2026-02-18 | 2026-02-17 | 2026-02-28 | 2026-05-19 | 2026-09-12 | OL | ol-f3f7-14948 | 80 | 1202435 | Pending | 819496 | Approved/Printed | 2026-03-24 | 2026-09-17 | NEWCON | 22762 | 1 | Madinat Khalifa(South)(34) | 60 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 3 |  | 4 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7120 | 0 | Pending | Pending | Pending | 489 |  |  |  |  | Pending | Pending
490 | 246685 | 490 | 2026-02-18 | 2026-02-17 | 2026-02-28 | 2026-04-18 | 2026-04-15 | MOC | IN-113699 MOC-242299 | 49 | 1202490 | Completed | 818862 | Approved/Printed | 2026-03-24 | 2026-09-11 | Smart Elevation | 0124 | 1 | Madinat Khalifa(South)(34) | 412 | 412 | 0 | 0 | 0 | 0 | 395 | 395 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 51310 | 51310 | Invoiced | Invoiced | 10 | 490 |  |  |  | 2026-04-09 | Completed | Invoiced
491 | 246686 | 491 | 2026-02-18 | 2026-02-17 | 2026-02-28 | 2026-05-18 | 2026-08-04 | BP | BP153157 | 79 | 1202491 | Completed | 818747 | Approved/Printed | 2026-03-15 | 2026-09-10 | NEWCON | 37661 | 1 | New District Of Doha 67(67) | 107 | 107 | 0 | 0 | 0 | 0 | 107 | 107 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 13209 | 13209 | Completed | Pending | Pending | 491 |  |  |  | 2026-07-30 | Completed | Pending
492 | 246687 | 492 | 2026-02-18 | 2026-02-17 | 2026-02-28 | 2026-05-18 | 2026-07-27 | BP | BP-N/2025/3642(PIN31170075) | 79 | 1202492 | Completed | 819497 | Approved/Printed | 2026-03-24 | 2026-09-17 | NEWCON | 29267 | 1 | Al Duhail South (31 ) | 23 | 23 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2965 | 2965 | Completed | Pending | Pending | 492 |  |  |  | 2026-07-20 | Completed | Pending
493 | 246737 | 493 | 2026-02-19 | 2026-02-18 | 2026-03-01 | 2026-05-19 | 2026-03-31 | BP | BP#N/2025/4843(PIN74050444) | 79 | 1202881 | Completed | 818548 | Approved/Printed | 2026-03-16 | 2026-08-27 | KAR | 11416 | 1 | Al Khor (74 ) | 191 | 191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 12740 | 12740 | Invoiced | Invoiced | 9 | 493 |  |  |  | 2026-03-16 | Completed | Invoiced
494 | 246841 | 494 | 2026-02-23 | 2026-02-22 | 2026-03-05 | 2026-05-24 | 2026-09-12 | BP | BP#N/2025/8191 PIN#31240159 | 80 | 1204080 | Pending | 819497 | Approved/Printed | 2026-03-24 | 2026-09-17 | AL MORAQUIB | 29272 | 1 | Al Duhail South (31 ) | 220 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 14935 | 0 | Pending | Pending | Pending | 494 |  |  |  |  | Pending | Pending
495 | 246845 | 495 | 2026-02-23 | 2026-02-22 | 2026-03-05 | 2026-05-24 | 2026-09-12 | BP | BP#N/2025/3188 PIN#51400091 | 80 | 1204113 | Hold | Pending | Waiting for Proposal Revision | Pending | Pending | NEWCON | 16149 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 400 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 2 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25795 | 0 | Pending | Pending | Pending | 495 |  |  |  |  | Pending | Pending
496 | 246849 | 496 | 2026-02-24 | 2026-02-23 | 2026-03-06 | 2026-05-25 | 2026-09-12 | BP | BP146535 | 80 | 1204403 | Pending | 819502 | Approved/Printed | 2026-03-24 | 2026-09-17 | BD DHAKA | 15492 | 1 | New District Of Doha 66(66) | 180 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 12535 | 0 | Pending | Pending | Pending | 496 |  |  |  |  | Pending | Pending
497 | 246850 | 497 | 2026-02-24 | 2026-02-23 | 2026-03-06 | 2026-05-25 | 2026-09-12 | BP | BP146520 | 80 | 1204416 | Pending | 819502 | Approved/Printed | 2026-03-24 | 2026-09-17 | NEWCON | 15492 | 1 | New District Of Doha 66(66) | 273 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 2 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 18175 | 0 | Pending | Pending | Pending | 497 |  |  |  |  | Pending | Pending
498 | 246851 | 498 | 2026-02-24 | 2026-02-23 | 2026-03-06 | 2026-05-25 | 2026-09-12 | BP | BP149829 | 80 | 1204423 | Pending | 820336 | Approved/Printed | 2026-03-31 | 2026-09-24 | NEWCON | 1352 | 1 | Madinat Al Shamal/Al Ruwais(79) | 74 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6175 | 0 | Pending | Pending | Pending | 498 |  |  |  |  | Pending | Pending
499 | 246942 | 499 | 2026-02-25 | 2026-02-24 | 2026-03-07 | 2026-04-25 | 2026-04-22 | MOC | IN-114545 MOC-241044 | 49 | 1205078 | Completed | 819503 | Approved/Printed | 2026-04-08 | 2026-09-17 | NEWCON | 20462 | 1 | Madinat Khalifa(North)(32) | 47 | 47 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 7788 | 7788 | Invoiced | Invoiced | 10 | 499 |  |  |  | 2026-04-21 | Completed | Invoiced
500 | 247116 | 500 | 2026-03-09 | 2026-03-08 | 2026-03-19 | 2026-05-09 | 2026-06-01 | MOC | IN-113640 MOC-173901 | 51 | 1206767 | Completed | 820337/ 825964 | Approved/Printed | 2026-04-05 | 2026-09-24 | BD DHAKA | 25908 | 1 | Madinat Al Shamal/Al Ruwais(79) | 182 | 182 | 40 | 40 | 0 | 0 | 60 | 60 | 0 | 0 | 40 | 40 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 25640 | 25640 | Completed | Pending | Pending | 500 |  |  |  | 2026-05-21 | Pending | Pending
501 | 247340 | 501 | 2026-03-15 | 2026-03-14 | 2026-03-25 | 2026-06-15 | 2026-09-12 | BP | BP#150662 | 82 | 1207538 | Pending | 821794 | Approved/Printed | 2026-04-20 | 2026-10-15 | NEWCON | 0131 | 1 | Madinat Khalifa(South)(34) | 420 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 3 |  | 2 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 28175 | 0 | Pending | Pending | Pending | 501 |  |  |  |  | Pending | Pending
502 | 247346 | 502 | 2026-03-15 | 2026-03-14 | 2026-03-25 | 2026-06-15 | 2026-09-12 | BP | BP152373 | 82 | 1207564 | Pending | 821795 | Approved/Printed | 2026-04-11 | 2026-10-08 | NEWCON | 33788 | 1 | Al Kheesa (70 ) | 22 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 2600 |  | Pending | Pending | Pending | 502 |  |  |  |  | Pending | Pending
503 | 247347 | 503 | 2026-03-15 | 2026-03-14 | 2026-03-25 | 2026-06-15 | 2026-08-04 | BP | BP#N/2025/9658 (PIN70132019) | 82 | 1207565 | Completed | 821795 | Approved/Printed | 2026-04-11 | 2026-10-08 | NEWCON | 40937 | 1 | Al Kheesa (70 ) | 67 | 67 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 4710 | 4710 | Completed | Pending | Pending | 503 |  |  |  | 2026-07-29 | Pending | Pending
504 | 247438 | 504 | 2026-03-16 | 2026-03-15 | 2026-03-26 | 2026-05-16 | 2026-04-02 | MOC | IN-111761 MOC-245642 | 51 | 1207765 | Completed | 821734 | Approved/Printed | 2026-03-30 | 2026-04-14 | NEWCON | 0099 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 77 | 77 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 2 | 2 | 6 | 6 | 6 | 6 | 0 | 0 | 1 | 1 | 0 | 0 | 12624 | 12624 | Invoiced | Invoiced | 10 | 504 |  |  |  | 2026-04-05 | Completed | Invoiced
505 | 247475 | 505 | 2026-03-17 | 2026-03-16 | 2026-03-27 | 2026-05-16 | 2026-04-05 | MOC | IN#114483 MOC#250890 | 50 | 1208069 | Completed | 821735 | Approved/Printed | 2026-03-31 | 2026-04-15 | NEWCON | 13470 | 1 | Al Kheesa (70 ) | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 4540 | 4540 | Invoiced | Invoiced | 10 | 505 |  |  |  | 2026-04-05 | Completed | Invoiced
506 | 247476 | 506 | 2026-03-17 | 2026-03-16 | 2026-03-27 | 2026-05-16 | 2026-04-06 | MOC | IN#114788 MOC#246479 | 50 | 1208070 | Completed | 821735 | Approved/Printed | 2026-03-31 | 2026-04-15 | NEWCON | 9714 | 1 | Al Kheesa (70 ) | 29 | 29 | 0 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 5655 | 5655 | Invoiced | Invoiced | 10 | 506 |  |  |  | 2026-04-05 | Completed | Invoiced
507 | 247511 | 507 | 2026-05-19 | 2026-05-18 | 2026-05-29 | 2026-07-06 | 2026-07-08 | MOC+BP | MOC-247458+BP154097 | 38 | 1208338 | Completed | 822460 | Approved/Printed | 2026-04-11 | 2026-10-08 | NEWCON | 10631 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 112 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 9670 | 9670 | Invoiced | Invoiced | 13 | 507 |  |  |  | 2026-06-09 | Completed | Invoiced
508 | 247512 | 508 | 2026-06-07 | 2026-06-06 | 2026-06-17 | 2026-06-16 | 2026-08-27 | MOC | IN#115946 MOC#250726+27 | -1 | 1208339 | Completed | 832427 | Approved/Printed | 2026-08-03 | 2026-09-12 | NEWCON | 16851 | 1 | Kulaib (35 ) | 116 | 116 | 35 | 35 | 0 | 0 | 113 | 113 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 1 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 2 | 21401 | 21401 | Completed | Pending | Pending | 508 |  |  |  | 2026-08-26 | Pending | Pending
508 | 247512 | 508-P2 | 2026-06-07 | 2026-06-06 | 2026-06-17 | 2026-06-16 | 2026-08-27 | MOC | IN#115946 MOC#250726+27 | -1 | 1208339 | Completed | 832427 | Approved/Printed | 2026-08-03 | 2026-09-12 | NEWCON | 16851 | 1 | Kulaib (35 ) | 99 | 99 | 0 | 0 | 0 | 0 | 99 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 5 | 5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 14913 | 14913 | Completed | Pending | Pending | 508 |  |  |  | 2026-08-30 | Pending | Pending
509 | 247513 | 509 | 2026-07-30 | 2026-07-29 | 2026-08-09 | 2026-09-28 | 2026-09-03 | MOC | IN#115580 MOC#250223 | 50 | 1208340 | Completed | 838215/ 841381 | Approved/Printed | 2026-08-09 | 2026-11-14 | NEWCON | 0069 | 1 | Madinat Khalifa(South)(34) | 112 | 112 | 0 | 0 | 0 | 0 | 111 | 111 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 14847 | 14847 | Completed | Pending | Pending | 509 |  |  |  | 2026-09-02 | Pending | Pending
509 | 247513 | 509-P2 | 2026-07-30 | 2026-07-29 | 2026-08-09 | 2026-09-28 | 2026-09-03 | MOC | IN#115580 MOC#250223 | 50 | 1208340 | Completed | 838215/ 841381 | Approved/Printed | 2026-08-09 | 2026-11-14 | NEWCON | 0069 | 1 | Madinat Khalifa(South)(34) | 22 | 22 | 0 | 0 | 0 | 0 | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3954 | 3954 | Completed | Pending | Pending | 509 |  |  |  | 2026-09-02 | Pending | Pending
510 | 247514 | 510 | 2026-03-18 | 2026-03-17 | 2026-03-28 | 2026-06-16 | 2026-09-12 | BP | BP#N/2025/7725 PIN71090260 | 80 | 1208341 | Pending | 821796 | Approved/Printed | 2026-04-11 | 2026-10-08 | NEWCON | 4139 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 53 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 4915 |  | Pending | Pending | Pending | 510 |  |  |  |  | Pending | Pending
511 | 247543 | 511 | 2026-03-24 | 2026-03-23 | 2026-04-03 | 2026-06-22 | 2026-09-12 | OL | OL-F4-0143 | 80 | 1209059 | Not Clear | Hold | Hold | Pending | Pending | NEWCON | 39884 | 1 | Al Markhiya (33 ) | 250 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 2 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 17325 |  | Hold | Pending | Pending | 511 |  |  |  |  | Pending | Pending
512 | 247589 | 512 | 2026-03-25 | 2026-03-24 | 2026-04-04 | 2026-05-25 | 2026-05-03 | MOC | IN-114643 MOC-251294 | 51 | 1209521 | Completed | 822463 | Approved/Printed | 2026-04-11 | 2026-10-08 | NEWCON | 32700 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 11 | 11 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3432 | 3432 | Invoiced | Invoiced | 11 | 512 |  |  |  | 2026-04-22 | Completed | Invoiced
513 | 247737 | 513 | 2026-03-26 | 2026-03-25 | 2026-04-05 | 2026-05-26 | 2026-04-29 | MOC | IN-114804 MOC-250717+18 | 51 | 1210284 | Completed | 821797 | Approved/Printed | 2026-04-16 | 2026-06-20 | NEWCON | 0027 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 376 | 376 | 0 | 0 | 0 | 0 | 366 | 366 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 46232 | 46232 | Invoiced | Invoiced | 12 | 513 |  |  |  | 2026-04-22 | Completed | Invoiced
514 | 247762 | 514 | 2026-03-29 | 2026-03-28 | 2026-04-08 | 2026-06-27 | 2026-04-06 | BP | BP#150946+ 150947 | 80 | 1210714 | Completed | 810031 | Approved/Printed | 2025-12-11 | 2026-06-04 | NEWCON | 10632 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 185 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 11790 | 11790 | Invoiced | Invoiced | 10 | 514 |  |  |  | 2026-03-30 | Completed | Invoiced
515 | 247837 | 515 | 2026-03-29 | 2026-03-28 | 2026-04-08 | 2026-06-29 | 2026-09-12 | BP | BP-N/2023/7633 (PIN27370019) | 82 | 1211106 | Pending | 822464 | Approved/Printed | 2026-04-18 | 2026-10-15 | NEWCON | 2270 | 1 | Umm Ghuwailina(27) | 194 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 12920 |  | Pending | Pending | Pending | 515 |  |  |  |  | Pending | Pending
516 | 247838 | 516 | 2026-03-30 | 2026-03-29 | 2026-04-09 | 2026-06-28 | 2026-09-12 | OL | OL-F4-10032 | 80 | 1211200 | Cancelled | 822614 | Approved/Printed | 2026-04-18 | 2026-10-15 | NEWCON | 10032 | 1 | New District Of Doha 67(67) | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1392 | 1392 | Cancelled | Cancelled | Cancelled | 516 |  |  |  | 2026-08-18 | Cancelled | Job Combine With CWR-478
517 | 247871 | 517 | 2026-03-30 | 2026-03-29 | 2026-04-09 | 2026-06-28 | 2026-08-19 | OL | OL-F6-9728 | 80 | 1211340 | Completed | 822614 | Approved/Printed | 2026-04-18 | 2026-10-15 | NEWCON | 9728 | 1 | New District Of Doha 67(67) | 12 | 12 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3374 | 3374 | Completed | Pending | Pending | 517 |  |  |  | 2026-08-19 | Completed | Pending
518 | 247916 | 518 | 2026-03-31 | 2026-03-30 | 2026-04-10 | 2026-06-30 | 2026-09-12 | BP | BP152070 | 81 | 1211715 | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NEWCON | 26102 | 1 | Al Kheesa (70 ) | 33 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 3837 |  | Cancelled | Cancelled | Cancelled | 518 |  |  |  |  | Cancelled | Cancelled
519 | 247969 | 519 | 2026-03-31 | 2026-03-30 | 2026-04-10 | 2026-05-31 | 2026-05-10 | MOC | IN-114827 MOC-251631 | 51 | 1211918 | Completed | 823136 | Approved/Printed | 2026-04-18 | 2026-10-15 | NEWCON | 251631 | 1 | Al Jemailiya (73 ) | 95 | 95 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 10452 | 10452 | Invoiced | Invoiced | 11 | 519 |  |  |  | 2026-05-06 | Completed | Invoiced
520 | 248036 | 520 | 2026-04-01 | 2026-03-31 | 2026-04-11 | 2026-07-01 | 2026-09-12 | BP | BP15257 | 81 | 1212424 | WORK IN PROGRESS | 837395 | Approved/Printed | 2026-08-16 | 2027-02-06 | NEWCON | 15165 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 64 | 64 | 0 | 0 | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5556 | 5556 | WORK IN PROGRESS | Pending | Pending | 520 |  |  |  | 2026-09-09 | Pending | Pending
521 | 248108 | 521 | 2026-04-02 | 2026-04-01 | 2026-04-12 | 2026-07-02 | 2026-09-12 | BP | BP#N/2025/7099(PIN34390023) | 81 | 1212898 | Pending | 837448 | Approved/Printed | 2026-08-19 | 2026-10-03 | NEWCON | 21785 | 1 | Madinat Khalifa(South)(34) | 53 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 4460 |  | Pending | Pending | Pending | 521 |  |  |  |  | Pending | Pending
522 | 248183 | 522 | 2026-04-05 | 2026-04-04 | 2026-04-15 | 2026-07-05 | 2026-09-12 | BP | BP146759 | 81 | 1213607 | Pending | 837397 | Approved/Printed | 2026-08-25 | 2027-02-11 | NEWCON | 34780 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 12 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 2000 |  | Pending | Pending | Pending | 522 |  |  |  |  | Pending | Pending
523 | 248303 | 523 | 2026-04-07 | 2026-04-06 | 2026-04-17 | 2026-07-07 | 2026-09-12 | BP | BP153124 | 81 | 1214338 | Pending | 823452 | Approved/Printed | 2026-04-23 | 2026-10-22 | NEWCON | 1583 | 1 | New District Of Doha 67(67) | 98 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 7160 |  | Pending | Pending | Pending | 523 |  |  |  |  | Pending | Pending
524 | 248306 | 524 | 2026-04-07 | 2026-04-06 | 2026-04-17 | 2026-07-07 | 2026-09-12 | BP | BP#N/2025/7263 (PIN15390022) | 81 | 1214349 | Pending | 837398 | Approved/Printed | 2026-08-24 | 2027-02-13 | NEWCON | 25175 | 1 | Al Doha Al Jadeeda (15 ) | 65 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 5180 |  | Pending | Pending | Pending | 524 |  |  |  |  | Pending | Pending
525 | 248317 | 525 | 2026-04-07 | 2026-04-06 | 2026-04-17 | 2026-07-07 | 2026-09-12 | BP | BP153391 | 81 | 1214376 | Pending | 839314 | Approved/Printed | 2026-09-01 | Pending | NEWCON | 28323 | 1 | Al Wakra (90 ) | 34 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 3320 |  | Pending | Pending | Pending | 525 |  |  |  |  | Pending | Pending
526 | 248324 | 526 | 2026-04-07 | 2026-04-06 | 2026-04-17 | 2026-07-07 | 2026-07-25 | BP | BP153385 | 81 | 1214401 | Completed | 823452 | Approved/Printed | 2026-04-23 | 2026-10-22 | BD DHAKA | 3203 | 1 | New District Of Doha 67(67) | 240 | 240 | 0 | 0 | 0 | 0 | 173 | 173 | 45 | 45 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28286 | 28286 | Completed | Pending | Pending | 526 |  |  |  | 2026-07-15 | Pending | Pending
527 | 248331 | 527 | 2026-04-07 | 2026-04-06 | 2026-04-17 | 2026-07-07 | 2026-09-12 | BP | BP#N/2025/9107 (PIN26310073) | 81 | 1214436 | Not Clear | Pending | Hold | Pending | Pending | NEWCON | 0479 | 1 | Najma(26) | 30 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 3080 |  | Hold | Pending | Pending | 527 |  |  |  |  | Pending | Pending
528 | 248350 | 528 | 2026-04-07 | 2026-04-06 | 2026-04-17 | 2026-07-07 | 2026-09-12 | BP | BP#N/2025/8590 (PIN34530033) | 81 | 1214452 | Pending | 837399 | Approved/Printed | 2026-08-23 | 2027-02-15 | NEWCON | 22222 | 1 | Madinat Khalifa(South)(34) | 200 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 13280 |  | Pending | Pending | Pending | 528 |  |  |  |  | Pending | Pending
529 | 248357 | 529 | 2026-04-07 | 2026-04-06 | 2026-04-17 | 2026-06-07 | 2026-05-06 | MOC | IN-114903 MOC-247444 | 51 | 1214454 | Completed | 823735 | Approved/Printed | 2026-04-18 | 2026-10-15 | NEWCON | 20611 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3900 | 3900 | Invoiced | Invoiced | 11 | 529 |  |  |  | 2026-05-03 | Completed | Invoiced
530 | 248358 | 530 | 2026-04-07 | 2026-04-06 | 2026-04-17 | 2026-06-07 | 2026-05-05 | MOC | IN-114932 MOC-129313 | 51 | 1214460 | Completed | 823736 | Approved/Printed | 2026-04-18 | 2026-10-15 | NEWCON | 2805 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 37 | 37 | 0 | 0 | 0 | 0 | 37 | 37 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 6169 | 6169 | Invoiced | Invoiced | 11 | 530 |  |  |  | 2026-05-03 | Completed | Invoiced
531 | 248380 | 531 | 2026-04-07 | 2026-04-06 | 2026-04-17 | 2026-07-07 | 2026-09-12 | BP | BP153479 | 81 | 1214541 | Pending | 834116 | Approved/Printed | 2026-08-04 | 2027-01-09 | NEWCON | 20786 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 88 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 6560 |  | Pending | Pending | Pending | 531 |  |  |  |  | Pending | Pending
532 | 248529 | 532 | 2026-04-09 | 2026-04-08 | 2026-04-19 | 2026-06-09 | 2026-05-05 | MOC | IN-114913 MOC-214265 | 51 | 1215327 | Completed | 823736 | Approved/Printed | 2026-04-18 | 2026-10-15 | BD DHAKA | 24530 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 112 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 7870 | 7870 | Invoiced | Invoiced | 11 | 532 |  |  |  | 2026-05-03 | Completed | Invoiced
533 | 248538 | 533 | 2026-04-09 | 2026-04-08 | 2026-04-19 | 2026-07-09 | 2026-09-12 | BP | BP-138540 | 81 | 1215391 | Pending | 839286 | Approved/Printed | 2026-08-24 | 2027-02-20 | NEWCON | 4978 | 1 | Al Kheesa (70 ) | 68 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 5360 |  | Pending | Pending | Pending | 533 |  |  |  |  | Pending | Pending
534 | 248539 | 534 | 2026-04-09 | 2026-04-08 | 2026-04-19 | 2026-07-09 | 2026-09-12 | BP | BP#N/2025/2100 | 81 | 1215397 | Pending | Pending | Pending | Pending | Pending | NEWCON | 2224 | 1 | Al Khor (74 ) | 165 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 11180 |  | Pending | Pending | Pending | 534 |  |  |  |  | Pending | Pending
535 | 248540 | 535 | 2026-04-09 | 2026-04-08 | 2026-04-19 | 2026-07-09 | 2026-09-12 | BP | BP149182 | 81 | 1215398 | Pending | 837397 | Approved/Printed | 2026-08-25 | 2027-02-11 | NEWCON | 9839 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 65 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 5180 |  | Pending | Pending | Pending | 535 |  |  |  |  | Pending | Pending
536 | 248541 | 536 | 2026-04-09 | 2026-04-08 | 2026-04-19 | 2026-07-09 | 2026-09-12 | BP | BP-128888 | 81 | 1215406 | Pending | 837400 | Approved/Printed | 2026-08-22 | 2027-02-18 | NEWCON | 25899 | 1 | Madinat Al Shamal/Al Ruwais(79) | 161 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 10940 |  | Pending | Pending | Pending | 536 |  |  |  |  | Pending | Pending
537 | 248560 | 537 | 2026-04-12 | 2026-04-11 | 2026-04-22 | 2026-07-12 | 2026-09-12 | OL | OL-F18-23447 | 81 | 1215957 | ROW | RO NA | ROW | Pending | Pending | NEWCON | 23447 | 1 | Madinat Khalifa(South)(34) | 160 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 3 |  | 3 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 12635 |  | Pending | Pending | Pending | 537 |  |  |  |  | Pending | Pending
538 | 248640 | 538 | 2026-04-12 | 2026-04-11 | 2026-04-22 | 2026-07-12 | 2026-09-12 | BP | BP-N/2025/4472 (PIN34320023) | 81 | 1216291 | Pending | Pending | Pending | Pending | Pending | NEWCON | 40544 | 1 | Madinat Khalifa(South)(34) | 55 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 4580 |  | Pending | Pending | Pending | 538 |  |  |  |  | Pending | Pending
539 | 248716 | 539 | 2026-04-13 | 2026-04-12 | 2026-04-23 | 2026-07-13 | 2026-09-12 | BP | BP-N/2025/1056 (PIN35116053) | 81 | 1216613 | Pending | 837394 | Approved/Printed | 2026-08-23 | 2027-02-04 | NEWCON | 2161 | 1 | Kulaib (35 ) | 101 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 7340 |  | Pending | Pending | Pending | 539 |  |  |  |  | Pending | Pending
540 | 248717 | 540 | 2026-04-13 | 2026-04-12 | 2026-04-23 | 2026-07-13 | 2026-09-12 | BP | BP153327 | 81 | 1216617 | Pending | 837397 | Approved/Printed | 2026-08-25 | 2027-02-11 | NEWCON | 3904 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 84 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 6320 |  | Pending | Pending | Pending | 540 |  |  |  |  | Pending | Pending
541 | 248721 | 541 | 2026-04-13 | 2026-04-12 | 2026-04-23 | 2026-07-13 | 2026-09-12 | BP | BP153421 | 81 | 1216621 | Pending | Pending | Pending | Pending | Pending | NEWCON | 3072 | 1 | New District Of Doha 65(65) | 65 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 5180 |  | Pending | Pending | Pending | 541 |  |  |  |  | Pending | Pending
542 | 248729 | 542 | 2026-04-13 | 2026-04-12 | 2026-04-23 | 2026-07-13 | 2026-09-12 | BP | BP153512 | 81 | 1216628 | Pending | Pending | Pending | Pending | Pending | NEWCON | 18821 | 1 | New District Of Doha 67(67) | 106 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 7640 |  | Pending | Pending | Pending | 542 |  |  |  |  | Pending | Pending
543 | 248736 | 543 | 2026-04-13 | 2026-04-12 | 2026-04-23 | 2026-07-13 | 2026-09-12 | BP | BP153497 | 81 | 1216631 | Pending | 837397 | Approved/Printed | 2026-08-25 | 2027-02-11 | NEWCON | 10216 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 121 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 8540 |  | Pending | Pending | Pending | 543 |  |  |  |  | Pending | Pending
544 | 248738 | 544 | 2026-04-13 | 2026-04-12 | 2026-04-23 | 2026-07-13 | 2026-09-12 | BP | BP-CE/2026/0005 (PIN82020551) | 81 | 1216637 | Pending | Pending | Pending | Pending | Pending | NEWCON | 39946 | 1 | Raudat Rashid (82 ) | 165 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 11180 |  | Pending | Pending | Pending | 544 |  |  |  |  | Pending | Pending
545 | 248812 | 545 | 2026-04-14 | 2026-04-13 | 2026-04-24 | 2026-06-14 | 2026-05-11 | MOC | IN-114811 MOC-251098 | 51 | 1217234 | Completed | 824703 | Approved/Printed | 2026-04-25 | 2026-10-22 | NEWCON | 18092 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 15 | 15 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 3618 | 3618 | Invoiced | Invoiced | 11 | 545 |  |  |  | 2026-05-07 | Completed | Invoiced
546 | 248813 | 546 | 2026-04-14 | 2026-04-13 | 2026-04-24 | 2026-06-14 | 2026-05-10 | MOC | IN-114972 MOC-229390 | 51 | 1217238 | Completed | 824476 | Approved/Printed | 2026-04-25 | 2026-10-22 | NEWCON | 229390 | 1 | Al Kheesa (70 ) | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 3820 | 3820 | Invoiced | Invoiced | 11 | 546 |  |  |  | 2026-05-06 | Completed | Invoiced
547 | 248814 | 547 | 2026-04-14 | 2026-04-13 | 2026-04-24 | 2026-06-14 | 2026-04-29 | MOC | IN-114984 MOC-221279 | 51 | 1217240 | Completed | 824703 | Approved/Printed | 2026-04-25 | 2026-10-22 | NEWCON | 24596 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 20 | 20 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 3154 | 3154 | Invoiced | Invoiced | 11 | 547 |  |  |  | 2026-04-29 | Completed | Invoiced
548 | 248815 | 548 | 2026-04-14 | 2026-04-13 | 2026-04-24 | 2026-07-14 | 2026-09-12 | BP | BP152262 | 81 | 1217242 | Pending | 837397 | Approved/Printed | 2026-08-25 | 2027-02-11 | NEWCON | 3507 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 8 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 1760 |  | Pending | Pending | Pending | 548 |  |  |  |  | Pending | Pending
549 | 248816 | 549 | 2026-05-13 | 2026-05-12 | 2026-05-23 | 2026-07-13 | 2026-06-24 | MOC+BP | MOC-250513+BP153612+BP154133 | 51 | 1217244 | Completed | 827871 | Approved/Printed | 2026-05-31 | 2026-11-14 | NEWCON | 26567 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 330 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 22190 | 22190 | Invoiced | Invoiced | 13 | 549 |  |  |  | 2026-06-15 | Completed | Invoiced
550 | 248817 | 550 | 2026-04-14 | 2026-04-13 | 2026-04-24 | 2026-07-14 | 2026-09-12 | BP | BP153614 | 81 | 1217247 | Pending | 837397 | Approved/Printed | 2026-08-25 | 2027-02-11 | NEWCON | 9939 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 37 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 3500 |  | Pending | Pending | Pending | 550 |  |  |  |  | Pending | Pending
551 | 248818 | 551 | 2026-04-14 | 2026-04-13 | 2026-04-24 | 2026-07-14 | 2026-09-12 | BP | BP153615 | 81 | 1217248 | Pending | 843432 | In Review | Pending | Pending | NEWCON | 11694 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 83 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 6260 |  | Pending | Pending | Pending | 551 |  |  |  |  | Pending | Pending
552 | 248895 | 552 | 2026-04-15 | 2026-04-14 | 2026-04-25 | 2026-06-15 | 2026-05-07 | MOC | IN-114933 MOC-245527 | 51 | 1217688 | Completed | 824703 | Approved/Printed | 2026-04-25 | 2026-10-22 | NEWCON | 27461 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 3940 | 3940 | Invoiced | Invoiced | 11 | 552 |  |  |  | 2026-05-03 | Completed | Invoiced
553 | 249033 | 553 | 2026-05-21 | 2026-05-20 | 2026-05-31 | 2026-07-21 | 2026-07-01 | MOC | IN-115753 MOC-251238 | 51 | 1218960 | Completed | 831253 | Approved/Printed | 2026-06-23 | 2026-12-15 | NEWCON | 5112 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 75 | 75 | 0 | 0 | 0 | 0 | 22 | 22 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 7594 | 7594 | Completed | Pending | Pending | 553 |  |  |  | 2026-06-28 | Pending | Pending
553 | 249033 | 553-P2 | 2026-05-21 | 2026-05-20 | 2026-05-31 | 2026-07-21 | 2026-07-01 | MOC | IN-115753 MOC-251238 | 51 | 1218960 | Completed | 831253 | Approved/Printed | 2026-06-23 | 2026-12-15 | NEWCON | 5112 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 23 | 23 |  |  |  |  | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2577 | 2577 | Completed | Pending | Pending | 553 |  |  |  | 2026-06-30 | Pending | Pending
554 | 249034 | 554 | 2026-04-19 | 2026-04-18 | 2026-04-29 | 2026-07-19 | 2026-09-12 | BP | BP#N/2025/4643 | 81 | 1218970 | Pending | 838760 | Approved/Printed | 2026-08-31 | 2027-02-23 | NEWCON | 17352 | 1 | Abu Nakhla / Mukainess (81 ) | 200 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 13280 |  | Pending | Pending | Pending | 554 |  |  |  |  | Pending | Pending
555 | 249035 | 555 | 2026-04-19 | 2026-04-18 | 2026-04-29 | 2026-07-19 | 2026-09-12 | BP | BP153722 | 81 | 1218971 | Pending | 843432 | In Review | Pending | Pending | NEWCON | 13662 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 64 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 5120 |  | Pending | Pending | Pending | 555 |  |  |  |  | Pending | Pending
556 | 249036 | 556 | 2026-04-19 | 2026-04-18 | 2026-04-29 | 2026-07-19 | 2026-09-12 | BP | BP153733 | 81 | 1218972 | Pending | 843432 | In Review | Pending | Pending | NEWCON | 13438 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 150 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 10857 |  | Pending | Pending | Pending | 556 |  |  |  |  | Pending | Pending
557 | 249037 | 557 | 2026-04-19 | 2026-04-18 | 2026-04-29 | 2026-07-19 | 2026-09-12 | BP | BP153744 | 81 | 1218973 | Pending | 834116 | Approved/Printed | 2026-08-04 | 2027-01-09 | NEWCON | 4150 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 119 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 8420 |  | Pending | Pending | Pending | 557 |  |  |  |  | Pending | Pending
558 | 249038 | 558 | 2026-04-19 | 2026-04-18 | 2026-04-29 | 2026-07-19 | 2026-09-12 | BP | BP153791 | 81 | 1218975 | Pending | Pending | Pending | Pending | Pending | NEWCON | 13304 | 1 | Madinat Khalifa(North)(34) | 204 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 13520 |  | Pending | Pending | Pending | 558 |  |  |  |  | Pending | Pending
559 | 249300 | 559 | 2026-04-23 | 2026-04-22 | 2026-05-03 | 2026-06-23 | 2026-07-02 | MOC+OL | IN-114950 MOC-224508+OLF113500 | 51 | 1220657 | Completed | 826621 | Approved/Printed | 2026-05-18 | 2026-09-26 | NEWCON | 13500 | 1 | Madinat Khalifa(South)(34) | 150 | 150 | 20 | 20 | 0 | 0 | 150 | 150 | 0 | 0 | 25 | 25 | 1 | 1 | 0 | 0 | 2 | 2 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 26765 | 26765 | Invoiced | Invoiced | 13 | 559 |  |  |  | 2026-06-18 | Completed | Invoiced
560 | 249405 | 560 | 2026-04-26 | 2026-04-25 | 2026-05-06 | 2026-06-26 | 2026-05-24 | MOC | IN-115123 MOC-154809 | 51 | 1221490 | Completed | 825624 | Approved/Printed | 2026-05-07 | 2026-10-29 | NEWCON | 26441 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 143 | 143 | 0 | 0 | 0 | 0 | 143 | 143 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 18571 | 18571 | Invoiced | Invoiced | 12 | 560 |  |  |  | 2026-05-17 | Completed | Invoiced
561 | 249635 | 561 | 2026-04-30 | 2026-04-29 | 2026-05-10 | 2026-06-30 | 2026-05-20 | MOC | IN-115218 MOC-119155 | 51 | 1223165 | Completed | 826282 | Approved/Printed | 2026-05-09 | 2026-11-05 | NEWCON | 4309 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 68 | 68 | 0 | 0 | 0 | 0 | 68 | 68 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 4 | 4 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 11366 | 11366 | Invoiced | Invoiced | 11 | 561 |  |  |  | 2026-05-12 | Completed | Invoiced
562 | 249647 | 562 | 2026-05-03 | 2026-05-02 | 2026-05-13 | 2026-07-03 | 2026-06-09 | MOC | C-1047744(MSA-18037570) | 51 | 1223816 | Completed | 826441 | Approved/Printed | 2026-05-17 | 2026-11-05 | NEWCON | 4866 | 1 | Al Duhail South (31 ) | 103 | 103 | 0 | 0 | 0 | 0 | 49 | 49 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 1 | 1 | 0 | 0 | 12593 | 12593 | Invoiced | Invoiced | 12 | 562 |  |  |  | 2026-06-07 | Completed | Invoiced
563 | 249783 | 563 | 2026-05-05 | 2026-05-04 | 2026-05-15 | 2026-05-15 | 2026-05-24 | DS | IN-115237 MOC-238616 | 0 | 1224722 | Completed | 826925 | Approved/Printed | 2026-05-18 | 2026-11-08 | NEWCON | 0869 | 1 | Fareeq Al Amir/Muraykh/Al Soud(54 ) | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3780 | 3780 | Invoiced | Invoiced | 11 | 563 |  |  |  | 2026-05-24 | Completed | Invoiced
564 | 249890 | 564 | 2026-05-06 | 2026-05-05 | 2026-05-16 | 2026-07-06 | 2026-06-21 | MOC | IN-115344 MOC-138281 | 51 | 1225254 | Completed | 827165 | Approved/Printed | 2026-05-21 | 2026-11-12 | NEWCON | 30540 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 50 | 50 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 7690 | 7690 | Invoiced | Invoiced | 13 | 564 |  |  |  | 2026-06-16 | Completed | Invoiced
565 | 250169 | 565 | 2026-05-12 | 2026-05-11 | 2026-05-22 | 2026-07-12 | 2026-05-20 | MOC | IN-115400 MOC-196702 | 51 | 1227602 | Completed | 828127 | Approved/Printed | 2026-05-19 | 2026-06-03 | NEWCON | 19054 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3770 | 3770 | Invoiced | Invoiced | 11 | 565 |  |  |  | 2026-05-20 | Completed | Invoiced
566 | 250649 | 566 | 2026-05-21 | 2026-05-20 | 2026-05-31 | 2026-07-21 | 2026-06-20 | MOC | IN-115658 MOC-251867+68 | 51 | 1230814 | Completed | 831950 | Approved/Printed | 2026-06-17 | 2026-07-02 | NEWCON | 15895 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 131 | 131 | 0 | 0 | 0 | 0 | 131 | 131 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 3 | 3 | 2 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 2 | 21347 | 21347 | Invoiced | Invoiced | 12 | 566 |  |  |  | 2026-06-15 | Completed | Invoiced
567 | 250706 | 567 | 2026-05-24 | 2026-05-23 | 2026-06-03 | 2026-07-24 | 2026-06-25 | MOC | C-159502 MSA-18037494 | 51 | 1231369 | Completed | 830037 | Approved/Printed | 2026-06-10 | 2026-11-07 | NEWCON | 15497 | 1 | Al Thakhira (75 ) | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 15 | 15 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 4045 | 4045 | Completed | Pending | Pending | 567 |  |  |  | 2026-06-23 | Pending | Pending
568 | 250840 | 568 | 2026-06-10 | 2026-06-09 | 2026-06-20 | 2026-08-10 | 2026-09-12 | MOC | IN-115819+934 MOC-243602+251445 | 51 | 1232817 | Cancelled | 830617 | Cancelled | Cancelled | Cancelled | NEWCON | 13188 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 351 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 0 | 2 |  | 2 |  | 2 |  | 0 | 0 | 2 |  | 0 | 0 | 24774 |  | Cancelled | Pending | Pending | 568 |  |  |  |  | Cancelled | Cancelled
569 | 251076 | 569 | 2026-06-07 | 2026-06-06 | 2026-06-17 | 2026-08-07 | 2026-07-02 | MOC | C-1413507 MSA-12935 | 51 | 1234789 | Completed | 831472 | Approved/Printed | 2026-06-21 | 2026-12-18 | NEWCON | 24602 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 66 | 66 | 0 | 0 | 0 | 0 | 31 | 31 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 3 | 3 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 8447 | 8447 | Completed | Pending | Pending | 569 |  |  |  | 2026-06-28 | Pending | Pending
570 | 251127 | 570 | 2026-06-08 | 2026-06-07 | 2026-06-18 | 2026-09-08 | 2026-08-25 | BP | BP-N/2025/7148 | 82 | 1235212 | Completed | 831053/ 835586 | Approved/Printed | 2026-06-21 | 2026-12-14 | NEWCON | 25040 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 593 | 593 | 32 | 32 | 0 | 0 | 150 | 150 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54190 | 54190 | Completed | Pending | Pending | 570 |  |  |  | 2026-07-06 | Pending | Pending
571 | 251133 | 571 | 2026-06-09 | 2026-06-08 | 2026-06-19 | 2026-09-09 | 2026-09-12 | BP | BP-N/2025/7513 (PIN80030258) | 82 | 1235429 | Pending | 839315 | Approved/Printed | 2026-09-01 | 2027-02-18 | NEWCON | 20619 | 1 | Al Shahhniya (80 ) | 158 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 10760 |  | Pending | Pending | Pending | 571 |  |  |  |  | Pending | Pending
572 | 251150 | 572 | 2026-06-09 | 2026-06-08 | 2026-06-19 | 2026-09-09 | 2026-09-12 | BP | BP153868 | 82 | 1235517 | Pending | 834116 | Approved/Printed | 2026-08-04 | 2027-01-09 | NEWCON | 3584 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 189 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 12620 |  | Pending | Pending | Pending | 572 |  |  |  |  | Pending | Pending
573 | 251157 | 573 | 2026-06-09 | 2026-06-08 | 2026-06-19 | 2026-09-09 | 2026-09-12 | BP | BP154064 | 82 | 1235571 | WORK IN PROGRESS | 832431 | Approved/Printed | 2026-07-20 | 2026-12-25 | NEWCON | 39559 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 114 | 114 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 7530 | 7530 | WORK IN PROGRESS | Pending | Pending | 573 |  |  |  | 2026-08-23 | Pending | Pending
574 | 251165 | 574 | 2026-06-09 | 2026-06-08 | 2026-06-19 | 2026-09-09 | 2026-09-12 | BP | BP149100+BP-154072 | 82 | 1235596 | Pending | 843435 | In Review | Pending | Pending | NEWCON | 2661 | 2 | Umm Slal/Al Kharaitiyat (71 ) | 254 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 16520 |  | Pending | Pending | Pending | 574 |  |  |  |  | Pending | Pending
575 | 251174 | 575 | 2026-06-09 | 2026-06-08 | 2026-06-19 | 2026-09-09 | 2026-09-12 | BP | BP154061 | 82 | 1235608 | Pending | 832431 | Approved/Printed | 2026-07-20 | 2026-12-25 | NEWCON | 3329 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 51 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 4340 |  | Pending | Pending | Pending | 575 |  |  |  |  | Pending | Pending
576 | 251188 | 576 | 2026-06-09 | 2026-06-08 | 2026-06-19 | 2026-09-09 | 2026-09-12 | BP | BP154069 | 82 | 1235622 | Pending | 832431 | Approved/Printed | 2026-07-20 | 2026-12-25 | NEWCON | 3537 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 142 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 9800 |  | Pending | Pending | Pending | 576 |  |  |  |  | Pending | Pending
577 | 251191 | 577 | 2026-07-23 | 2026-07-22 | 2026-08-02 | 2026-09-23 | 2026-08-17 | MOC | C-1031860(MSA-18038683) | 52 | 1235632 | Completed | 837356 | Approved/Printed | 2026-08-04 | 2027-01-28 | NEWCON | 9620 | 1 | Al Shahhniya (80 ) | 30 | 30 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 3640 | 3640 | Completed | Pending | Pending | 577 |  |  |  | 2026-08-17 | Completed | Pending
578 | 251234 | 578 | 2026-06-10 | 2026-06-09 | 2026-06-20 | 2026-09-10 | 2026-09-12 | BP | BP-N/2025/9082(PIN37470022) | 82 | 1235985 | Pending | Pending | Pending | Pending | Pending | NEWCON | 0191 | 1 | Bin Omran/Al Hitmi Al Jadeed (37 ) | 290 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 18680 |  | Pending | Pending | Pending | 578 |  |  |  |  | Pending | Pending
579 | 251241 | 579 | 2026-06-10 | 2026-06-09 | 2026-06-20 | 2026-09-10 | 2026-09-12 | BP | BP154031 | 82 | 1236019 | Pending | 843435 | In Review | Pending | Pending | NEWCON | 3488 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 154 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 10520 |  | Pending | Pending | Pending | 579 |  |  |  |  | Pending | Pending
580 | 251250 | 580 | 2026-06-10 | 2026-06-09 | 2026-06-20 | 2026-09-10 | 2026-09-12 | BP | BP153397 | 82 | 1236025 | Pending | Pending | Pending | Pending | Pending | NEWCON | 29248 | 1 | Al Duhail (30 ) | 191 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 12740 |  | Pending | Pending | Pending | 580 |  |  |  |  | Pending | Pending
581 | 251251 | 581 | 2026-06-10 | 2026-06-09 | 2026-06-20 | 2026-09-10 | 2026-09-12 | BP | BP150829 | 82 | 1236026 | Pending | 843432 | In Review | Pending | Pending | NEWCON | 28359 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 5 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 1580 |  | Pending | Pending | Pending | 581 |  |  |  |  | Pending | Pending
582 | 251253 | 582 | 2026-06-10 | 2026-06-09 | 2026-06-20 | 2026-09-10 | 2026-09-12 | BP | BP-N/2025/1992(PIN34080055) | 82 | 1236031 | Pending | 837399 | Approved/Printed | 2026-08-23 | 2027-02-15 | NEWCON | 20169 | 1 | Madinat Khalifa(South)(34) | 311 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 19940 |  | Pending | Pending | Pending | 582 |  |  |  |  | Pending | Pending
583 | 251254 | 583 | 2026-09-08 | 2026-09-07 | 2026-09-18 | 2026-11-08 | 2026-09-12 | MOC | C-140996 (MSA-18039621) | 51 | 1236032 | Pending | 838762 | Approved/Printed | 2026-09-08 | 2027-02-27 | NEWCON | 20672 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 54 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 4690 |  | Pending | Pending | Pending | 583 |  |  |  |  | Pending | Pending
584 | 251258 | 584 | 2026-06-10 | 2026-06-09 | 2026-06-20 | 2026-08-10 | 2026-07-06 | MOC | IN-115978 MOC-200514 | 51 | 1236072 | Completed | 831507 | Approved/Printed | 2026-07-01 | 2026-07-16 | NEWCON | 23350 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 32 | 32 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 5454 | 5454 | Invoiced | Invoiced | 13 | 584 |  |  |  | 2026-07-02 | Completed | Invoiced
585 | 251305 | 585 | 2026-06-11 | 2026-06-10 | 2026-06-21 | 2026-09-11 | 2026-09-12 | BP | BP153850 | 82 | 1236407 | Pending | 834116 | Approved/Printed | 2026-08-04 | 2027-01-09 | NEWCON | 15018 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 258 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 16760 |  | Pending | Pending | Pending | 585 |  |  |  |  | Pending | Pending
586 | 251308 | 586 | 2026-06-11 | 2026-06-10 | 2026-06-21 | 2026-09-11 | 2026-09-12 | BP | BP153854 | 82 | 1236415 | Pending | 839315 | Approved/Printed | 2026-09-01 | 2027-02-18 | NEWCON | 9604 | 1 | Al Shahhniya (80 ) | 50 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 4280 |  | Pending | Pending | Pending | 586 |  |  |  |  | Pending | Pending
587 | 251311 | 587 | 2026-06-11 | 2026-06-10 | 2026-06-21 | 2026-09-11 | 2026-09-12 | BP | BP153857 | 82 | 1236419 | Pending | 838762 | Approved/Printed | 2026-09-08 | 2027-02-27 | NEWCON | 33779 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 85 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 6380 |  | Pending | Pending | Pending | 587 |  |  |  |  | Pending | Pending
588 | 251312 | 588 | 2026-06-11 | 2026-06-10 | 2026-06-21 | 2026-09-11 | 2026-09-12 | BP | BP-N/2025/3551(PIN53310098) | 82 | 1236420 | Pending | Pending | Pending | Pending | Pending | NEWCON | 3441 | 1 | Al Rayyan Al Jadeed/Muaither N(53 ) | 129 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 9020 |  | Pending | Pending | Pending | 588 |  |  |  |  | Pending | Pending
589 | 251384 | 589 | 2026-06-14 | 2026-06-13 | 2026-06-24 | 2026-08-14 | 2026-07-19 | MOC | IN-115947 MOC-249080 | 51 | 1236984 | Completed | 832013/ 835043 | Approved/Printed | 2026-07-13 | 2026-09-08 | NEWCON | 22702 | 1 | Madinat Khalifa(South)(34) | 13 | 13 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 4155 | 4155 | Completed | Pending | Pending | 589 |  |  |  | 2026-07-19 | Pending | Pending
590 | 251445 | 590 | 2026-06-15 | 2026-06-14 | 2026-06-25 | 2026-08-15 | 2026-07-30 | MOC | IN-116015 MOC-245216+217 | 51 | 1237419 | Completed | 831990 | Approved/Printed | 2026-07-19 | 2026-12-27 | NEWCON | 3714 | 1 | Madinat Khalifa(South)(34) | 103 | 103 | 0 | 0 | 0 | 0 | 103 | 103 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 14521 | 14521 | Completed | Pending | Pending | 590 |  |  |  | 2026-07-23 | Pending | Pending
591 | 251488 | 591 | 2026-06-16 | 2026-06-15 | 2026-06-26 | 2026-09-16 | 2026-09-12 | BP | BP#N/2025/8717(PIN31240153) | 82 | 1237620 | Pending | 838764 | Approved/Printed | 2026-09-02 | 2027-03-01 | NEWCON | 15019 | 1 | Al Duhail South (31 ) | 35 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 3380 |  | Pending | Pending | Pending | 591 |  |  |  |  | Pending | Pending
592 | 251494 | 592 | 2026-06-16 | 2026-06-15 | 2026-06-26 | 2026-09-16 | 2026-08-24 | BP | BP154422 | 82 | 1237637 | Completed | 834721 | Approved/Printed | 2026-08-04 | 2027-01-09 | NEWCON | 16770 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 42 | 42 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 3210 | 3210 | Completed | Pending | Pending | 592 |  |  |  | 2026-08-19 | Pending | Pending
592 | 251494 | 592-R | 2026-09-07 | 2026-09-06 | 2026-09-17 | 2026-09-17 | 2026-08-24 | MOC | IN-117111 MOC-252173 | 0 | 1237637 | Completed | 834721 | Approved/Printed | 2026-08-04 | 2027-01-09 | NEWCON | 16770 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 4200 |  | Pending | Pending | Pending | 592 |  |  |  |  | Pending | Pending
593 | 251500 | 593 | 2026-06-16 | 2026-06-15 | 2026-06-26 | 2026-09-16 | 2026-09-12 | BP | BP154455 | 82 | 1237652 | Pending | Pending | Pending | Pending | Pending | NEWCON | 1787 | 1 | New District Of Doha 63(63) | 121 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 8540 |  | Pending | Pending | Pending | 593 |  |  |  |  | Pending | Pending
594 | 251521 | 594 | 2026-06-16 | 2026-06-15 | 2026-06-26 | 2026-09-16 | 2026-09-12 | BP | BP153990 | 82 | 1237758 | Pending | 839286 | Approved/Printed | 2026-08-24 | 2027-02-20 | NEWCON | 18886 | 1 | Al Kheesa (70 ) | 47 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 4100 |  | Pending | Pending | Pending | 594 |  |  |  |  | Pending | Pending
595 | 251528 | 595 | 2026-06-16 | 2026-06-15 | 2026-06-26 | 2026-09-16 | 2026-09-12 | BP | BP153998 | 82 | 1237784 | Pending | 839286 | Approved/Printed | 2026-08-24 | 2027-02-20 | NEWCON | 39712 | 1 | Al Kheesa (70 ) | 200 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 13280 |  | Pending | Pending | Pending | 595 |  |  |  |  | Pending | Pending
596 | 251532 | 596 | 2026-06-16 | 2026-06-15 | 2026-06-26 | 2026-09-16 | 2026-09-12 | BP | BP154023 | 82 | 1237830 | Pending | 838762 | Approved/Printed | 2026-09-08 | 2027-02-27 | NEWCON | 4187 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 101 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 7340 |  | Pending | Pending | Pending | 596 |  |  |  |  | Pending | Pending
597 | 251533 | 597 | 2026-06-16 | 2026-06-15 | 2026-06-26 | 2026-09-16 | 2026-08-20 | BP | BP153817 | 82 | 1237836 | Completed | 834721 | Approved/Printed | 2026-08-04 | 2027-01-09 | NEWCON | 19789 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 6 | 6 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 | 0 | 1640 | 1640 | Completed | Pending | Pending | 597 |  |  |  | 2026-08-18 | Completed | Pending
598 | 251537 | 598 | 2026-06-16 | 2026-06-15 | 2026-06-26 | 2026-08-16 | 2026-07-12 | MOC | IN-116073 MOC-250184 | 51 | 1237856 | Completed | 832145 | Approved/Printed | 2026-06-30 | 2026-12-22 | NEWCON | 13439 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 74 | 74 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 7514 | 7514 | Invoiced | Invoiced | 13 | 598 |  |  |  | 2026-07-07 | Completed | Invoiced
599 | 251538 | 599 | 2026-06-16 | 2026-06-15 | 2026-06-26 | 2026-09-16 | 2026-09-12 | BP | BP153929 | 82 | 1237859 | Pending | 838762 | Approved/Printed | 2026-09-08 | 2027-02-27 | NEWCON | 16294 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 77 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 5900 |  | Pending | Pending | Pending | 599 |  |  |  |  | Pending | Pending
600 | 251539 | 600 | 2026-06-16 | 2026-06-15 | 2026-06-26 | 2026-09-16 | 2026-09-12 | BP | BP154125 | 82 | 1237861 | Pending | 838762 | Approved/Printed | 2026-09-08 | 2027-02-27 | NEWCON | 26215 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 48 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 4160 |  | Pending | Pending | Pending | 600 |  |  |  |  | Pending | Pending
601 | 251558 | 601 | 2026-06-17 | 2026-06-16 | 2026-06-27 | 2026-08-17 | 2026-07-22 | MOC | IN-115165 MOC-252355 | 51 | 1238109 | Completed | 832446/ 835473 | Approved/Printed | 2026-06-30 | 2026-12-25 | NEWCON | 32699 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 113 | 113 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 9555 | 9555 | Invoiced | Invoiced | 13 | 601 |  |  |  | 2026-07-12 | Completed | Invoiced
602 | 251578 | 602 | 2026-06-17 | 2026-06-16 | 2026-06-27 | 2026-09-17 | 2026-09-12 | BP | BP#N/2024/6619(PIN80090239) | 82 | 1238240 | Pending | 839315 | Approved/Printed | 2026-09-01 | 2027-02-18 | NEWCON | 25034 | 1 | Al Shahhniya (80 ) | 12 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 2000 |  | Pending | Pending | Pending | 602 |  |  |  |  | Pending | Pending
603 | 251594 | 603 | 2026-06-17 | 2026-06-16 | 2026-06-27 | 2026-09-17 | 2026-09-12 | BP | BP149160 | 82 | 1238259 | Pending | 839286 | Approved/Printed | 2026-08-24 | 2027-02-20 | NEWCON | 149160 | 1 | Al Kheesa (70 ) | 80 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 6080 |  | Pending | Pending | Pending | 603 |  |  |  |  | Pending | Pending
604 | 251596 | 604 | 2026-06-17 | 2026-06-16 | 2026-06-27 | 2026-08-17 | 2026-07-22 | MOC | IN-116067 MOC-203266 | 51 | 1238265 | Completed | 832449 | Approved/Printed | 2026-06-30 | 2026-12-25 | NEWCON | 17640 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 72 | 72 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 8440 | 8440 | Completed | Pending | Pending | 604 |  |  |  | 2026-07-07 | Pending | Pending
605 | 251598 | 605 | 2026-06-17 | 2026-06-16 | 2026-06-27 | 2026-08-17 | 2026-08-31 | MOC | IN-116007 MOC-240713 | 51 | 1238268 | Completed | 832450 | Approved/Printed | 2026-07-20 | 2026-12-27 | NEWCON | 0644 | 1 | Umm Ghuwailina(27) | 88 | 88 | 23 | 23 | 0 | 0 | 36 | 36 | 0 | 0 | 47 | 47 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 19272 | 19272 | Completed | Pending | Pending | 605 |  |  |  | 2026-08-31 | Pending | Pending
605 | 251598 | 605-P2 | 2026-06-17 | 2026-06-16 | 2026-06-27 | 2026-08-17 | 2026-08-31 | MOC | IN-116007 MOC-240713 | 51 | 1238268 | Completed | 832450 | Approved/Printed | 2026-07-20 | 2026-12-27 | NEWCON | 0644 | 1 | Umm Ghuwailina(27) | 20 | 20 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3680 | 3680 | Completed | Pending | Pending | 605 |  |  |  | 2026-09-02 | Pending | Pending
606 | 251681 | 606 | 2026-06-18 | 2026-06-17 | 2026-06-28 | 2026-09-18 | 2026-09-12 | BP | BP#N/2025/9517 (PIN27790015) | 82 | 1238606 | Pending | 839316 | Approved/Printed | 2026-09-03 | 2027-03-02 | NEWCON | 20137 | 1 | Umm Ghuwailina(27) | 377 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 23900 |  | Pending | Pending | Pending | 606 |  |  |  |  | Pending | Pending
607 | 251682 | 607 | 2026-06-18 | 2026-06-17 | 2026-06-28 | 2026-09-18 | 2026-09-12 | BP | BP-N/2025/9504 (PIN27480059) | 82 | 1238608 | Pending | 839316 | Approved/Printed | 2026-09-03 | 2027-03-02 | NEWCON | 0708 | 1 | Umm Ghuwailina(27) | 70 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 5480 |  | Pending | Pending | Pending | 607 |  |  |  |  | Pending | Pending
608 | 251683 | 608 | 2026-06-18 | 2026-06-17 | 2026-06-28 | 2026-09-18 | 2026-09-12 | BP | BP-N/2026/200 (PIN25410011) | 82 | 1238609 | Pending | Pending | Pending | Pending | Pending | NEWCON | 26196 | 1 | Al Mansoura/Bin Dirhem (25 ) | 60 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 4880 |  | Pending | Pending | Pending | 608 |  |  |  |  | Pending | Pending
609 | 251718 | 609 | 2026-06-21 | 2026-06-20 | 2026-07-01 | 2026-09-21 | 2026-09-12 | BP | BP154090 | 82 | 1239061 | Pending | Pending | Pending | Pending | Pending | NEWCON | 0137 | 1 | Madinat Khalifa(South)(34) | 129 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 9020 |  | Pending | Pending | Pending | 609 |  |  |  |  | Pending | Pending
610 | 251720 | 610 | 2026-06-21 | 2026-06-20 | 2026-07-01 | 2026-09-21 | 2026-09-12 | BP | BP154186 | 82 | 1239102 | Pending | 838762 | Approved/Printed | 2026-09-08 | 2027-02-27 | NEWCON | 4177 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 5 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 990 |  | Pending | Pending | Pending | 610 |  |  |  |  | Pending | Pending
611 | 251791 | 611 | 2026-06-22 | 2026-06-21 | 2026-07-02 | 2026-09-21 | 2026-09-12 | BP | BP-N/2025/0675 (PIN71053796) | 81 | 1239615 | Pending | 838765 | Approved/Printed | 2026-09-05 | 2027-03-04 | NEWCON | 22431 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 55 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 4580 |  | Pending | Pending | Pending | 611 |  |  |  |  | Pending | Pending
612 | 251792 | 612 | 2026-06-22 | 2026-06-21 | 2026-07-02 | 2026-09-21 | 2026-09-12 | BP | BP153923 | 81 | 1239687 | Pending | 834721 | Approved/Printed | 2026-08-04 | 2027-01-09 | NEWCON | 3563 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 80 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 6080 |  | Pending | Pending | Pending | 612 |  |  |  |  | Pending | Pending
613 | 251856 | 613 | 2026-06-23 | 2026-06-22 | 2026-07-03 | 2026-08-23 | 2026-08-23 | MOC | IN-116031 MOC-252636 | 51 | 1240085 | Completed | 833228/ 837276 | Approved/Printed | 2026-07-08 | 2026-12-29 | NEWCON | 0655 | 1 | Umm Ghuwailina(27) | 38 | 38 | 0 | 0 | 0 | 0 | 33 | 33 | 0 | 0 | 20 | 20 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 9101 | 9101 | Completed | Pending | Pending | 613 |  |  |  | 2026-08-19 | Pending | Pending
614 | 251933 | 614 | 2026-06-24 | 2026-06-23 | 2026-07-04 | 2026-09-24 | 2026-09-02 | BP | BP154335 | 82 | 1240538 | Completed | 834721 | Approved/Printed | 2026-08-04 | 2027-01-09 | NEWCON | 29976 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 124 | 124 | 0 | 0 | 0 | 0 | 113 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0 |  | 14571 | 14571 | Completed | Pending | Pending | 614 |  |  |  | 2026-08-31 | Pending | Pending
615 | 251934 | 615 | 2026-06-24 | 2026-06-23 | 2026-07-04 | 2026-09-24 | 2026-09-12 | BP | BP154281 | 82 | 1240540 | Pending | 838765 | Approved/Printed | 2026-09-05 | 2027-03-04 | NEWCON | 25831 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 5 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 1580 |  | Pending | Pending | Pending | 615 |  |  |  |  | Pending | Pending
616 | 251935 | 616 | 2026-06-24 | 2026-06-23 | 2026-07-04 | 2026-09-24 | 2026-09-12 | BP | BP154283 | 82 | 1240546 | Pending | 837400 | Approved/Printed | 2026-08-22 | 2027-02-18 | NEWCON | 12197 | 1 | Madinat Al Shamal/Al Ruwais(79) | 65 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 5180 |  | Pending | Pending | Pending | 616 |  |  |  |  | Pending | Pending
617 | 251974 | 617 | 2026-06-25 | 2026-06-24 | 2026-07-05 | 2026-09-25 | 2026-09-12 | BP | BP154307 | 82 | 1240771 | Pending | 837395 | Approved/Printed | 2026-08-16 | 2027-02-06 | NEWCON | 26154 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 91 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 6740 |  | Pending | Pending | Pending | 617 |  |  |  |  | Pending | Pending
618 | 251979 | 618 | 2026-06-25 | 2026-06-24 | 2026-07-05 | 2026-09-25 | 2026-09-12 | BP | BP154310 | 82 | 1240779 | Pending | Pending | Pending | Pending | Pending | NEWCON | 11579 | 1 | Musaimeer(46) | 81 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 6140 |  | Pending | Pending | Pending | 618 |  |  |  |  | Pending | Pending
619 | 251986 | 619 | 2026-06-25 | 2026-06-24 | 2026-07-05 | 2026-09-25 | 2026-09-12 | BP | BP153922 | 82 | 1240786 | WORK IN PROGRESS | 838764 | Approved/Printed | 2026-09-02 | 2027-03-01 | NEWCON | 9851 | 1 | Al Duhail South (31 ) | 130 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 9080 |  | WORK IN PROGRESS | Pending | Pending | 619 |  |  |  |  | Pending | Pending
620 | 251994 | 620 | 2026-06-25 | 2026-06-24 | 2026-07-05 | 2026-09-25 | 2026-09-12 | BP | BP153824 | 82 | 1240796 | Pending | 838765 | Approved/Printed | 2026-09-05 | 2027-03-04 | NEWCON | 41102 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 149 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3 |  | 2 |  | 0 | 0 | 0 |  | 0 | 0 | 10380 |  | Pending | Pending | Pending | 620 |  |  |  |  | Pending | Pending
621 | 252003 | 621 | 2026-06-25 | 2026-06-24 | 2026-07-05 | 2026-09-25 | 2026-09-12 | BP | BP154558 | 82 | 1240860 | Pending | Pending | Pending | Pending | Pending | NEWCON | 5231 | 1 | Al Kheesa (70 ) | 32 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2 |  | 2 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 3850 |  | Pending | Pending | Pending | 621 |  |  |  |  | Pending | Pending
622 | 252004 | 622 | 2026-06-25 | 2026-06-24 | 2026-07-05 | 2026-09-25 | 2026-09-12 | BP | BP154562 | 82 | 1240861 | Pending | 838765 | Approved/Printed | 2026-09-05 | 2027-03-04 | NEWCON | 40506 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 136 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 2 |  | 2 |  | 0 | 0 | 0 |  | 0 | 0 | 10130 |  | Pending | Pending | Pending | 622 |  |  |  |  | Pending | Pending
623 | 252005 | 623 | 2026-06-25 | 2026-06-24 | 2026-07-05 | 2026-09-25 | 2026-09-12 | BP | BP124571 | 82 | 1240862 | Pending | 837395 | Approved/Printed | 2026-08-16 | 2027-02-06 | NEWCON | 4803 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 133 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 8670 |  | Pending | Pending | Pending | 623 |  |  |  |  | Pending | Pending
624 | 252052 | 624 | 2026-06-28 | 2026-06-27 | 2026-07-08 | 2026-08-28 | 2026-08-18 | MOC | IN-116133 MOC-252651 | 51 | 1241353 | Completed | 833894 | Approved/Printed | 2026-07-19 | 2026-01-04 | BD DHAKA | 26442 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 214 | 214 | 0 | 0 | 0 | 0 | 194 | 194 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 25698 | 25698 | Completed | Pending | Pending | 624 |  |  |  | 2026-08-06 | Pending | Pending
625 | 252103 | 625 | 2026-06-29 | 2026-06-28 | 2026-07-09 | 2026-08-29 | 2026-07-28 | MOC | IN-115960 MOC-248275 | 51 | 1241640 | Completed | 833894 | Approved/Printed | 2026-07-19 | 2026-01-04 | NEWCON | 16128 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 43 | 43 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 5520 | 5520 | Completed | Pending | Pending | 625 |  |  |  | 2026-07-22 | Pending | Pending
626 | 252163 | 626 | 2026-06-29 | 2026-06-28 | 2026-07-09 | 2026-08-29 | 2026-09-12 | BP | BP154314 | 51 | 1241882 | Pending | Pending | Pending | Pending | Pending | NEWCON | 31551 | 1 | Musaimeer(46) | 14 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2 |  | 1 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 2080 |  | Pending | Pending | Pending | 626 |  |  |  |  | Pending | Pending
627 | 252164 | 627 | 2026-06-29 | 2026-06-28 | 2026-07-09 | 2026-09-29 | 2026-09-12 | BP | BP154317 | 82 | 1241883 | Pending | Pending | Pending | Pending | Pending | NEWCON | 11506 | 1 | Musaimeer(46) | 20 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 1850 |  | Pending | Pending | Pending | 627 |  |  |  |  | Pending | Pending
628 | 252165 | 628 | 2026-06-29 | 2026-06-28 | 2026-07-09 | 2026-09-29 | 2026-09-12 | BP | BP154318 | 82 | 1241884 | Pending | Pending | Pending | Pending | Pending | NEWCON | 11505 | 1 | Musaimeer(46) | 30 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 2450 |  | Pending | Pending | Pending | 628 |  |  |  |  | Pending | Pending
629 | 252166 | 629 | 2026-06-29 | 2026-06-28 | 2026-07-09 | 2026-09-29 | 2026-09-12 | BP | BP154339 | 82 | 1241885 | Pending | Pending | Pending | Pending | Pending | NEWCON | 25915 | 1 | Al Duhail(South) | 68 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 4770 |  | Pending | Pending | Pending | 629 |  |  |  |  | Pending | Pending
630 | 252167 | 630 | 2026-06-29 | 2026-06-28 | 2026-07-09 | 2026-09-29 | 2026-09-12 | BP | BP154698 | 82 | 1241886 | Pending | 837395 | Approved/Printed | 2026-08-16 | 2027-02-06 | NEWCON | 2810 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 79 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 5390 |  | Pending | Pending | Pending | 630 |  |  |  |  | Pending | Pending
631 | 252168 | 631 | 2026-06-29 | 2026-06-28 | 2026-07-09 | 2026-09-29 | 2026-09-12 | BP | BP154734 | 82 | 1241887 | Pending | 837395 | Approved/Printed | 2026-08-16 | 2027-02-06 | NEWCON | 19694 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 118 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2 |  | 2 |  | 0 | 0 | 0 |  | 0 | 0 | 8460 |  | Pending | Pending | Pending | 631 |  |  |  |  | Pending | Pending
632 | 252169 | 632 | 2026-06-29 | 2026-06-28 | 2026-07-09 | 2026-09-29 | 2026-09-12 | BP | BP#154786+BP#154785 | 82 | 1241888 | Pending | 838765 | Approved/Printed | 2026-09-05 | 2027-03-04 | NEWCON | 36216 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 53 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 |  | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 3870 |  | Pending | Pending | Pending | 632 |  |  |  |  | Pending | Pending
633 | 252243 | 633 | 2026-06-30 | 2026-06-29 | 2026-07-10 | 2026-09-30 | 2026-09-12 | BP | BP154701 | 82 | 1242262 | Pending | Pending | Pending | Pending | Pending | NEWCON | 12129 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 48 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3530 |  | Pending | Pending | Pending | 633 |  |  |  |  | Pending | Pending
634 | 252244 | 634 | 2026-06-30 | 2026-06-29 | 2026-07-10 | 2026-09-30 | 2026-09-12 | BP | BP154631 | 82 | 1242263 | Pending | 838765 | Approved/Printed | 2026-09-05 | 2027-03-04 | NEWCON | 25897 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 51 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3710 |  | Pending | Pending | Pending | 634 |  |  |  |  | Pending | Pending
635 | 252245 | 635 | 2026-06-30 | 2026-06-29 | 2026-07-10 | 2026-09-30 | 2026-09-12 | BP | BP#N/2026/1263(PIN15410015) | 82 | 1242264 | Pending | 837398 | Approved/Printed | 2026-08-24 | 2027-02-13 | NEWCON | 0433 | 1 | Al Doha Al Jadeeda (15 ) | 96 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6450 |  | Pending | Pending | Pending | 635 |  |  |  |  | Pending | Pending
636 | 252246 | 636 | 2026-06-30 | 2026-06-29 | 2026-07-10 | 2026-09-30 | 2026-09-12 | BP | BP154778 | 82 | 1242267 | Pending | Pending | Pending | Pending | Pending | NEWCON | 25543 | 1 | Al Kheesa (70 ) | 117 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7670 |  | Pending | Pending | Pending | 636 |  |  |  |  | Pending | Pending
637 | 252247 | 637 | 2026-06-30 | 2026-06-29 | 2026-07-10 | 2026-09-30 | 2026-09-12 | BP | BP152804 | 82 | 1242268 | Pending | Pending | Pending | Pending | Pending | NEWCON | 2664 | 1 | Al Kheesa (70 ) | 111 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 2 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8000 |  | Pending | Pending | Pending | 637 |  |  |  |  | Pending | Pending
638 | 252248 | 638 | 2026-06-30 | 2026-06-29 | 2026-07-10 | 2026-09-30 | 2026-09-12 | BP | BP154757 | 82 | 1242269 | Pending | Pending | Pending | Pending | Pending | NEWCON | 13470 | 1 | Al Kheesa (70 ) | 186 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11810 |  | Pending | Pending | Pending | 638 |  |  |  |  | Pending | Pending
639 | 252344 | 639 | 2026-07-02 | 2026-07-01 | 2026-07-12 | 2026-10-02 | 2026-09-12 | BP | BP154824 | 82 | 1242984 | Pending | 838766 | Approved/Printed | 2026-09-07 | 2027-03-06 | NEWCON | 4146 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 64 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 4 |  | 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8450 |  | Pending | Pending | Pending | 639 |  |  |  |  | Pending | Pending
640 | 252353 | 640-P1 | 2026-08-23 | 2026-08-22 | 2026-09-02 | 2026-10-23 | 2026-09-12 | MOC | IN-116884 MOC-253896+97 | 51 | 1242990 | WORK IN PROGRESS | 839317 | Approved/Printed | 2026-08-27 | 2027-02-23 | NEWCON | 19961 | 2 | Najma(26) | 476 | 476 | 0 | 0 | 0 | 0 | 372 | 372 | 104 | 104 | 0 | 0 | 0 | 0 | 2 | 2 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60794 | 60794 | WORK IN PROGRESS | Pending | Pending | 640 |  |  |  | 2026-09-08 | Pending | Pending
641 | 252367 | 641 | 2026-07-02 | 2026-07-01 | 2026-07-12 | 2026-10-02 | 2026-09-12 | BP | BP-N/2026/977 (PIN34430025) | 82 | 1243003 | Pending | Pending | Pending | Pending | Pending | NEWCON | 22762 | 1 | Madinat Khalifa(South)(34) | 117 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7710 |  | Pending | Pending | Pending | 641 |  |  |  |  | Pending | Pending
642 | 252389 | 642 | 2026-07-02 | 2026-07-01 | 2026-07-12 | 2026-10-02 | 2026-09-12 | BP | BP155064 | 82 | 1243033 | Pending | 838766 | Approved/Printed | 2026-09-07 | 2027-03-06 | NEWCON | 12925 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 80 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5490 |  | Pending | Pending | Pending | 642 |  |  |  |  | Pending | Pending
643 | 252390 | 643 | 2026-07-02 | 2026-07-01 | 2026-07-12 | 2026-10-02 | 2026-09-12 | BP | BP153863 | 82 | 1243034 | Pending | Pending | Pending | Pending | Pending | NEWCON | 0042 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 135 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 9540 |  | Pending | Pending | Pending | 643 |  |  |  |  | Pending | Pending
644 | 252391 | 644 | 2026-07-02 | 2026-07-01 | 2026-07-12 | 2026-10-02 | 2026-09-12 | BP | BP154732 | 82 | 1243035 | Pending | 838766 | Approved/Printed | 2026-09-07 | 2027-03-06 | NEWCON | 4850 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 201 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 |  | 2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 13950 |  | Pending | Pending | Pending | 644 |  |  |  |  | Pending | Pending
645 | 252392 | 645 | 2026-07-26 | 2026-07-25 | 2026-08-05 | 2026-09-24 | 2026-08-16 | MOC | IN#116522 MOC-252756 | 50 | 1243037 | Completed | 837433 | Approved/Printed | 2026-08-09 | 2027-01-28 | NEWCON | 20665 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 22 | 22 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 5124 | 5124 | Completed | Pending | Pending | 645 |  |  |  | 2026-08-11 | Pending | Pending
646 | 252433 | 646 | 2026-07-06 | 2026-07-05 | 2026-07-16 | 2026-10-06 | 2026-09-12 | BP | BP154284 | 82 | 1243948 | Pending | Pending | Pending | Pending | Pending | NEWCON | 1912 | 1 | New District Of Doha 67(67) | 69 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5420 |  | Pending | Pending | Pending | 646 |  |  |  |  | Pending | Pending
647 | 252434 | 647 | 2026-07-06 | 2026-07-05 | 2026-07-16 | 2026-10-06 | 2026-09-12 | BP | BP154443 | 82 | 1243954 | Pending | Pending | Pending | Pending | Pending | NEWCON | 3509 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 72 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5600 |  | Pending | Pending | Pending | 647 |  |  |  |  | Pending | Pending
648 | 252435 | 648 | 2026-07-06 | 2026-07-05 | 2026-07-16 | 2026-10-06 | 2026-09-12 | BP | BP155194 | 82 | 1243956 | Pending | 841112 | Approved/Printed | 2026-08-29 | 2027-02-25 | NEWCON | 17905 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 194 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 12920 |  | Pending | Pending | Pending | 648 |  |  |  |  | Pending | Pending
649 | 252436 | 649 | 2026-07-06 | 2026-07-05 | 2026-07-16 | 2026-10-06 | 2026-09-12 | BP | BP155004 | 82 | 1243957 | Pending | 837400 | Approved/Printed | 2026-08-22 | 2027-02-18 | NEWCON | 13105 | 1 | Madinat Al Shamal/Al Ruwais(79) | 97 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7100 |  | Pending | Pending | Pending | 649 |  |  |  |  | Pending | Pending
650 | 252465 | 650 | 2026-07-06 | 2026-07-05 | 2026-07-16 | 2026-10-06 | 2026-09-12 | BP | BP155110 | 82 | 1244044 | Pending | Pending | Pending | Pending | Pending | NEWCON | 4947 | 1 | Al Kheesa (70 ) | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950 |  | Pending | Pending | Pending | 650 |  |  |  |  | Pending | Pending
651 | 252466 | 651 | 2026-07-06 | 2026-07-05 | 2026-07-16 | 2026-10-06 | 2026-09-12 | BP | BP155149 | 82 | 1244045 | Pending | Pending | Pending | Pending | Pending | NEWCON | 3080 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 103 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7460 |  | Pending | Pending | Pending | 651 |  |  |  |  | Pending | Pending
652 | 252467 | 652 | 2026-07-06 | 2026-07-05 | 2026-07-16 | 2026-10-06 | 2026-09-12 | BP | BP#N/2025/8699 (PIN33120114) | 82 | 1244047 | Pending | Pending | Pending | Pending | Pending | NEWCON | 3417 | 1 | Al Markhiya (33 ) | 157 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10110 |  | Pending | Pending | Pending | 652 |  |  |  |  | Pending | Pending
653 | 252468 | 653 | 2026-07-06 | 2026-07-05 | 2026-07-16 | 2026-10-06 | 2026-09-12 | BP | BP155074 | 82 | 1244047 | Pending | Pending | Pending | Pending | Pending | NEWCON | 1814 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 318 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 20360 |  | Pending | Pending | Pending | 653 |  |  |  |  | Pending | Pending
654 | 252469 | 654 | 2026-07-06 | 2026-07-05 | 2026-07-16 | 2026-10-06 | 2026-09-12 | BP | BP155070 | 82 | 1244049 | Not Clear | Pending | Hold | Pending | Pending | NEWCON | 5125 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 104 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6890 |  | Pending | Pending | Pending | 654 |  |  |  |  | Pending | Pending
655 | 252500 | 655 | 2026-07-07 | 2026-07-06 | 2026-07-17 | 2026-10-07 | 2026-09-12 | BP | BP155188 | 82 | 1244449 | Pending | Pending | Pending | Pending | Pending | NEWCON | 11500 | 1 | Musaimeer(46) | 33 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2670 |  | Pending | Pending | Pending | 655 |  |  |  |  | Pending | Pending
656 | 252502 | 656 | 2026-07-07 | 2026-07-06 | 2026-07-17 | 2026-10-07 | 2026-09-12 | BP | BP155227 | 82 | 1244475 | Pending | Pending | Pending | Pending | Pending | NEWCON | 2801 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 80 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5490 |  | Pending | Pending | Pending | 656 |  |  |  |  | Pending | Pending
657 | 252503 | 657 | 2026-07-07 | 2026-07-06 | 2026-07-17 | 2026-10-07 | 2026-09-12 | BP | BP154665 | 82 | 1244486 | Pending | 838766 | Approved/Printed | 2026-09-07 | 2027-03-06 | NEWCON | 16294 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 53 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4460 |  | Pending | Pending | Pending | 657 |  |  |  |  | Pending | Pending
658 | 252512 | 658 | 2026-07-07 | 2026-07-06 | 2026-07-17 | 2026-09-07 | 2026-08-15 | MOC | IN-116315 MOC-252738+39+40+41 | 52 | 1244502 | Completed | 835032 | Approved/Printed | 2026-07-22 | 2027-01-11 | NEWCON | 41418 | 4 | Madinat Khalifa(South)(34) | 107 | 107 | 0 | 0 | 0 | 0 | 90 | 90 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 16210 | 16210 | Completed | Pending | Pending | 658 |  |  |  | 2026-08-09 | Pending | Pending
659 | 252514 | 659 | 2026-07-07 | 2026-07-06 | 2026-07-17 | 2026-09-07 | 2026-08-05 | MOC | C-83196(MSA-18038528) | 52 | 1244506 | Completed | 833201 | Approved/Printed | 2026-07-26 | 2027-01-21 | NEWCON | 18332 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 38 | 38 | 0 | 0 | 0 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 |  | 2 | 2 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 6976 | 6976 | Completed | Pending | Pending | 659 |  |  |  | 2026-08-04 | Pending | Pending
660 | 252518 | 660 | 2026-07-07 | 2026-07-06 | 2026-07-17 | 2026-10-07 | 2026-09-12 | BP | BP154833 | 82 | 1244513 | Pending | Pending | Pending | Pending | Pending | NEWCON | 34545 | 1 | Al Kheesa (70 ) | 130 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7860 |  | Pending | Pending | Pending | 660 |  |  |  |  | Pending | Pending
661 | 252519 | 661 | 2026-07-07 | 2026-07-06 | 2026-07-17 | 2026-10-07 | 2026-09-12 | BP | BP155100 | 82 | 1244514 | Pending | Pending | Pending | Pending | Pending | NEWCON | 3053 | 1 | New District Of Doha 65(65) | 38 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2970 |  | Pending | Pending | Pending | 661 |  |  |  |  | Pending | Pending
662 | 252526 | 662 | 2026-07-08 | 2026-07-07 | 2026-07-18 | 2026-10-08 | 2026-09-12 | BP | BP155288 | 82 | 1244831 | Pending | Pending | Pending | Pending | Pending | NEWCON | 20596 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510 |  | Pending | Pending | Pending | 662 |  |  |  |  | Pending | Pending
663 | 252527 | 663 | 2026-07-08 | 2026-07-07 | 2026-07-18 | 2026-10-08 | 2026-09-12 | BP | BP154686 | 82 | 1244834 | Pending | Pending | Pending | Pending | Pending | NEWCON | 40066 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 145 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9350 |  | Pending | Pending | Pending | 663 |  |  |  |  | Pending | Pending
664 | 252549 | 664 | 2026-07-08 | 2026-07-07 | 2026-07-18 | 2026-10-08 | 2026-09-12 | BP | BP155417 | 82 | 1244875 | Pending | 838767 | Approved/Printed | 2026-09-09 | 2027-03-08 | NEWCON | 38232 | 1 | Al Salata Al Jadeeda/Al Asiri(40) | 275 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17150 |  | Pending | Pending | Pending | 664 |  |  |  |  | Pending | Pending
665 | 252550 | 665 | 2026-07-21 | 2026-07-20 | 2026-07-31 | 2026-09-21 | 2026-07-30 | MOC | IN-116451 MOC-253473 | 52 | 1244876 | Completed | 837603 | Approved/Printed | 2026-07-28 | 2026-08-12 | NEWCON | 14338 | 1 | Al Nuaija(East)(44) | 15 | 15 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3464 | 3464 | Invoiced | Invoiced | 13 | 665 |  |  |  | 2026-07-28 | Completed | Invoiced
666 | 252551 | 666 | 2026-07-08 | 2026-07-07 | 2026-07-18 | 2026-10-08 | 2026-09-12 | BP | BP155166 | 82 | 1244878 | Pending | 838766 | Approved/Printed | 2026-09-07 | 2027-03-06 | NEWCON | 18964 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 79 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5390 |  | Pending | Pending | Pending | 666 |  |  |  |  | Pending | Pending
667 | 252601 | 667 | 2026-07-12 | 2026-07-11 | 2026-07-22 | 2026-10-12 | 2026-09-12 | BP | BP155532 | 82 | 1245942 | Pending | Pending | Pending | Pending | Pending | NEWCON | 19608 | 1 | Al Nuaija(West)(43) | 96 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6450 |  | Pending | Pending | Pending | 667 |  |  |  |  | Pending | Pending
668 | 252602 | 668 | 2026-07-12 | 2026-07-11 | 2026-07-22 | 2026-10-12 | 2026-09-12 | BP | BP155603 | 82 | 1245946 | Pending | 843432 | In Review | Pending | Pending | NEWCON | 23903 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 92 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6170 |  | Pending | Pending | Pending | 668 |  |  |  |  | Pending | Pending
669 | 252604 | 669 | 2026-07-12 | 2026-07-11 | 2026-07-22 | 2026-10-12 | 2026-09-12 | BP | BP155505 | 82 | 1245949 | Pending | 843435 | In Review | Pending | Pending | NEWCON | 36217 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 49 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3590 |  | Pending | Pending | Pending | 669 |  |  |  |  | Pending | Pending
670 | 252651 | 670 | 2026-07-12 | 2026-07-11 | 2026-07-22 | 2026-09-12 | 2026-08-11 | MOC | C-980393 (MSA-18038581) | 52 | 1246019 | Completed | 833203 | Approved/Printed | 2026-07-25 | 2027-01-21 | NEWCON | 34787 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 65 | 65 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 8590 | 8590 | Completed | Pending | Pending | 670 |  |  |  | 2026-08-06 | Pending | Pending
671 | 252657 | 671 | 2026-07-12 | 2026-07-11 | 2026-07-22 | 2026-10-12 | 2026-09-12 | BP | BP155138 | 82 | 1246030 | Pending | Pending | Pending | Pending | Pending | NEWCON | 20266 | 1 | Al Matar Al Qadeem(45 ) | 339 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20990 |  | Pending | Pending | Pending | 671 |  |  |  |  | Pending | Pending
672 | 252664 | 672 | 2026-07-13 | 2026-07-12 | 2026-07-23 | 2026-09-13 | 2026-07-28 | MOC | IN#113719 MOC#231998 | 52 | 1246260 | Completed | 833203 | Approved/Printed | 2026-07-25 | 2027-01-21 | NEWCON | 21884 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 3900 | 3900 | Completed | Pending | Pending | 672 |  |  |  | 2026-07-27 | Pending | Pending
673 | 252805 | 673 | 2026-07-19 | 2026-07-18 | 2026-07-29 | 2026-10-19 | 2026-09-12 | BP | BP154215 | 82 | 1247724 | Pending | Pending | Pending | Pending | Pending | NEWCON | 20788 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 189 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11990 |  | Pending | Pending | Pending | 673 |  |  |  |  | Pending | Pending
674 | 252806 | 674 | 2026-07-19 | 2026-07-18 | 2026-07-29 | 2026-10-19 | 2026-09-12 | BP | BP154261 | 82 | 1247726 | Pending | Pending | Pending | Pending | Pending | NEWCON | 12061 | 1 | New District Of Doha 67(67) | 26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2840 |  | Pending | Pending | Pending | 674 |  |  |  |  | Pending | Pending
675 | 252807 | 675 | 2026-07-19 | 2026-07-18 | 2026-07-29 | 2026-10-19 | 2026-09-12 | BP | BP155725 | 82 | 1247727 | Pending | Pending | Pending | Pending | Pending | NEWCON | 19359 | 1 | Madinat Khalifa(South)(34) | 99 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6590 |  | Pending | Pending | Pending | 675 |  |  |  |  | Pending | Pending
676 | 252808 | 676 | 2026-07-19 | 2026-07-18 | 2026-07-29 | 2026-10-19 | 2026-09-12 | BP | BP-N/2026/652 (PIN 34010043) | 82 | 1247728 | Pending | Pending | Pending | Pending | Pending | NEWCON | 0140 | 1 | Madinat Khalifa(South)(34) | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950 |  | Pending | Pending | Pending | 676 |  |  |  |  | Pending | Pending
677 | 252809 | 677 | 2026-07-19 | 2026-07-18 | 2026-07-29 | 2026-10-19 | 2026-09-12 | BP | BP155614 | 82 | 1247731 | Pending | 839315 | Approved/Printed | 2026-09-01 | 2027-02-18 | NEWCON | 17217 | 1 | Al Shahhniya (80 ) | 116 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8240 |  | Pending | Pending | Pending | 677 |  |  |  |  | Pending | Pending
678 | 252887 | 678 | 2026-07-20 | 2026-07-19 | 2026-07-30 | 2026-09-20 | 2026-08-26 | MOC | IN-116399 MOC-231584 | 52 | 1248065 | Completed | 836890 | Approved/Printed | 2026-08-04 | 2027-01-28 | NEWCON | 40521 | 1 | New District Of Doha 67(67) | 146 | 146 | 27 | 27 |  |  | 146 | 146 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 4 | 4 | 3 | 3 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 22932 | 22932 | Completed | Pending | Pending | 678 |  |  |  | 2026-08-23 | Pending | Pending
679 | 252898 | 679 | 2026-07-21 | 2026-07-20 | 2026-07-31 | 2026-10-21 | 2026-09-12 | BP | BP155210 | 82 | 1248295 | Pending | 843435 | In Review | Pending | Pending | NEWCON | 26559 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 531 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32510 |  | Pending | Pending | Pending | 679 |  |  |  |  | Pending | Pending
680 | 252899 | 680 | 2026-07-21 | 2026-07-20 | 2026-07-31 | 2026-10-21 | 2026-09-12 | BP | BP155376 | 82 | 1248297 | Pending | Pending | Pending | Pending | Pending | NEWCON | 3284 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 83 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5630 |  | Pending | Pending | Pending | 680 |  |  |  |  | Pending | Pending
681 | 252900 | 681 | 2026-07-21 | 2026-07-20 | 2026-07-31 | 2026-10-21 | 2026-09-12 | BP | BP155385 | 82 | 1248298 | Cancelled | Pending | Cancelled | Cancelled | Cancelled | NEWCON | 0786 | 1 | Al Luqta/Al Rayyan Al Qadeem (52 ) | 54 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3930 |  | Cancelled | Cancelled | Cancelled | 681 |  |  |  |  | Cancelled | Cancelled
682 | 252964 | 682 | 2026-07-21 | 2026-07-20 | 2026-07-31 | 2026-10-21 | 2026-09-12 | BP | BP155701 | 82 | 1248439 | Pending | 838768 | Approved/Printed | 2026-09-10 | 2027-03-09 | NEWCON | 27119 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 81 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6140 |  | Pending | Pending | Pending | 682 |  |  |  |  | Pending | Pending
683 | 252965 | 683 | 2026-07-21 | 2026-07-20 | 2026-07-31 | 2026-10-21 | 2026-09-12 | BP | BP155465+BP155467 | 82 | 1248441 | Not Clear | Pending | Hold | Pending | Pending | NEWCON | 5122 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 188 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 12560 |  | Pending | Pending | Pending | 683 |  |  |  |  | Pending | Pending
684 | 253035 | 684 | 2026-07-23 | 2026-07-22 | 2026-08-02 | 2026-10-23 | 2026-09-12 | BP | BP155444 | 82 | 1249381 | Pending | 838768 | Approved/Printed | 2026-09-10 | 2027-03-09 | NEWCON | 39507 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 990 |  | Pending | Pending | Pending | 684 |  |  |  |  | Pending | Pending
685 | 253036 | 685 | 2026-07-23 | 2026-07-22 | 2026-08-02 | 2026-10-23 | 2026-09-12 | BP | BP155659 | 82 | 1249383 | Pending | Pending | Pending | Pending | Pending | NEWCON | 13514 | 1 | Al Kheesa (70 ) | 46 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3450 |  | Pending | Pending | Pending | 685 |  |  |  |  | Pending | Pending
686 | 253037 | 686 | 2026-07-23 | 2026-07-22 | 2026-08-02 | 2026-10-23 | 2026-09-12 | BP | BP156016 | 82 | 1249385 | Pending | 838768 | Approved/Printed | 2026-09-10 | 2027-03-09 | NEWCON | 9939 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 208 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 13170 |  | Pending | Pending | Pending | 686 |  |  |  |  | Pending | Pending
687 | 253038 | 687 | 2026-07-23 | 2026-07-22 | 2026-08-02 | 2026-10-23 | 2026-09-12 | BP | BP155970 | 82 | 1249387 | Pending | Pending | Pending | Pending | Pending | NEWCON | 5193 | 1 | Al Matar Al Qadeem(45 ) | 54 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3930 |  | Pending | Pending | Pending | 687 |  |  |  |  | Pending | Pending
688 | 253039 | 688 | 2026-07-23 | 2026-07-22 | 2026-08-02 | 2026-10-23 | 2026-09-12 | BP | BP155644 | 82 | 1249389 | Pending | 839314 | Approved/Printed | 2026-09-01 | Pending | NEWCON | 40527 | 1 | Al Wakra (90 ) | 155 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 9990 |  | Pending | Pending | Pending | 688 |  |  |  |  | Pending | Pending
689 | 253141 | 689 | 2026-07-26 | 2026-07-25 | 2026-08-05 | 2026-09-24 | 2026-08-31 | MOC | IN#116444 MOC#246203 | 50 | 1250239 | Completed | 837433 | Approved/Printed | 2026-08-09 | 2027-01-28 | NEWCON | 4095 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 81 | 81 | 32 | 32 | 0 | 0 | 81 | 81 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 13837 | 13837 | Completed | Pending | Pending | 689 |  |  |  | 2026-08-23 | Pending | Pending
689 | 253141 | 689-P2 | 2026-07-26 | 2026-07-25 | 2026-08-05 | 2026-09-24 | 2026-08-31 | MOC | IN#116444 MOC#246203 | 50 | 1250239 | Completed | 837433 | Approved/Printed | 2026-08-09 | 2027-01-28 | NEWCON | 4095 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 7 | 7 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2099 | 2099 | Completed | Pending | Pending | 689 |  |  |  | 2026-09-01 | Pending | Pending
690 | 253163 | 690 | 2026-07-27 | 2026-07-26 | 2026-08-06 | 2026-09-25 | 2026-08-17 | MOC | IN#114458 MOC#250561 | 50 | 1250516 | Completed | 837857 | Approved/Printed | 2026-08-06 | 2027-01-28 | NEWCON | 30161 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 177 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 13010 | 13010 | Completed | Pending | Pending | 690 |  |  |  | 2026-08-13 | Pending | Pending
691 | 253220 | 691 | 2026-07-28 | 2026-07-27 | 2026-08-07 | 2026-09-26 | 2026-08-19 | MOC | C-129677 MSA-18038684 | 50 | 1250951 | Completed | 838251 | Approved/Printed | 2026-08-08 | 2026-10-10 | NEWCON | 1295 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 43 | 43 | 0 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 29 | 29 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 10896 | 10896 | Completed | Pending | Pending | 691 |  |  |  | 2026-08-23 | Pending | Pending
691 | 253220 | 691-P2 | 2026-07-28 | 2026-07-27 | 2026-08-07 | 2026-09-26 | 2026-08-19 | MOC | C-129677 MSA-18038684 | 50 | 1250951 | Completed | 838251 | Approved/Printed | 2026-08-08 | 2026-10-10 | NEWCON | 1295 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 77 | 77 | 0 | 0 | 0 | 0 | 17 | 17 | 0 | 0 | 156 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 31149 | 31149 | Completed | Pending | Pending | 691 |  |  |  | 2026-09-07 | Pending | Pending
692 | 253216 | 692 | 2026-07-27 | 2026-07-26 | 2026-08-06 | 2026-10-27 | 2026-09-12 | BP | BP155832 | 82 | 1250732 | Pending | Pending | Pending | Pending | Pending | NEWCON | 20474 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3140 |  | Pending | Pending | Pending | 692 |  |  |  |  | Pending | Pending
693 | 253217 | 693 | 2026-07-27 | 2026-07-26 | 2026-08-06 | 2026-10-27 | 2026-09-12 | BP | BP156022 | 82 | 1250733 | Pending | Pending | Pending | Pending | Pending | NEWCON | 2100 | 1 | Madinat Khalifa(South)(34) | 233 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 14670 |  | Pending | Pending | Pending | 693 |  |  |  |  | Pending | Pending
694 | 253288 | 694 | 2026-07-28 | 2026-07-27 | 2026-08-07 | 2026-10-28 | 2026-09-12 | BP | BP154668 | 82 | 1251167 | Pending | Pending | Pending | Pending | Pending | NEWCON | 22351 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3050 |  | Pending | Pending | Pending | 694 |  |  |  |  | Pending | Pending
695 | 253289 | 695 | 2026-07-28 | 2026-07-27 | 2026-08-07 | 2026-09-26 | 2026-08-13 | MOC | C-37296+37297MSA-18037546+550 | 50 | 1251219 | Completed | 838447 | Approved/Printed | 2026-08-04 | 2026-08-19 | NEWCON | 3905 | 2 | Al Mirqab Al Jadeed/Al Nasr (39 ) | 94 | 94 | 0 | 0 | 0 | 0 | 94 | 94 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 3 | 3 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 14138 | 14138 | Completed | Pending | Pending | 695 |  |  |  | 2026-08-06 | Pending | Pending
696 | 253378 | 696 | 2026-07-29 | 2026-07-28 | 2026-08-08 | 2026-10-29 | 2026-09-12 | BP | BP-N/2025/2171 (PIN71051333) | 82 | 1251661 | Pending | 843432 | In Review | Pending | Pending | NEWCON | 34114 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 68 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4140 |  | Pending | Pending | Pending | 696 |  |  |  |  | Pending | Pending
697 | 253743 | 697 | 2026-08-06 | 2026-08-05 | 2026-08-16 | 2026-11-06 | 2026-09-12 | BP | BP156183 | 82 | 1253940 | Pending | Pending | Pending | Pending | Pending | NEWCON | 16314 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3350 |  | Pending | Pending | Pending | 697 |  |  |  |  | Pending | Pending
698 | 253751 | 698 | 2026-08-06 | 2026-08-05 | 2026-08-16 | 2026-11-06 | 2026-09-12 | BP | BP156405 | 82 | 1253956 | Pending | Pending | Pending | Pending | Pending | NEWCON | 11409 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 57 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4110 |  | Pending | Pending | Pending | 698 |  |  |  |  | Pending | Pending
699 | 253836 | 699 | 2026-08-09 | 2026-08-08 | 2026-08-19 | 2026-10-09 | 2026-09-12 | MOC | IN-116750 MOC-251628 | 51 | 1254617 | Pending | 841573/ 841462 | Approved/Printed | 2026-09-01 | 2027-02-25 | NEWCON | 10049 | 1 | Al Kheesa (70 ) | 308 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 19340 |  | Pending | Pending | Pending | 699 |  |  |  |  | Pending | Pending
700 | 253839 | 700 | 2026-08-09 | 2026-08-08 | 2026-08-19 | 2026-11-09 | 2026-09-12 | BP | BP149392 | 82 | 1254627 | WORK IN PROGRESS | Pending | Pending | Pending | Pending | NEWCON | 1643 | 1 | New District Of Doha 65(65) | 248 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15530 |  | Pending | Pending | Pending | 700 |  |  |  |  | Pending | Pending
701 | 253921 | 701 | 2026-08-10 | 2026-08-09 | 2026-08-20 | 2026-10-10 | 2026-09-08 | MOC | C-146330A(MSA+18039268) | 51 | 1254913 | Completed | 840733 | Approved/Printed | 2026-08-31 | 2027-02-18 | NEWCON | 4316 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 18 | 18 | 0 | 0 | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 4006 | 4006 | Completed | Pending | Pending | 701 |  |  |  | 2026-09-07 | Pending | Pending
702 | 254038 | 702 | 2026-08-12 | 2026-08-11 | 2026-08-22 | 2026-10-12 | 2026-09-09 | MOC | IN-116675 MOC-248122 | 51 | 1255640 | Completed | 840734 | Approved/Printed | 2026-08-24 | 2027-02-18 | NEWCON | 13515 | 1 | Al Kheesa (70 ) | 145 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 4 | 0 | 0 | 1 | 1 | 0 | 0 | 11800 | 11800 | Completed | Pending | Pending | 702 |  |  |  | 2026-09-06 | Pending | Pending
703 | 254163 | 703 | 2026-09-08 | 2026-09-07 | 2026-09-18 | 2026-11-08 | 2026-09-12 | MOC | IN-116691 MOC-247178+79 | 51 | 1256617 | Pending | Pending | Pending | Pending | Pending | NEWCON | 14854 | 1 | Al Duahil(30) | 61 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 2 |  | 0 | 0 | 1 |  | 0 | 0 | 5560 |  | Pending | Pending | Pending | 703 |  |  |  |  | Pending | Pending
704 | 254164 | 704 | 2026-08-16 | 2026-08-15 | 2026-08-26 | 2026-10-16 | 2026-09-12 | MOC | IN-116729 MOC-219890 | 51 | 1256619 | Pending | 841403 | Approved/Printed | 2026-09-07 | 2027-02-25 | NEWCON | 14948 | 1 | Madinat Khalifa(South)(34) | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 4770 |  | Pending | Pending | Pending | 704 |  |  |  |  | Pending | Pending
705 | 254167 | 705 | 2026-08-17 | 2026-08-16 | 2026-08-27 | 2026-10-17 | 2026-09-08 | MOC | IN-116812 MOC-232560 | 51 | 1256883 | Completed | 841123 | Approved/Printed | 2026-08-31 | 2026-11-07 | NEWCON | 25155 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 4850 | 4850 | Completed | Pending | Pending | 705 |  |  |  | 2026-09-07 | Pending | Pending
706 | 254330 | 706 | 2026-08-19 | 2026-08-18 | 2026-08-29 | 2026-10-19 | 2026-09-09 | MOC | IN-116921 MOC-253359 | 51 | 1257677 | Completed | 841573 | Approved/Printed | 2026-09-01 | 2027-02-25 | NEWCON | 22741 | 1 | Al Kheesa (70 ) | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 2610 | 2610 | Completed | Pending | Pending | 706 |  |  |  | 2026-09-07 | Pending | Pending
707 | 254386 | 707 | 2026-08-20 | 2026-08-19 | 2026-08-30 | 2026-10-20 | 2026-09-12 | MOC+BP | C-189150(MSA 18039428)+BP157168 | 51 | 1258055 | Pending | 842225 | Approved/Printed | 2026-09-08 | 2027-03-04 | NEWCON | 9986 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 37 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 4020 |  | Pending | Pending | Pending | 707 |  |  |  |  | Pending | Pending
708 | 254389 | 708 | 2026-08-20 | 2026-08-19 | 2026-08-30 | 2026-10-20 | 2026-09-12 | MOC | C-125143A(MSA-18039411) | 51 | 1258093 | Pending | 842415 | Technical Verification | Pending | Pending | NEWCON | 3253 | 1 | New District Of Doha 67(67) | 153 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 10980 |  | Pending | Pending | Pending | 708 |  |  |  |  | Pending | Pending
709 | 254390 | 709 | 2026-08-20 | 2026-08-19 | 2026-08-30 | 2026-10-20 | 2026-09-12 | MOC | IN-116877 MOC-255528 | 51 | 1258094 | WORK IN PROGRESS | 841827 | Approved/Printed | 2026-08-31 | 2027-02-25 | NEWCON | 4707 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 155 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 | 0 | 0 | 0 | 10450 |  | WORK IN PROGRESS | Pending | Pending | 709 |  |  |  |  | Pending | Pending
710 | 254451 | 710 | 2026-08-23 | 2026-08-22 | 2026-09-02 | 2026-10-23 | 2026-09-12 | MOC | C-1201570 9MSA-18039159) | 51 | 1258766 | Pending | 841573 | Approved/Printed | 2026-09-01 | 2027-02-25 | NEWCON | 13462 | 1 | Al Kheesa (70 ) | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 3550 |  | Pending | Pending | Pending | 710 |  |  |  |  | Pending | Pending
711 | 254629 | 711 | 2026-08-26 | 2026-08-25 | 2026-09-05 | 2026-10-26 | 2026-09-12 | MOC | C-159007A (MSA-18039140) | 51 | 1259770 | Pending | 842785 | Technical Verification | Pending | Pending | NEWCON | 4478 | 1 | Al Duhail South (31 ) | 70 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 6000 |  | Pending | Pending | Pending | 711 |  |  |  |  | Pending | Pending
712 | 254670 | 712 | 2026-08-27 | 2026-08-26 | 2026-09-06 | 2026-10-27 | 2026-09-07 | MOC | IN-116938 MOC-248969+70 | 51 | 1260092 | Completed | 843265 | Approved/Printed | 2026-09-05 | 2026-09-20 | NEWCON | 21882 | 1 | Al Khor (74 ) | 20 | 20 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 4940 | 4940 | Completed | Pending | Pending | 712 |  |  |  | 2026-09-06 | Pending | Pending
713 | 254733 | 713 | 2026-08-30 | 2026-08-29 | 2026-09-09 | 2026-10-30 | 2026-09-12 | MOC | IN-116968 MOC-255730 | 51 | 1260889 | Pending | 843534 | In Review/ NOC from QTCG | Pending | Pending | NEWCON | 35638 | 1 | Al Kheesa (70 ) | 162 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 11520 |  | Pending | Pending | Pending | 713 |  |  |  |  | Pending | Pending
714 | 254735 | 714 | 2026-08-30 | 2026-08-29 | 2026-09-09 | 2026-10-30 | 2026-09-12 | MOC | IN -116874 MOC-255731 | 51 | 1260893 | Pending | 843534 | In Review/ NOC from QTCG | Pending | Pending | NEWCON | 39027 | 1 | Al Kheesa (70 ) | 91 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 7260 |  | Pending | Pending | Pending | 714 |  |  |  |  | Pending | Pending
715 | 254895 | 715 | 2026-09-01 | 2026-08-31 | 2026-09-11 | 2026-11-01 | 2026-09-12 | MOC | C-13511 (MSA-18039365) | 51 | 1261676 | Pending | 844088 | In Review | Pending | Pending | NEWCON | 4291 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 74 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 5650 |  | Pending | Pending | Pending | 715 |  |  |  |  | Pending | Pending
716 | 254950 | 716 | 2026-09-02 | 2026-09-01 | 2026-09-12 | 2026-11-02 | 2026-09-12 | MOC | C-111456AA(MSA-18039606) | 51 | 1262023 | Pending | 844089 | In Review | Pending | Pending | NEWCON | 4478 | 1 | Al Duhail(South) | 55 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 5100 |  | Pending | Pending | Pending | 716 |  |  |  |  | Pending | Pending
717 | 254997 | 717 | 2026-09-03 | 2026-09-02 | 2026-09-13 | 2026-11-03 | 2026-09-12 | MOC | IN#116981+7047 MOC#256050+522 | 51 | 1262363 | Pending | 844495 | Shared RO | Pending | Pending | NEWCON | 23034 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 230 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 15600 |  | Pending | Pending | Pending | 717 |  |  |  |  | Pending | Pending
718 | 255066 | 718 | 2026-09-06 | 2026-09-05 | 2026-09-16 | 2026-11-06 | 2026-09-12 | MOC | IN-116843 MOC-241459+60 | 51 | 1263206 | Pending | Pending | Pending | Pending | Pending | NEWCON | 28501 | 1 | Al Khor (74 ) | 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | 0 | 0 | 2 |  | 2 |  | 2 |  | 0 | 0 | 2 |  | 0 | 0 | 6300 |  | Pending | Pending | Pending | 718 |  |  |  |  | Pending | Pending
719 | 255067 | 719 | 2026-09-06 | 2026-09-05 | 2026-09-16 | 2026-11-06 | 2026-09-12 | MOC | C-1065639(MSA-18039562) | 51 | 1263220 | Pending | Pending | Pending | Pending | Pending | NEWCON | 10814 | 1 | Al Gharrafa/Bani Hajer/Al Zagh(51 ) | 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 2520 |  | Pending | Pending | Pending | 719 |  |  |  |  | Pending | Pending
720 | 255126 | 720 | 2026-09-07 | 2026-09-06 | 2026-09-17 | 2026-12-07 | 2026-09-12 | OL | OL-F4-28919 | 81 | 1263649 | Pending | Pending | Pending | Pending | Pending | NEWCON | 28919 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 2770 |  | Pending | Pending | Pending | 720 |  |  |  |  | Pending | Pending
721 | 255156 | 721 | 2026-09-07 | 2026-09-06 | 2026-09-17 | 2026-09-17 | 2026-09-12 | MOC | IN-116967 MOC-216573 | 0 | 1263748 | Pending | 844495 | Shared RO | Pending | Pending | NEWCON | 16389 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 1810 |  | Pending | Pending | Pending | 721 |  |  |  |  | Pending | Pending
722 | 255169 | 722 | 2026-09-08 | 2026-09-07 | 2026-09-18 | 2026-11-08 | 2026-09-12 | MOC | C-159011A (MSA-18039457) | 51 | 1263960 | Pending | Pending | Pending | Pending | Pending | NEWCON | 159011 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 175 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 1 |  | 0 | 0 | 11710 |  | Pending | Pending | Pending | 722 |  |  |  |  | Pending | Pending
723 | 255261 | 723 | 2026-09-09 | 2026-09-08 | 2026-09-19 | 2026-12-09 | 2026-09-12 | BP | BP156746 | 81 | 1264414 | Pending | Pending | Pending | Pending | Pending | NEWCON | 4102 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 99 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6590 |  | Pending | Pending | Pending | 723 |  |  |  |  | Pending | Pending
724 | 255278 | 724 | 2026-09-09 | 2026-09-08 | 2026-09-19 | 2026-12-09 | 2026-09-12 | BP | BP156162 | 81 | 1264438 | Pending | Pending | Pending | Pending | Pending | NEWCON | 12610 | 1 | Umm Slal/Al Kharaitiyat (71 ) | 39 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2990 |  | Pending | Pending | Pending | 724 |  |  |  |  | Pending | Pending
[49 empty] | 0 | 0
[21 empty] | 65496 | 36954 | 1017 | 936 | 283 | 282 | 17440 | 17414 | 562 | 562 | 2383 | 2383 | 524 | 410 | 58 | 25 | 641 | 340 | 1063 | 642 | 1003 | 658 | 0 | 0 | 341 | 290 | 41 | 40 | 6762099 | 4579184 |  |  |  |  | 0
[21 empty] | 33552 | 6689 | 267 | 189 | 32 | 32 | 3645 | 3638 | 216 | 216 | 557 | 557 | 142 | 49 | 36 | 4 | 346 | 67 | 517 | 122 | 440 | 120 | 0 | 0 | 67 | 33 | 5 | 5
0
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Chandan will enter
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MOC-40 DAYS, BP/OFF LOAD-90DAYS
Note on AZ2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: to be planned/Planned/Finished
Note on BA2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending/Invoiced
Note on BD2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: manul type -invoiced vale
Note on BH2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending/Done
Note on BI2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending/Invoiced/Work in progress/Hold

## Sheet1
CABLE WORK SUMMARY - GTC 1240/2024- M/s. NEWCON
BOQ | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-02-01
TOTAL CWR | 123 | 84 | 105 | 77 | 15
TOTAL CABLE WORK ISSUED (KM) | 5.331 | 7.515 | 11.219 | 6.16 | 0.993
TOTAL NO OF S/D | 49 | 69 | 40 | 26 | 12
TOTAL CABLE WORK COMPLETED (KM) | 344 | 1729 | 4.226 | 2.847 | 0.953
TOTAL CABLE WORK NOT STARTED (KM) | 4987 | 5.786 | 6.993 | 2.398 | 19.941
TOTAL CABEL WORK IN PROGRESS (KM) | - | - | - | 1602 | 1760
.
AVERAGE OF XX KM FOR THE PAST YY MONTHS